## Sheet1
WBS Code | WBS Name | Total Activities | Remaining Duration | Start | Finish
19282-FS-CURRENT-35 | GEMCO Water Disposal FS Master Schedule - 16-01-2026 - Jan Update | 1678 | 605.9d | 22-Nov-23 A | 2027-08-17
19282-FS-CURRENT-35.5 | Environmental Approvals | 268 | 570.9d | 22-Nov-23 A | 2027-07-13
19282-FS-CURRENT-35.5.PGHN | Environmental Impact Assessment studies | 268 | 570.9d | 22-Nov-23 A | 2027-07-13
19282-FS-CURRENT-35.5.PGHN.1 | Project Milestones | 2 | 0.0d | 22-Nov-23 A | 01-May-25 A
19282-FS-CURRENT-35.5.PGHN.2 | Marine Ecology (Field Study)- On hold until future review) | 0 | 0.0d
19282-FS-CURRENT-35.5.PGHN.3 | Primary Approval Submission Process | 160 | 0.0d | 06-Dec-23 A | 01-May-25 A
19282-FS-CURRENT-35.5.PGHN.3.9 | Primary Approval Applications | 22 | 568.9d | 01-Jan-25 A | 2027-07-13
19282-FS-CURRENT-35.5.PGHN.7 | Secondary Approvals | 44 | 283.2d | 31-Mar-25 A | 2026-09-29
19282-FS-CURRENT-35.5.PGHN.4 | GHD - Supplementary Environmental Report (SER) | 40 | 225.9d | 03-Nov-25 A | 2026-08-04
19282-FS-CURRENT-35.6 | Base Case | 586 | 605.9d | 13-May-24 A | 2027-08-17
19282-FS-CURRENT-35.6.11 | Key Milestones | 19 | 575.7d | 2026-01-19 | 2027-08-17
19282-FS-CURRENT-35.6.1.3 | Design - IFT to IFC | 83 | 240.9d | 05-Aug-24 A | 2026-08-17
19282-FS-CURRENT-35.6.5 | Precommitment | 85 | 279.2d | 13-May-24 A | 2026-09-25
19282-FS-CURRENT-35.6.5.7 | Precommitment Approvals | 27 | 41.2d | 13-May-24 A | 2026-01-30
19282-FS-CURRENT-35.6.5.5 | Owners Team activities-1 | 0 | 0.0d
19282-FS-CURRENT-35.6.5.9 | Contracts and Supply Packages - Precommitment funding | 34 | 279.2d | 20-Oct-25 A | 2026-09-25
19282-FS-CURRENT-35.6.5.3 | Owners Team activities | 6 | 122.3d | 2026-01-23 | 2026-05-25
19282-FS-CURRENT-35.6.5.2 | Option 2 - Marine Contractor Negotiations | 0 | 0.0d
19282-FS-CURRENT-35.6.5.1 | NH2 to Port Procurement | 0 | 0.0d
19282-FS-CURRENT-35.6.5.10 | NH2 Procurement Precommitment - Company Supplied | 0 | 0.0d
19282-FS-CURRENT-35.6.5.4 | Marine Procurement - Contractor Supply | 0 | 0.0d
19282-FS-CURRENT-35.6.5.6 | Early Execution Works | 18 | 158.0d | 2026-03-15 | 2026-08-19
19282-FS-CURRENT-35.6.7 | Tollgate Phase | 43 | 285.8d | 01-Aug-25 A | 2026-10-01
19282-FS-CURRENT-35.6.7.5 | Preparation works for Tollgating - Partial Funding | 12 | 102.5d | 31-Oct-25 A | 2026-04-01
19282-FS-CURRENT-35.6.7.2 | Tollgate Partial Funding - Conditional Approval pending Regulatory Approvals | 6 | 24.9d | 2026-03-21 | 2026-04-14
19282-FS-CURRENT-35.6.7.4 | Contacts & Procurement | 0 | 0.0d
19282-FS-CURRENT-35.6.7.6 | Contracts and Procurement - Tollgate March Partial funding | 14 | 283.9d | 01-Aug-25 A | 2026-09-29
19282-FS-CURRENT-35.6.7.1 | Regulatory Approvals (Primary & Secondary) | 2 | 14.0d | 2026-08-06 | 2026-08-20
19282-FS-CURRENT-35.6.7.3 | Full Funding Confirmation of Primary Approval | 4 | 90.9d | 2026-04-09 | 2026-08-17
19282-FS-CURRENT-35.6.7.7 | Contracts and Procurement - August Full Funding (upon regulatory approvals receipt) | 5 | 48.9d | 2026-08-13 | 2026-10-01
19282-FS-CURRENT-35.6.10 | Contracts & Procurement | 0 | 0.0d
19282-FS-CURRENT-35.6.3 | Execution Works | 343 | 548.9d | 06-Oct-25 A | 2027-07-07
19282-FS-CURRENT-35.6.3.2 | Approvals & Permits | 5 | 177.0d | 2026-01-05 | 2026-06-30
19282-FS-CURRENT-35.6.3.3 | Design Confirmation Site Assesments | 4 | 14.0d | 06-Oct-25 A | 2026-07-06
19282-FS-CURRENT-35.6.3.1 | Onshore | 247 | 386.0d | 2026-04-06 | 2027-04-27
19282-FS-CURRENT-35.6.3.1.3 | S19 | 1 | 60.0d | 2026-08-20 | 2026-10-19
19282-FS-CURRENT-35.6.3.1.2 | WASCO | 241 | 313.0d | 2026-04-06 | 2027-02-13
19282-FS-CURRENT-35.6.3.1.2.1.1 | KEY DATES (MILESTONES) | 8 | 296.9d | 2026-04-06 | 2027-02-13
19282-FS-CURRENT-35.6.3.1.2.1.2.1 | PREPARATION & PRELIMINARY WORK | 42 | 164.0d | 2026-04-06 | 2026-09-17
19282-FS-CURRENT-35.6.3.1.2.1.2.2 | MOBILISE & CONSTRUCT | 191 | 253.0d | 2026-05-20 | 2027-02-12
19282-FS-CURRENT-35.6.3.1.2.1.2.2.1.2.2.1 | SP1 - EARLY WORKS | 28 | 116.6d | 2026-05-20 | 2026-09-21
19282-FS-CURRENT-35.6.3.1.2.1.2.2.1.2.2.2 | SP2 - MAIN WORKS | 155 | 237.9d | 2026-06-04 | 2027-02-12
19282-FS-CURRENT-35.6.3.1.2.1.2.2.1.2.2.2.1.2.2.2.1 | BARGE VOYAGES - EAST ARM TO MILNER BAY (SEASWIFT) | 1 | 0.0d | 2026-06-04 | 2026-06-04
19282-FS-CURRENT-35.6.3.1.2.1.2.2.1.2.2.2.1.2.2.2.2 | PIPELINE - EWP Stage 1 (ES to NH2) DN800 Single Line | 126 | 190.0d | 2026-07-02 | 2027-01-23
19282-FS-CURRENT-35.6.3.1.2.1.2.2.1.2.2.2.1.2.2.2.3 | Hydrostatic Testing | 2 | 20.0d | 2027-01-24 | 2027-02-12
19282-FS-CURRENT-35.6.3.1.2.1.2.2.1.2.2.2.1.2.2.2.4 | NH2 PUMPING FACILITY - CONCRETE WORKS | 26 | 94.3d | 2026-08-16 | 2026-12-04
19282-FS-CURRENT-35.6.3.1.2.1.2.2.1.2.2.3 | SP3 - OCEAN OUTFALL AREA | 8 | 78.0d | 2026-07-01 | 2026-09-24
19282-FS-CURRENT-35.6.3.1.2.1.2 | PROJECT MANAGEMENT | 0 | 0.0d
19282-FS-CURRENT-35.6.3.1.1 | Summary (superseded) | 5 | 228.0d | 2026-06-05 | 2027-04-27
19282-FS-CURRENT-35.6.3.1.5 | Marine Site works | 78 | 380.9d | 2026-04-22 | 2027-05-07
19282-FS-CURRENT-35.6.3.1.5.1.4.7 | Marine Mobilisation | 18 | 261.4d | 2026-04-22 | 2027-01-08
19282-FS-CURRENT-35.6.3.1.5.1.5.1 | Offshore works | 42 | 208.1d | 2026-09-18 | 2027-04-30
19282-FS-CURRENT-35.6.3.1.5.1.5.1.1.5.1.5 | Kingpile wall (135m) | 30 | 97.0d | 2026-10-26 | 2027-02-16
19282-FS-CURRENT-35.6.3.1.5.1.5.1.1 | Excavation & Backfill | 8 | 84.0d | 2027-02-05 | 2027-04-30
19282-FS-CURRENT-35.6.3.1.5.1.5.2 | Shoreside Works | 14 | 136.1d | 2026-10-22 | 2027-03-23
19282-FS-CURRENT-35.6.3.1.5.1.5.2.1.5.2.4 | Construct truss tower | 2 | 111.1d | 2026-10-27 | 2027-03-03
19282-FS-CURRENT-35.6.3.1.5.1.5.2.1.5.2.5 | Construct outfall Ch-4 to CH91 | 9 | 117.1d | 2026-11-10 | 2027-03-23
19282-FS-CURRENT-35.6.3.1.5.1 | Final | 4 | 7.0d | 2027-04-30 | 2027-05-07
19282-FS-CURRENT-35.6.3.1.4.8 | Marine Demobilisation | 6 | 153.5d | 2026-12-02 | 2027-05-20
19282-FS-CURRENT-35.6.3.4 | Final works | 3 | 61.0d | 2027-05-07 | 2027-07-07
19282-FS-CURRENT-35.6.4 | NH2 to Port - Supply | 0 | 0.0d
19282-FS-CURRENT-35.6.31 | 8.0 Project Approval Process - Final Tollgate | 1 | 0.0d | 01-Apr-25 A | 02-Jun-25 A
19282-FS-CURRENT-35.6.8 | NH2 to Port EXECUTION | 0 | 0.0d
19282-FS-CURRENT-35.6.6 | NH2 to Port | 0 | 0.0d
19282-FS-CURRENT-35.6.1 | Marine | 4 | 34.0d | 06-Jan-25 A | 2026-01-22
19282-FS-CURRENT-35.6.2 | Close Out | 8 | 62.0d | 2027-06-16 | 2027-08-17