## GEMCO Excess Water Summary Rev0
GEMCO Excess Water Disposal L1 Summary Schedule
2025 | [11 empty] | 2026 | [11 empty] | 2027
J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | TODO
Execution Duration (10 Months)
AAPA Sacred Sites Certificate
Split - Environmental Mining license
Split - Access Authority and Access Agreement
Summary/long lead, required on site date -add new tab to spreadsheet
Add Contract awrd Onshore
Contracts and procurement lead times
PC deterministic
Add NTP - SP2 - Contract Award / Offshore
Critical Path Activity in red font
* Other risks
Secondary Approval - Sacred Sites Authority Certificate process managed by GEMCO, forecast completion end of June ,delays to this process could impact Secondary Approvals Finish date
NH2,NH1 mining areas completed by GEMCO Mining ready for commissioning in May /June 2027.
Tier 2 Assessment by SER
Primary Approval (Tier 2 Environmental)
Secondary Approvals (Tier 2 Environmental)
Submit SER to NT EPA
Preparation works for Tollgating - Partial Funding
Tollgate Approval - Partial Funding
Procurement of Pumps, HDPE Piping, Fuel Storage, Structural Fab, Gensets and custom pipe fittings
FS Engineering - ES to NH2
FS Engineering - NH2 to Ocean
Tollgate Approval for ES to NH2
Tollgate Documentation, Review and Project Assurance Review
King Pile Wall, Construct Truss Tower and Piping Installation
FS to Exe Tollgate Approval (Dependent on Primary Approval)
Tollgate Approval for NH2 to Ocean
Onshore Pipeline Installation
SP2 - Onshore Pump Station Installation (SMP & E&I)
Excavation & Backfill
Project Close Out
Commissioning
Procurement of HDPE Pipe & Fittings, Concrete Collars, Temp Sheet and Tube Piling, Concrete Mattresses, Steel Pipe & Vent Steel, Switchroom, Valves, Flow meters
Mining Preparation Activities
Onshore Contractor MOB/Procurement
Offshore MOB
Required by Operations Date
Secondary Approvals (Access agreement, Sacred Sites, Environmental Mining License)
Tie in pipeline onshore to offshore
Pre-commitment Approvals - Long Lead Items
Owners team preparation and onboardoing
S19 Early Works
S19 earthworks
S19 Rehab
SP1 Onshore Early Works
Secondary Approvals (Access agreement, Sacred Sites, Environmental Mining License)

## CASS PFS EXE Summary Schedu BL (hidden)
CASS PFS High level Execution Summary Schedule
2024 | [7 empty] | 2025 | [11 empty] | 2026 | [11 empty] | 2027 | [11 empty] | 2028 | [11 empty] | 2029 | [11 empty] | 2030
M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D
PFS2 Tollgate (32 months)
Note: Font in red is critical path activity
PFS Defined (ESP)
Governance Review, COO-IC Approval including long lead funds
Works Approval Submission (Part V)
Tollgate document compilation
Revised PFS - FS Tollgate Approval Nov-25
s45c Submission (Part IV)
Preferred Alternative Selected/Completion of PFS Select Phase
Early Engineering Vendor Design (Sumitomo & Zeeco)
ERD Approval
PRS Design (ESP)
Air Emission Modelling
s45c and Works Approval Application Preparation
Independent Technical Review (ITR) Review
s45c (Part IV) Approval (TBC)
Works Approval (Part V) Approval (TBC)
PRS IFT (ESP) - Skid
PRS IFC (ESP) - Gas line and PRS
PRS Gas Train Assembly, Valving & Instrument Procurement (8 months)
PRS SIS Hardware Procurement (12 months)
PRS SMP Mobilisation/Construction Readiness/Fabrication
PRS Civil Construction (Piping & Trenching)
PRS SMP Construction
PRS Hydro Test & Chem Cleaning of Piping
PRS E&I Construction
PRS Dry Commissioning
FS Phase & Detailed Engineering (IFC) - FS Finished
Detailed Engineering Ready for Fabrication by EEV - activity duration to be determine (Activity 1)
Contractor Mobilisation/Reassignment from PRS (MFC5)
Contractor Procurement - subject to lead time on materials
GBS Fund Release Nov-25/Dec-25
PRS IFC (ESP) - Skid Design Confirmation and IFC
PRS Civil Construction (Slab)
GHD Detailed Engineering & Balance of Plant
Procurement of MFC Control Hardware & Specialist Instrumentation -52 weeks for control cabinets and associates hardware
GBS Fund Release Mar-27
MFC5 Pre-shutdown Works
MFC5 Shutdown Works (duration TBC after detailed planning)
MFC5 Commissioning Works
IFT SMPEI, Evaluation, Negotiation and Contract & PO Award
GHG & Air Emission Impact Assessment
CASS Project Execution 12 months deferral strategy decision
EEV PO Award for Detailed Design (MFCs)
MFC6 Pre-shutdown Works (duration to be reassess based on MFC5 Pre shudown works)
MFC6 Shutdown Works (duration to be reassess based on MFC5 shutdown works)
MFC6 Commissioning Works (duration to be reassess based on MFC5 shutdown works)
Fabrication and Delivery of MFCs Equipment for MFC5 & 6
Governance Review, Steerco IC, COO-IC/CIC, CEO, JV Approval
Tollgate FID document compilation
Contractor Re-Mobilisation (MFC6)
Contractor Procurement - subject to lead time on materials
Shipping of MFCs Equipment for MFCs
FAT Testing of Safety System
Installation of PRS Skids & Safety Cabinets
Long Lead Procurement Activity
Latest Activity 2 for Valve and Instrumentation Ordering Nov-26
Valve and Instrumentation Purchases; Batch 1 - Delivery Aug-27 (Nominal Duration pending discussion with Zeeco)
Valve and Instrumentation Purchases; Batch 2 - Delivery May-27 (Nominal Duration pending discussion with Zeeco)
Valve and Instrumentation Purchases; Batch 3 - Delivery Mar-27 (Nominal Duration pending discussion with Zeeco)
Latest Activity 3 for Fabrication Equipment Mar-26
Required on Site Date Apr-28
Arrival on Site Date Nov-27
Arrival on Site Date Jan-28
Equipment FAT & readiness to Ship
PO Award for Control Hardware & Specialist Instrumentation Nov-26
PO Award for PRS SIS Hardware Jan-27
Valve and Instrumentation Purchases; Batch 1 - Delivery Aug-27 (Duration nominal pending discussion with Zeeco)
Valve and Instrumentation Purchases; Batch 2 - Delivery May-27 (Duration nominal pending discussion with Zeeco)
Valve and Instrumentation Purchases; Batch 3 - Delivery Mar-27 (Duration nominal pending discussion with Zeeco)
Earliest Activity 2 for Valve and Instrumentation Ordering Feb-26 (if there is capital available)
P&ID & HAZOP Completion (Valve and instrument ready for Procurement (IFT))
Fabrication and Delivery of MFCs Equipment for MFC5 & 6
Earliest Activity 3 for Fabrication Equipment Nov-26
Received EEV Models Feb-27