## TASK
task_code | status_code | wbs_id | task_name | start_date | end_date | target_drtn_hr_cnt | delete_record_flag
A2050 | Not Started | 18030-PFS-CURRENT-1.1.4.2.4 | MCC Delivery | 2025-12-23 08:00 | 2025-12-29 16:00 | 5
A2060 | Not Started | 18030-PFS-CURRENT-1.1.4.2.1 | Tender Long Lead items | 2026-07-30 08:00 | 2026-08-26 17:00 | 20
A2070 | Not Started | 18030-PFS-CURRENT-1.1.4.2.3 | MCC PO placed | 2026-08-27 08:00 | 2026-09-25 14:12 | 21.7
A2080 | Not Started | 18030-PFS-CURRENT-1.1.4.2.4 | MCC Delivery | 2026-09-25 14:12 | 2027-07-13 13:12 | 200
A2090 | Not Started | 18030-PFS-CURRENT-1.1.4.2.5 | Develop Sourcing Strategy Draft | 2026-02-19 08:00 | 2026-03-18 17:00 | 20
A2100 | Not Started | 18030-PFS-CURRENT-1.1.4.2.5 | Present ot PCC for approval | 2026-03-19 08:00 | 2026-04-08 17:00 | 15
EXE1000 | Not Started | 18030-PFS-CURRENT-1.1.4.2.5 | Structural Steel |  |  | 45
EXE1010 | Not Started | 18030-PFS-CURRENT-1.1.4.2.5 | Pumps and Pontoons |  |  | 60
EXE1020 | Not Started | 18030-PFS-CURRENT-1.1.4.2.5 | Instrumentation & Valves |  |  | 70
EXE1030 | Not Started | 18030-PFS-CURRENT-1.1.4.2.5 | Cable and supports |  |  | 45
EXE1040 | Not Started | 18030-PFS-CURRENT-1.1.4.2.5 | HDPE Pipework and fittings |  |  | 45
EXE1050 | Not Started | 18030-PFS-CURRENT-1.1.4.2.5 | Auxillary Genset |  |  | 60
EXE1060 | Not Started | 18030-PFS-CURRENT-1.1.4.2.5 | Monitoring equipment installation (incl. new VWPs and cables; supply and install) |  |  | 90
EXE1070 | Not Started | 18030-PFS-CURRENT-1.1.4.2.5 | Traffic signs and bollards |  |  | 60
EXE1080 | Not Started | 18030-PFS-CURRENT-1.1.4.2.5 | Concrete (incl. for lifting slab at decant) |  |  | 60
EXE1090 | Not Started | 18030-PFS-CURRENT-1.1.5.1 | Owners Team Mobilisation and Site Establishment (completed first) |  |  | 0
EXE1100 | Not Started | 18030-PFS-CURRENT-1.1.5.1 | Office and car park setup |  |  | 20
EXE1110 | Not Started | 18030-PFS-CURRENT-1.1.5.1 | Personnel onsite |  |  | 5
EXE1120 | Not Started | 18030-PFS-CURRENT-1.1.5.1 | LVs (incl. barging and site pass-out) |  |  | 30
EXE1130 | Not Started | 18030-PFS-CURRENT-1.1.5.2 | Pre-mobilisation activities - documentation review, medicals and offsite training/inductions |  |  | 20
EXE1140 | Not Started | 18030-PFS-CURRENT-1.1.5.2 | Contractor pre-mobilisation inspections (incl. plant and equipment) |  |  | 30
EXE1150 | Not Started | 18030-PFS-CURRENT-1.1.5.2 | Contractor Equipment and personnel mob |  |  | 20
EXE1160 | Not Started | 18030-PFS-CURRENT-1.1.5.2 | Contractor and Company complete WRAC |  |  | 1
EXE1170 | Not Started | 18030-PFS-CURRENT-1.1.5.2 | Contractor area setup, offices, laydowns, NATA lab, and go line (incl. survey base stations) |  |  | 10
EXE1180 | Not Started | 18030-PFS-CURRENT-1.1.5.2 | Contractor plant and equipment pass-outs (incl. on-site inspections) |  |  | 30
EXE1190 | Not Started | 18030-PFS-CURRENT-1.1.5.2 | Contractor personnel pass-outs (incl. VOCs and D&Q licenses) |  |  | 15
EXE1200 | Not Started | 18030-PFS-CURRENT-1.1.5.2 | Company issue relevent area permits (incl. services wanding if required) |  |  | 10
EXE1210 | Not Started | 18030-PFS-CURRENT-1.1.5.2 | Contractor establish borrow areas (i.e., in accordance with BMP) |  |  | 10
EXE1220 | Not Started | 18030-PFS-CURRENT-1.1.5.2 | Contractor establish temporary water storages (incl. pumps and stand pipes) |  |  | 10
EXE1230 | Not Started | 18030-PFS-CURRENT-1.1.5.2 | Contractor pre-construction survey and set-out |  |  | 2
EXE1240 | Not Started | 18030-PFS-CURRENT-1.1.5.2 | Contractor establish haul routes (i.e., in accordance with TMP) |  |  | 5
EXE1250 | Not Started | 18030-PFS-CURRENT-1.1.5.2 | Contractor establish surface water controls (i.e., in accordance with EMP) |  |  | 5
EXE1260 | Not Started | 18030-PFS-CURRENT-1.1.5.2 | Company decommission existing monitring equipment (incl. VWPs and comms) |  |  | 10
EXE1270 | Not Started | 18030-PFS-CURRENT-1.1.5.2 | Pre-mobilisation activities - documentation review, medicals and offsite training/inductions |  |  | 10
EXE1280 | Not Started | 18030-PFS-CURRENT-1.1.5.3 | Contractor Equipment and personnel mob |  |  | 15
EXE1290 | Not Started | 18030-PFS-CURRENT-1.1.5.3 | Contractor area setup, offices and laydowns |  |  | 10
EXE1300 | Not Started | 18030-PFS-CURRENT-1.1.5.8 | Backfill diversion drain |  |  | 5
EXE1310 | Not Started | 18030-PFS-CURRENT-1.1.5.8 | Strip and prepare foundation |  |  | 5
EXE1320 | Not Started | 18030-PFS-CURRENT-1.1.5.8 | Place blanket drain extension (incl. win middlings from stockpile) |  |  | 10
EXE1330 | Not Started | 18030-PFS-CURRENT-1.1.5.8 | Place comapcted earthfill (incl. win earthfill from borrow area) |  |  | 30
EXE1340 | Not Started | 18030-PFS-CURRENT-1.1.5.8 | Place chimney filter (incl. win sands from TSF20) |  |  | 30
EXE1350 | Not Started | 18030-PFS-CURRENT-1.1.5.8 | Trim and finish |  |  | 10
EXE1360 | Not Started | 18030-PFS-CURRENT-1.1.5.8 | Place road capping |  |  | 5
EXE1370 | Not Started | 18030-PFS-CURRENT-1.1.5.8 | Construct permanent safety bunds |  |  | 10
EXE1380 | Not Started | 18030-PFS-CURRENT-1.1.5.8 | Install surface water drains |  |  | 10
EXE1390 | Not Started | 18030-PFS-CURRENT-1.1.5.8 | Excavate new diversion drain (incl. tie in with existing) |  |  | 20
EXE1400 | Not Started | 18030-PFS-CURRENT-1.1.5.8 | Install toe access road and ramps |  |  | 5
EXE1410 | Not Started | 18030-PFS-CURRENT-1.1.5.8 | Decant ring works (incl. white rock production if required) |  |  | 10
EXE1420 | Not Started | 18030-PFS-CURRENT-1.1.5.8 | Spillway works (incl. widening if required) |  |  | 10
EXE1430 | Not Started | 18030-PFS-CURRENT-1.1.5.7 | Removal of redundant PC02 gangway, pontoon, pump and pipework |  |  | 10
EXE1440 | Not Started | 18030-PFS-CURRENT-1.1.5.7 | Removal of redundant concentrator gangway, pontoon, pump and pipework |  |  | 12
EXE1450 | Not Started | 18030-PFS-CURRENT-1.1.5.7 | Disconnection and removal of all cable, tray and supports |  |  | 6
EXE1460 | Not Started | 18030-PFS-CURRENT-1.1.5.7 | Removal of redundant MCC's and supporting structures |  |  | 10
EXE1470 | Not Started | 18030-PFS-CURRENT-1.1.5.7 | Demolition of civils |  |  | 6
EXE1480 | Not Started | 18030-PFS-CURRENT-1.1.5.5 | Preparation and excavation |  |  | 10
EXE1490 | Not Started | 18030-PFS-CURRENT-1.1.5.5 | Civil works to support pump installation (incl. place ballast) |  |  | 2
EXE1500 | Not Started | 18030-PFS-CURRENT-1.1.5.5 | Concrete plinth and footing pours |  |  | 15
EXE1510 | Not Started | 18030-PFS-CURRENT-1.1.5.5 | MCC Structure assembly |  |  | 10
EXE1520 | Not Started | 18030-PFS-CURRENT-1.1.5.5 | Gangway and Pontoon Assembly |  |  | 10
EXE1530 | Not Started | 18030-PFS-CURRENT-1.1.5.4 | Gangway and pontoon lifts |  |  | 3
EXE1540 | Not Started | 18030-PFS-CURRENT-1.1.5.4 | Pump lifts |  |  | 3
EXE1550 | Not Started | 18030-PFS-CURRENT-1.1.5.4 | Decant pipework/valves and supports |  |  | 15
EXE1560 | Not Started | 18030-PFS-CURRENT-1.1.5.4 | Pump alignment, testing and commissiong (can only happen after energisation) |  |  | 3
EXE1570 | Not Started | 18030-PFS-CURRENT-1.1.5.6 | MCC lift, securing and sealing (lift completed after pump lifts same crane) |  |  | 3
EXE1580 | Not Started | 18030-PFS-CURRENT-1.1.5.6 | Cable supports and tray |  |  | 10
EXE1590 | Not Started | 18030-PFS-CURRENT-1.1.5.6 | Cable rough ins |  |  | 10
EXE1600 | Not Started | 18030-PFS-CURRENT-1.1.5.6 | Instrumentation mounting |  |  | 5
EXE1610 | Not Started | 18030-PFS-CURRENT-1.1.5.6 | Install lights, GPO's and cameras |  |  | 3
EXE1620 | Not Started | 18030-PFS-CURRENT-1.1.5.6 | Field control panel install |  |  | 5
EXE1630 | Not Started | 18030-PFS-CURRENT-1.1.5.6 | Power cable termination and fit off |  |  | 10
EXE1640 | Not Started | 18030-PFS-CURRENT-1.1.5.6 | Control and instrumentation cable termination and fit off |  |  | 10
EXE1650 | Not Started | 18030-PFS-CURRENT-1.1.5.6 | Generator modifications and interfacing |  |  | 5
EXE1660 | Not Started | 18030-PFS-CURRENT-1.1.5.6 | Electrical testing and Energisation |  |  | 3
EXE1670 | Not Started | 18030-PFS-CURRENT-1.1.5.6 | Control system and SCADA setup and testing |  |  | 3
EXE1680 | Not Started | 18030-PFS-CURRENT-1.1.5.6 | Commissioning (incl. ATO) |  |  | 5
EXE1690 | Not Started | 18030-PFS-CURRENT-1.1.5.6 | New monitoring equipment installation (incl. new VWPs) |  |  | 10
EXE1700 | Not Started | 18030-PFS-CURRENT-1.1.5.6 | Re-commission existing monitoring installations |  |  | 10
EXE1710 | Not Started | 18030-PFS-CURRENT-1.1.5.6 | Integrate data aquisition system into SCADA / Dams32 |  |  | 30
EXE1720 | Not Started | 18030-PFS-CURRENT-1.1.5.9 | Removal of existing PC02 delivery pipework |  |  | 20
EXE1730 | Not Started | 18030-PFS-CURRENT-1.1.5.9 | Installation of Tech Taylor valve and connections |  |  | 14
EXE1740 | Not Started | 18030-PFS-CURRENT-1.1.5.9 | Re-instatement of main deposition line, including valves |  |  | 30
EXE1750 | Not Started | 18030-PFS-CURRENT-1.1.5.9 | Installation of spigots |  |  | 10
EXE1760 | Not Started | 18030-PFS-CURRENT-1.1.5.9 | Testing (incl. ATO) |  |  | 10
EXE1770 | Not Started | 18030-PFS-CURRENT-1.1.5.10 | Civil closeout and demob |  |  | 0
EXE1780 | Not Started | 18030-PFS-CURRENT-1.1.5.10 | Submit Construction Record Report (incl. as-con survey) |  |  | 10
EXE1790 | Not Started | 18030-PFS-CURRENT-1.1.5.10 | Submit Construction Certification Report (i.e., by REE) |  |  | 20
EXE1800 | Not Started | 18030-PFS-CURRENT-1.1.5.10 | Site clean up (incl. remove temporary site sheds etc) |  |  | 10
EXE1810 | Not Started | 18030-PFS-CURRENT-1.1.5.10 | Install traffic signs |  |  | 2
EXE1820 | Not Started | 18030-PFS-CURRENT-1.1.5.10 | Remediate borow areas and haul roads |  |  | 5

## USERDATA
user_data
UserSettings Do Not Edit
DurationQtyType=QT_Day ShowAsPercentage=0 SmallScaleQtyType=QT_Day DateFormat=d/mm/yyyy CurrencyFormat=Australian Dollar