## TASK
task_code | status_code | wbs_id | task_name | start_date | end_date | target_drtn_hr_cnt | delete_record_flag
A1000 | Not Started | GEMCO-L1.1 | Submit SER to NT EPA |  |  | 30
A1010 | Not Started | GEMCO-L1.2 | Tier 2 Assessment by SER |  |  | 180
A1020 | Not Started | GEMCO-L1.3 | Primary Approval (Tier 2 Environmental) |  |  | 30
A1030 | Not Started | GEMCO-L1.4 | Secondary Approvals (Access agreement, Sacred Sites, Environmental Mining License) |  |  | 240
A1040 | Not Started | GEMCO-L1.5 | Secondary Approvals (Tier 2 Environmental) |  |  | 60
A1050 | Not Started | GEMCO-L1.6 | Secondary Approvals (Access agreement, Sacred Sites, Environmental Mining License) |  |  | 210
A1060 | Not Started | GEMCO-L1.7 | Tollgate Approval for ES to NH2 |  |  | 60
A1070 | Not Started | GEMCO-L1.8 | FS Engineering - ES to NH2 |  |  | 120
A1080 | Not Started | GEMCO-L1.9 | FS Engineering - NH2 to Ocean |  |  | 150
A1090 | Not Started | GEMCO-L1.10 | Tollgate Documentation, Review and Project Assurance |  |  | 60
A1100 | Not Started | GEMCO-L1.11 | Tollgate Approval for NH2 to Ocean |  |  | 60
A1110 | Not Started | GEMCO-L1.12 | FS to Exe Tollgate Approval (Dependent on Primary Approval) |  |  | 30
A1120 | Not Started | GEMCO-L1.13 | Preparation works for Tollgating - Partial Funding |  |  | 180
A1130 | Not Started | GEMCO-L1.14 | Tollgate Approval - Partial Funding |  |  | 60
A1140 | Not Started | GEMCO-L1.15 | Procurement of Pumps, HDPE Piping, Fuel Storage, Structural Fab, Gensets and custom pipe fittings |  |  | 90
A1150 | Not Started | GEMCO-L1.16 | Onshore Contractor MOB/Procurement |  |  | 90
A1160 | Not Started | GEMCO-L1.17 | Onshore Pipeline Installation |  |  | 180
A1170 | Not Started | GEMCO-L1.18 | Mining Preparation Activities |  |  | 120
A1180 | Not Started | GEMCO-L1.19 | SP1 Onshore Early Works |  |  | 60
A1190 | Not Started | GEMCO-L1.20 | SP2 - Onshore Pump Station Installation (SMP & E&I) |  |  | 90
A1200 | Not Started | GEMCO-L1.21 | S19 earthworks |  |  | 60
A1210 | Not Started | GEMCO-L1.22 | S19 Early Works |  |  | 60
A1220 | Not Started | GEMCO-L1.23 | Owners team preparation and onboarding |  |  | 90
A1230 | Not Started | GEMCO-L1.24 | Pre-commitment Approvals - Long Lead Items |  |  | 90
A1240 | Not Started | GEMCO-L1.25 | Procurement of HDPE Pipe & Fittings, Concrete Collars, Temp Sheet and Tube Piling, Concrete Mattresses, Steel Pipe & Vent Steel, Switchroom, Valves, Flow meters |  |  | 240
A1250 | Not Started | GEMCO-L1.26 | Offshore MOB |  |  | 60
A1260 | Not Started | GEMCO-L1.27 | King Pile Wall, Construct Truss Tower and Piping Installation |  |  | 90
A1270 | Not Started | GEMCO-L1.28 | Excavation & Backfill |  |  | 60
A1280 | Not Started | GEMCO-L1.29 | Commissioning |  |  | 60
A1290 | Not Started | GEMCO-L1.30 | Tie in pipeline onshore to offshore |  |  | 120
A1300 | Not Started | GEMCO-L1.31 | S19 Rehab |  |  | 60
A1310 | Not Started | GEMCO-L1.32 | Project Close Out |  |  | 60

## USERDATA
user_data
UserSettings Do Not Edit
DurationQtyType=QT_Day ShowAsPercentage=0 SmallScaleQtyType=QT_Day DateFormat=d/mm/yyyy CurrencyFormat=Australian Dollar