## Sheet2
WBS Code | WBS | Remaining Duration | Start | Finish
| GEMCO Water Disposal FS Master Schedule - 16-01-2026 - Jan Update | 605.9d | 20-Oct-25 A | 2027-08-17
| Environmental Approvals | 281.2d | 03-Nov-25 A | 2026-09-29
| Base Case | 605.9d | 20-Oct-25 A | 2027-08-17
| Key Milestones | 575.7d | 2026-01-19 | 2027-08-17
| Design - IFT to IFC | 238.9d | 22-Dec-25 A | 2026-08-17
| Onshore | 199.8d | 2026-01-30 | 2026-08-17
| Offshore | 30.0d | 22-Dec-25 A | 2026-01-30
| Precommitment | 279.2d | 20-Oct-25 A | 2026-09-25
| Precommitment Approvals | 41.2d | 31-Oct-25 A | 2026-01-30
| Contracts and Supply Packages - Precommitment funding | 279.2d | 20-Oct-25 A | 2026-09-25
| Owners Team activities | 122.3d | 2026-01-23 | 2026-05-25
| Early Execution Works | 158.0d | 2026-03-15 | 2026-08-19
| Tollgate Phase | 285.8d | 20-Oct-25 A | 2026-10-01
| Preparation works for Tollgating - Partial Funding | 91.0d | 31-Oct-25 A | 2026-03-20
| Tollgate Partial Funding - Conditional Approval pending Regulatory Approvals | 24.9d | 2026-03-21 | 2026-04-14
| Contracts and Procurement - Tollgate March Partial funding | 267.9d | 20-Oct-25 A | 2026-09-29
| Regulatory Approvals (Primary & Secondary) | 14.0d | 2026-08-06 | 2026-08-20
| Full Funding Confirmation of Primary Approval | 90.9d | 2026-04-09 | 2026-08-17
| Contracts and Procurement - August Full Funding (upon regulatory approvals receipt) | 48.9d | 2026-08-13 | 2026-10-01
| Execution Works | 548.9d | 2026-01-05 | 2027-07-07
| Approvals & Permits | 177.0d | 2026-01-05 | 2026-06-30
| Design Confirmation Site Assesments | 14.0d | 2026-06-22 | 2026-07-06
| Onshore | 386.0d | 2026-04-06 | 2027-04-27
| S19 | 60.0d | 2026-08-20 | 2026-10-19
| WASCO | 313.0d | 2026-04-06 | 2027-02-13
| KEY DATES (MILESTONES) | 296.9d | 2026-04-06 | 2027-02-13
| PREPARATION & PRELIMINARY WORK | 164.0d | 2026-04-06 | 2026-09-17
| MOBILISE & CONSTRUCT | 253.0d | 2026-05-20 | 2027-02-12
| SP1 - EARLY WORKS | 116.6d | 2026-05-20 | 2026-09-21
| SP2 - MAIN WORKS | 237.9d | 2026-06-04 | 2027-02-12
| SP3 - OCEAN OUTFALL AREA | 78.0d | 2026-07-01 | 2026-09-24
| Summary (superseded) | 228.0d | 2026-06-05 | 2027-04-27
| Marine Site works | 263.1d | 2026-08-17 | 2027-05-07
| Marine Mobilisation | 143.6d | 2026-08-17 | 2027-01-08
| Offshore works | 208.1d | 2026-09-18 | 2027-04-30
| Kingpile wall (135m) | 135.1d | 2026-09-18 | 2027-02-16
| Excavation & Backfill | 84.0d | 2027-02-05 | 2027-04-30
| Shoreside Works | 136.1d | 2026-10-22 | 2027-03-23
| Construct truss tower | 116.1d | 2026-10-22 | 2027-03-03
| Construct outfall Ch-4 to CH91 | 117.1d | 2026-11-10 | 2027-03-23
| Final | 7.0d | 2027-04-30 | 2027-05-07
| Marine Demobilisation | 153.5d | 2026-12-02 | 2027-05-20
| Final works | 61.0d | 2027-05-07 | 2027-07-07
| Close Out | 62.0d | 2027-06-16 | 2027-08-17