## TASK
task_code | status_code | wbs_id | task_name | remain_drtn_hr_cnt | complete_pct | start_date | end_date | delete_record_flag
Activity ID | Activity Status | WBS Code | Activity Name | Remaining Duration(d) | Activity % Complete(%) | (*)Start | (*)Finish | Delete This Row
A1000 | Not Started | 19282-FS-Summary-FS-EXE-2 | GEMCO Water Disposal FS Master Schedule - 16-01-2026 - Jan Update | 0 | 0 | 2027-08-17 06:00 | 2027-08-17 06:00
A1010 | Not Started | 19282-FS-Summary-FS-EXE-2 | Environmental Approvals | 0 | 0 | 2026-09-29 06:00 | 2026-09-29 06:00
A1020 | Not Started | 19282-FS-Summary-FS-EXE-2 | Base Case | 0 | 0 | 2027-08-17 06:00 | 2027-08-17 06:00
A1030 | In Progress | 19282-FS-Summary-FS-EXE-2 | Key Milestones | 0 | 0 | 2026-01-19 | 2026-01-19 06:00
A1040 | Not Started | 19282-FS-Summary-FS-EXE-2 | Design - IFT to IFC | 0 | 0 | 2026-08-17 06:00 | 2026-08-17 06:00
A1050 | Not Started | 19282-FS-Summary-FS-EXE-2 | Onshore | 66.3 | 0 | 2026-01-30 06:00 | 2026-06-19 14:00
A1060 | Not Started | 19282-FS-Summary-FS-EXE-2 | Offshore | 0 | 0 | 2026-01-30 06:00 | 2026-01-30 06:00
A1070 | Not Started | 19282-FS-Summary-FS-EXE-2 | Precommitment | 0 | 0 | 2026-09-25 06:00 | 2026-09-25 06:00
A1080 | Not Started | 19282-FS-Summary-FS-EXE-2 | Precommitment Approvals | 0 | 0 | 2026-01-30 06:00 | 2026-01-30 06:00
A1090 | Not Started | 19282-FS-Summary-FS-EXE-2 | Contracts and Supply Packages - Precommitment funding | 0 | 0 | 2026-09-25 06:00 | 2026-09-25 06:00
A1100 | Not Started | 19282-FS-Summary-FS-EXE-2 | Owners Team activities | 40.7 | 0 | 2026-01-23 06:00 | 2026-04-22 10:00
A1110 | Not Started | 19282-FS-Summary-FS-EXE-2 | Early Execution Works | 52.3 | 0 | 2026-03-15 06:00 | 2026-06-27 14:00
A1120 | Not Started | 19282-FS-Summary-FS-EXE-2 | Tollgate Phase | 0 | 0 | 2026-10-01 06:00 | 2026-10-01 06:00
A1130 | Not Started | 19282-FS-Summary-FS-EXE-2 | Preparation works for Tollgating - Partial Funding | 0 | 0 | 2026-03-20 06:00 | 2026-03-20 06:00
A1140 | Not Started | 19282-FS-Summary-FS-EXE-2 | Tollgate Partial Funding - Conditional Approval pending Regulatory Approvals | 8 | 0 | 2026-03-21 06:00 | 2026-04-05 18:00
A1150 | Not Started | 19282-FS-Summary-FS-EXE-2 | Contracts and Procurement - Tollgate March Partial funding | 0 | 0 | 2026-09-29 06:00 | 2026-09-29 06:00
A1160 | Not Started | 19282-FS-Summary-FS-EXE-2 | Regulatory Approvals (Primary & Secondary) | 4.7 | 0 | 2026-08-06 06:00 | 2026-08-15 10:00
A1170 | Not Started | 19282-FS-Summary-FS-EXE-2 | Full Funding Confirmation of Primary Approval | 43.3 | 0 | 2026-04-09 06:00 | 2026-07-04 14:00
A1180 | Not Started | 19282-FS-Summary-FS-EXE-2 | Contracts and Procurement - August Full Funding (upon regulatory approvals receipt) | 16.3 | 0 | 2026-08-13 06:00 | 2026-09-14 14:00
A1190 | In Progress | 19282-FS-Summary-FS-EXE-2 | Execution Works | 0 | 0 | 2026-01-05 | 2026-01-05 06:00
A1200 | In Progress | 19282-FS-Summary-FS-EXE-2 | Approvals & Permits | 0 | 0 | 2026-01-05 | 2026-01-05 06:00
A1210 | Not Started | 19282-FS-Summary-FS-EXE-2 | Design Confirmation Site Assesments | 4.7 | 0 | 2026-06-22 06:00 | 2026-07-01 10:00
A1220 | Not Started | 19282-FS-Summary-FS-EXE-2 | Onshore | 128.7 | 0 | 2026-04-06 06:00 | 2027-01-17 10:00
A1230 | Not Started | 19282-FS-Summary-FS-EXE-2 | S19 | 20 | 0 | 2026-08-20 06:00 | 2026-09-28 18:00
A1240 | Not Started | 19282-FS-Summary-FS-EXE-2 | WASCO | 104.3 | 0 | 2026-04-06 06:00 | 2026-11-15 14:00
A1250 | Not Started | 19282-FS-Summary-FS-EXE-2 | KEY DATES (MILESTONES) | 104.3 | 0 | 2026-04-06 06:00 | 2026-11-15 14:00
A1260 | Not Started | 19282-FS-Summary-FS-EXE-2 | PREPARATION & PRELIMINARY WORK | 54.7 | 0 | 2026-04-06 06:00 | 2026-07-30 10:00
A1270 | Not Started | 19282-FS-Summary-FS-EXE-2 | MOBILISE & CONSTRUCT | 89.3 | 0 | 2026-05-20 06:00 | 2026-11-29 14:00
A1280 | Not Started | 19282-FS-Summary-FS-EXE-2 | SP1 - EARLY WORKS | 41.3 | 0 | 2026-05-20 06:00 | 2026-08-16 14:00
A1290 | Not Started | 19282-FS-Summary-FS-EXE-2 | SP2 - MAIN WORKS | 84.3 | 0 | 2026-06-04 06:00 | 2026-12-04 14:00
A1300 | Not Started | 19282-FS-Summary-FS-EXE-2 | SP3 - OCEAN OUTFALL AREA | 28.3 | 0 | 2026-07-01 06:00 | 2026-09-01 14:00
A1310 | Not Started | 19282-FS-Summary-FS-EXE-2 | Summary (superseded) | 108.7 | 0 | 2026-06-05 06:00 | 2027-02-06 10:00
A1320 | Not Started | 19282-FS-Summary-FS-EXE-2 | Marine Site works | 87.7 | 0 | 2026-08-17 06:00 | 2027-03-03 10:00
A1330 | Not Started | 19282-FS-Summary-FS-EXE-2 | Marine Mobilisation | 48 | 0 | 2026-08-17 06:00 | 2026-11-29 18:00
A1340 | Not Started | 19282-FS-Summary-FS-EXE-2 | Offshore works | 74.7 | 0 | 2026-09-18 06:00 | 2027-03-17 10:00
A1350 | Not Started | 19282-FS-Summary-FS-EXE-2 | Kingpile wall (135m) | 50.3 | 0 | 2026-09-18 06:00 | 2027-01-19 14:00
A1360 | Not Started | 19282-FS-Summary-FS-EXE-2 | Excavation & Backfill | 28 | 0 | 2027-02-05 06:00 | 2027-04-09 18:00
A1370 | Not Started | 19282-FS-Summary-FS-EXE-2 | Shoreside Works | 50.7 | 0 | 2026-10-22 06:00 | 2027-02-23 10:00
A1380 | Not Started | 19282-FS-Summary-FS-EXE-2 | Construct truss tower | 44 | 0 | 2026-10-22 06:00 | 2027-02-09 18:00
A1390 | Not Started | 19282-FS-Summary-FS-EXE-2 | Construct outfall Ch-4 to CH91 | 44.3 | 0 | 2026-11-13 06:00 | 2027-02-23 14:00
A1400 | Not Started | 19282-FS-Summary-FS-EXE-2 | Final | 2.3 | 0 | 2027-04-30 06:00 | 2027-05-04 14:00
A1410 | Not Started | 19282-FS-Summary-FS-EXE-2 | Marine Demobilisation | 56.3 | 0 | 2026-12-02 06:00 | 2027-04-15 14:00
A1420 | Not Started | 19282-FS-Summary-FS-EXE-2 | Final works | 20.3 | 0 | 2027-05-07 06:00 | 2027-06-16 14:00
A1430 | Not Started | 19282-FS-Summary-FS-EXE-2 | Close Out | 20.7 | 0 | 2027-06-16 06:00 | 2027-08-02 10:00

## RSRC
rsrc_short_name | rsrc_name | rsrc_type | unit_id | role_id | def_qty_per_hr
Resource ID | Resource Name | (*)Resource Type | Unit of Measure | (*)Role ID | Default Units / Time(d/d)
RH | Rowell Highway Resources | Nonlabor |  |  | 1
RH-1 | Rowell Highway Grouping Summary | Nonlabor |  |  | 1
RH-CP | Rowell Highway Commodity Profile | Nonlabor |  |  | 1
RH-AFO | Accommodation Forecast - Owners Team | Labor |  |  | 1
RH-AFS | Accommodation Forecast - Support Contractor | Labor |  |  | 1
RH-PPH | Rowell Highway Power Pole Direct Hours | Labor |  |  | 1
JQ | J Quarry Resources | Labor |  |  | 1
JQ-AFO | Accommodation Forecast - Owners Team | Labor |  |  | 1
JQ-AFS | Accommodation Forecast - Support Contractor | Labor |  |  | 1
JQ-AFM | Accommodation Forecast - Main Contractor | Labor |  |  | 1
JQ-PFS | J Quarry PFS Budget | Nonlabor |  |  | 1
JQCP-1 | Deliverable Profile | Labor |  |  | 1
TSF15 | TSF15 Resources | Labor |  |  | 1
TSF15-AFM | Accommodation Forecast - Main Contractor | Labor |  |  | 1
TSF15-AFS | Accommodation Forecast - Support Contractor | Labor |  |  | 1
TSF15-AFO | Accommodation Forecast - Owners Team | Labor |  |  | 1
TSF15-D-1 | Deliverable Hours | Labor |  |  | 1
TSF15CP | Commodity Profile | Nonlabor |  |  | 1
TSF20-2 | TSF 20 - Budget | Nonlabor |  |  | 1
TSF20-AFO | Accommodation Forecast - Owners Team | Labor |  |  | 1
TSF20-AFS | Accommodation Forecast - Support Contractor | Labor |  |  | 1
TSF20-AFM | Accommodation Forecast - Main Contractor | Labor |  |  | 1
TSF20CP | TSF20 Commodity Profile | Nonlabor |  |  | 1
TSF20PP | TSF20 Package Profile | Nonlabor |  |  | 1
TSF20 | TSF20 Resources | Labor |  |  | 1
HR | Historical Resources | Labor |  |  | 1
EASTL | Eastern Leases | Labor |  |  | 1
EASTL-02 | Support Function | Labor |  |  | 1
EASTL-02a | 01 Project Management | Labor |  |  | 1
EASTL-02f | 08 Consultants & 3rd Parties | Labor |  |  | 1
TSF15PP | TSF15 Package Profile | Nonlabor |  |  | 2
79000 | Owners Team - Proposed | Labor |  |  | 1
72000 | Consultants - Proposed | Labor |  |  | 1
71100 | Contractor Management Team - Proposed | Labor |  |  | 2
79120 | Engineering Management | Labor |  |  | 1
79110 | Project Management | Labor |  |  | 1
79140 | Construction | Labor |  |  | 1
79150 | Project Administration | Labor |  |  | 1
79170 | Project Services | Labor |  |  | 1
79190 | Operations Support | Labor |  |  | 2
72150 | Commissioning | Labor |  |  | 1
79130 | Engineering and Design | Labor |  |  | 1
79110-1 | Project Management | Labor |  |  | 1
72120 | Engineering Management | Labor |  |  | 1
72130 | Engineering and Design | Labor |  |  | 1
72140 | Construction | Labor |  |  | 1
72160 | Project Administration | Labor |  |  | 1
72170 | Project Services | Labor |  |  | 1
71110 | Project Management | Labor |  |  | 2
71120 | Engineering Management | Labor |  |  | 1
71130 | Engineering and Design | Labor |  |  | 1
71140 | Construction | Labor |  |  | 1
71150 | Commissioning | Labor |  |  | 1
71160 | Project Administration | Labor |  |  | 1
71170 | Project Services | Labor |  |  | 1
Y1140 | Risk | Labor |  |  | 1
Y1130 | Quality | Labor |  |  | 1
Y1120 | HSEC | Labor |  |  | 1
Y1110 | Project Management | Labor |  |  | 1
Y1370 | Marine | Labor |  |  | 1
Y1360 | Instrumentation | Labor |  |  | 1
Y1350 | Electrical | Labor |  |  | 1
Y1340 | Piping | Labor |  |  | 1
Y1330 | Mechanical | Labor |  |  | 1
Y1320 | Civiil | Labor |  |  | 1
Y1310 | Process | Labor |  |  | 1
Y1380 | Other | Labor |  |  | 1
Y1400 | Construction | Labor |  |  | 1
Y1640 | Finance | Labor |  |  | 1
Y1630 | IT and Comms | Labor |  |  | 1
Y1620 | HR and IR | Labor |  |  | 1
Y1610 | Clerical | Labor |  |  | 1
Y1760 | Document Control | Labor |  |  | 1
Y1750 | Purchasing | Labor |  |  | 1
Y1740 | Contracts | Labor |  |  | 1
Y1730 | Estimating | Labor |  |  | 1
Y1720 | Planning | Labor |  |  | 1
Y1710 | Project Controls | Labor |  |  | 1
Y1900 | Operations Support | Labor |  |  | 2
JQ-Y2110 | Project Management | Labor |  |  | 1
Y2120 | HSEC | Labor |  |  | 1
Y2130 | Quality | Labor |  |  | 1
Y2140 | Risk | Labor |  |  | 1
Y2200 | Engineering Management | Labor |  |  | 1
Y2310 | Process | Labor |  |  | 1
Y2320 | Civiil | Labor |  |  | 1
Y2330 | Mechanical | Labor |  |  | 1
Y2340 | Piping | Labor |  |  | 1
Y2350 | Electrical | Labor |  |  | 1
Y1360-1 | Instrumentation | Labor |  |  | 1
Y2370 | Marine | Labor |  |  | 1
Y2380 | Other | Labor |  |  | 1
JQU-Y2440 | Construction | Labor |  |  | 1
Y2810 | Commissioning | Labor |  |  | 1
Y2610 | Clerical | Labor |  |  | 1
Y2620 | HR and IR | Labor |  |  | 1
Y2630 | IT and Comms | Labor |  |  | 1
Y2640 | Finance | Labor |  |  | 1
Y2710 | Project Controls | Labor |  |  | 1
Y2720 | Planning | Labor |  |  | 1
Y2730 | Estimating | Labor |  |  | 1
Y2740 | Contracts | Labor |  |  | 1
Y2750 | Purchasing | Labor |  |  | 1
Y2760 | Document Control | Labor |  |  | 1
PL | Plant - Proposed | Nonlabor |  |  | 1
PL-777 | 777 Truck | Nonlabor |  |  | 1
PL-EX | Excavator GPS 20T | Nonlabor |  |  | 1
PL-SC | Scraper 657 | Nonlabor |  |  | 1
PL-AT | Agi Truck | Nonlabor |  |  | 1
PL-MX | Moxy | Nonlabor |  |  | 1
PL-DZ | D6, D10 Dozers | Nonlabor |  |  | 1
PL-LD | Loader | Nonlabor |  |  | 1
PL-WC | Water Cart | Nonlabor |  |  | 1
PL-ST | Spray Truck | Nonlabor |  |  | 1
PL-HB | Hydraulic Breaker | Nonlabor |  |  | 1
PL-RL | Roller | Nonlabor |  |  | 1
PL-GD | Grader | Nonlabor |  |  | 1
PL-CP | Compactor | Nonlabor |  |  | 1
PL-LVT | Ancillary LV and Trailer | Nonlabor |  |  | 1
PL-SB | Skull Bucker | Nonlabor |  |  | 1
PL-PT | Posi-Track | Nonlabor |  |  | 1
PL-CS | Crusher and Screen | Nonlabor |  |  | 1
TSFE5 | TSFE5 Resources | Labor |  |  | 1
TSFE5-C | TSFE5 Commoidty Profile | Nonlabor |  |  | 1
TSFE5-Progress | Progress | Labor |  |  | 1
ELS Labour | ELS Execution | Labor |  |  | 1
EASTL-03-01 | Labor | Labor |  |  | 1
EASTL-03-03 | Materials | Labor |  |  | 1
M-01 | Clear & Grub (m2) | Material | Square Metres |  | 1
M-02 | Topsoil Strip (m3) | Material | Cubic Metres |  | 1
M-03 | General Earthworks (m3) | Material | Cubic Metres |  | 1
M-04 | Base Course (m3) | Material |  |  | 1
M-05 | Wearing Course (m3) | Material | Cubic Metres |  | 1
PL-VOL | Earthworks Quantity | Material | Cubic Metres |  | 6
EASTL-CONS | Eastern Leases Construction | Labor |  |  | 1
L1 | Plant/ Equipment Operators | Labor |  |  | 1
L2 | Support Crew (on the field) | Labor |  |  | 1
L3 | Indirect Labor (Other) | Labor |  |  | 1
PL-TX | Tilt Excavator GPS 20T w/Roll wheel | Nonlabor |  |  | 1
PL-CR80 | 80T Mobile Crane | Nonlabor |  |  | 1
M-06 | Dams ?? | Material | Cubic Metres |  | 1
M-07 | HV Berms and GO Line | Material | Cubic Metres |  | 1
M-08 | Rock Production | Material | Cubic Metres |  | 1
EASTL-03-04 | Cost | Labor |  |  | 1
C-01 | Cost | Nonlabor |  |  | 1
JQU | J Quarry | Nonlabor |  |  | 1
AR | Airport Runway | Nonlabor |  |  | 1
Y2110 | Project Management | Labor |  |  | 1
Y2440 | Construction | Labor |  |  | 1
JQ-OT | Owners Team | Labor |  |  | 1
JQU-CN | Contractors Team | Labor |  |  | 1
AR-OT | Owners Team | Labor |  |  | 1
AR-Y2110 | Project Management | Labor |  |  | 1
AR-CN | Contractors Team | Labor |  |  | 1
AR-Y2440 | Construction | Labor |  |  | 1
NC | Ndunga Creek | Labor |  |  | 1
NC-OT | Owners Team | Labor |  |  | 1
NC-Y2110 | Project Management | Labor |  |  | 1
NC-CN | Contractors Team | Labor |  |  | 1
NC-Y2440 | Construction | Labor |  |  | 1
Proposed | Proposed Resources | Nonlabor |  |  | 1
TSF17 | TSF17 | Labor |  |  | 1
TSF17-OT | Owners Team | Labor |  |  | 1
TSF17-Y2110 | Project Management | Labor |  |  | 1
TSF17-CN | Contractors Team | Labor |  |  | 1
TSF17-Y2440 | Construction | Labor |  |  | 1
AP | Accommodation | Labor |  |  | 1
SL | Southern Leases | Labor |  |  | 1
SL-OT | Owners Team | Labor |  |  | 1
SL-Y2110 | Project Management | Labor |  |  | 1
SL-CN | Contractors Team | Labor |  |  | 1
SL-Y2440 | Construction | Labor |  |  | 1
AR-L | Labor | Labor |  |  | 1
AR-BP | Budget Profile | Nonlabor |  |  | 1
NC-L | Labour | Labor |  |  | 1
NC-BP | Budget Profile | Nonlabor |  |  | 1
JQ-L | Labor | Labor |  |  | 1
JQ-BP | Budget Profile | Nonlabor |  |  | 1
TSF17-L | Labor | Labor |  |  | 1
TSF17-BP | Budget Profile | Nonlabor |  |  | 1
SL-L | Labor | Labor |  |  | 1
SL-BP | Budget Profile | Nonlabor |  |  | 1
TSF20L | Labor | Labor |  |  | 1
RHL | Labor | Nonlabor |  |  | 1
RH-AFS-1 | Accommodation Forecast - Main Contractor | Labor |  |  | 1
EL-PA | Sub Contractors - Piping | Labor |  |  | 1
GEN-OW | General - Owners Team | Labor |  |  | 1
WSP | Water Storage Project | Nonlabor |  |  | 1
WSP-DP | Deliverable Profile | Labor |  |  | 1
_J | Base | Material |  |  | 0
_K | Wearing | Material |  |  | 0
_Q | Scraper fleet 1 | Labor |  |  | 1
_S | Truck fleet 1 | Labor |  |  | 1
_U | Clearing Fleet 1 | Labor |  |  | 1
C_V | Clearing Fleet 2 | Labor |  |  | 1
C_W | Culvert 1 | Labor |  |  | 1
S_X | Subgrade Prep | Labor |  |  | 1
M_Y | Moxy Fleet 1 | Labor |  |  | 1
C_\ | Culvert 2 | Labor |  |  | 1
T_AA | Trim Crew | Labor |  |  | 1
R_BA | Road Furniture | Labor |  |  | 1
E_CA | Ex and Truck | Labor |  |  | 1
R_DA | Rip Rap | Labor |  |  | 1
S_EA | Subcontractor | Labor |  |  | 1
B_FA | Backfill | Labor |  |  | 1
AMRUN | Amrun Dam C and Infrastructure Corridor | Material |  |  | 8
EASTERN LEASES - LABOUR | Fleet Resources | Labor |  |  | 1
ELL-1 | Clearing Fleet | Labor |  |  | 1
ELL-2 | Haul Truck Fleet - LH | Labor |  |  | 1
ELL-3 | Scraper Fleet - SH | Labor |  |  | 1
ELL-4 | Culvert Crew | Labor |  |  | 1
ELL-5 | Detail Works Crew (Sed, Batter Chutes, Detailed Exc) | Labor |  |  | 1
ELL-6 | Trim Fleet | Labor |  |  | 1
ELL-7 | Ground Crew | Labor |  |  | 1
ELL-8 | Subcontractor - Piling | Labor |  |  | 1
ELL-9 | Subcontractor - Arch | Labor |  |  | 1
ELL-10 | Subcontractor - Concrete/Culverts | Labor |  |  | 1
ELL-11 | Subgrade Prep Fleet | Labor |  |  | 1
ELL-12 | Moxy Fleet | Labor |  |  | 1
GEN-MHRS | Man Hours | Material |  |  | 1
FH GEMCO | GEMCO Site | Labor |  |  | 1
R-196 | Logistics Team | Labor |  |  | 1
Friction | Friiction Team | Labor |  |  | 1
R-198 | Project Management | Labor |  |  | 1
Mob team | Mobilisation Team | Labor |  |  | 1
R-200 | Laboratory Team | Labor |  |  | 1
Prod team | Production Team | Labor |  |  | 1
R-201 | Profiling Team | Labor |  |  | 1
R-202 | Placement Team | Labor |  |  | 1
line-1 | Line Marking Team | Labor |  |  | 1
R-206 | Grooving Team | Labor |  |  | 1
Asp Crew | Asphalt Crew | Labor |  |  | 1
PD-1 | Project Director | Labor |  |  | 1
Mechanic-1 | Mechanic | Labor |  |  | 1
CompSupervisor | CompactionSupervisor | Labor |  |  | 1
PM-2 | Project Manager | Labor |  |  | 1
Lab Sp | Laboratory Supervisor | Labor |  |  | 1
Saftey Mgr | Safety/Envionmental Manager | Labor |  |  | 1
Bitumen Heating | Bitumen Heating | Labor |  |  | 1
Surveyor-3 | Surveyor | Labor |  |  | 1
AGL | AGL Supervisor | Labor |  |  | 1
Asph Sup | Asphlat Supervisor | Labor |  |  | 1
Profil Crew | Profiing Operator | Labor |  |  | 1
Plant Op | Plant Operator 1/2 | Labor |  |  | 1
Sweper | Sweeper | Labor |  |  | 1
Quality | Quality Engineer | Labor |  |  | 1
Constr Mgr | Construction Manager | Labor |  |  | 1
Bit Lab Tech | Bitumen Lab. Technician | Labor |  |  | 1
Asp Lab-Tech | Asphlat Lab. Technician | Labor |  |  | 1
Field Lab-Tech | Field Lab. Technician | Labor |  |  | 1
Logistics Mager | Logistics Manager | Labor |  |  | 1
Logistic/safty | Logistics/Safety Manager | Labor |  |  | 1
Day Manger | Day Works Manager | Labor |  |  | 1
prog Eng | Project Engineer | Labor |  |  | 1
Loader Op | Loader Operator | Labor |  |  | 1
Truck Drv | Truck Driver | Labor |  |  | 1
Groove Sup | Grooving Supervisor | Labor |  |  | 1
Groover | Groover | Labor |  |  | 1
EXdriv | Excavator Driver | Labor |  |  | 1
Electricaian | Electricain | Labor |  |  | 1
Mob Mnager | Mobilsation Manager | Labor |  |  | 1
Sprayer | Sprayer Operator (Transfer) | Labor |  |  | 1
R-199 | Design Manager | Labor |  |  | 1
Skid-1 | Skid Steer | Labor |  |  | 1
Mechanic-3 | Mechanic | Labor |  |  | 1
Sprayer-1 | Sprayer Operator | Labor |  |  | 1
R-203 | Auto Sprayer | Labor |  |  | 1
R-204 | Asphalt Foremen | Labor |  |  | 1
Truck Drv-1 | Truck Driver | Labor |  |  | 1
R-205 | Paveset Operator | Labor |  |  | 1
LinMk | Line Marker | Labor |  |  | 1
FT' | Friction Tester | Labor |  |  | 1
TTT | Transition to Trucking | Labor |  |  | 12
TTT-CONS | Construction | Labor |  |  | 12
TTT-CIV | CIVIL | Labor |  |  | 1
TTT-SMP | SMP | Labor |  |  | 1
TTT-E&I | E&I | Labor |  |  | 1
TTT-COMM | COMMISSIONING | Labor |  |  | 1
TTT-Direct | Direct | Labor |  |  | 12
TTT-Surv | Surveyor | Labor |  |  | 1
TTT-LAB | Labourer | Labor |  |  | 1
TTT-CONC | Concreter | Labor |  |  | 1
TTT-STF | Carpenter | Labor |  |  | 1
TTT-RIG | Rigger | Labor |  |  | 1
TTT-MECH | Mechanical Fitter | Labor |  |  | 1
TTT-TAMECH | TA - SMP | Labor |  |  | 1
TTT-ENG | OEM Engineer | Labor |  |  | 1
TTT-CROP | Crane Operator | Labor |  |  | 1
TTT-FRAOP | Franna Operator | Labor |  |  | 1
TTT-FD | Fernner Dunlop | Labor |  |  | 1
TTT-ELEC | Electrician | Labor |  |  | 1
TTT-OPR | OPERATOR | Labor |  |  | 1
TTT-OPER | Operator | Labor |  |  | 1
TTT-BOG | Bogger Operator | Labor |  |  | 1
TTT-OPRR | Operational Readiness | Labor |  |  | 1
TTT-TACIV | TA - Civil | Labor |  |  | 1
TTT-TAELEC | TA - E&I | Labor |  |  | 1
TTT-PIPE | Pipe Fitter | Labor |  |  | 1
TTT-BM | Boiler Maker | Labor |  |  | 1
TTT-NDT | NDT Tech | Labor |  |  | 1
TTT-EXCAVOP | Excavator Operator | Labor |  |  | 1
TTT-MECHSP | Mech Fitter - Specialist | Labor |  |  | 1
TTT-SCAFF | Scaffolder | Labor |  |  | 1
GEMCO | GEMCO - J QUARRY | Nonlabor |  |  | 0
GMC_OFFS | Offsite Staff | Labor |  |  | 1
GMC_ONSS | Onsite Staff | Labor |  |  | 1
GMC_OFSC | Offsite Crew | Labor |  |  | 1
GMC_OSDC | Onsite Direct Crew | Labor |  |  | 1
GMC_OSID | Onsite Indirect Crew | Labor |  |  | 1
TTT-COMMS | Comms Tech | Labor |  |  | 1
TTT-A/C | A/C Tech | Labor |  |  | 1
TTT-E&I TECH | E&I Tech | Labor |  |  | 1
TTT-CSYS | Control System Tech | Labor |  |  | 1
TTT-SMP-UG | SMP-UG | Labor |  |  | 1
TTT-SCAFF-UG | Scaffolder-UG | Labor |  |  | 1
TTT-RIG-UG | Rigger-UG | Labor |  |  | 1
TTT-MECH-UG | Mechanical Fitter-UG | Labor |  |  | 1
TTT-MECHSP-UG | Mech Fitter - Specialist-UG | Labor |  |  | 1
TTT-TAMECH-UG | TA - SMP-UG | Labor |  |  | 1
TTT-PIPE-UG | Pipe Fitter-UG | Labor |  |  | 1
TTT-BM-UG | Boiler Maker-UG | Labor |  |  | 1
TTT-NDT-UG | NDT Tech-UG | Labor |  |  | 1
TTT-ENG-UG | OEM Engineer-UG | Labor |  |  | 1
TTT_CR-UGOP | Crane-UG Operator | Labor |  |  | 1
TTT_FRA-UGOP | Franna-UG Operator | Labor |  |  | 1
TTT-SPE-FD-UG | Specialist Technician - Fernner Dunlop-UG | Labor |  |  | 1
TTT-E&I-UG | E&I-UG | Labor |  |  | 1
TTT-E&I TECH-1 | E&I Tech-UG | Labor |  |  | 1
TTT-A/C-1 | A/C Tech-UG | Labor |  |  | 1
TTT_TAELEC-1 | TA - E&I-UG | Labor |  |  | 1
TTT-ELEC-UG | Electrician-UG | Labor |  |  | 1
TTT-COMMS-1 | Comms Tech-UG | Labor |  |  | 1
TTT-CSYS-1 | Control System Tech-UG | Labor |  |  | 1
PM | Project Manager | Labor |  |  | 1
HSA | Health & Safety Advisor | Labor |  |  | 1
T1 | Heavy crane and rigging crew | Labor |  |  | 1
T2 | Transport and finishing crew | Labor |  |  | 1
STE | Extendable Semi Truck | Labor |  |  | 1
PE | Project Engineer | Labor |  |  | 1
SUP | Superintendant | Labor |  |  | 1
SSU | Site Supervisor | Labor |  |  | 1
SAD | Site Admin | Labor |  |  | 1
EMV | EMV Hammer | Labor |  |  | 1
GEM | GEMCO | Labor |  |  | 1
Log | Logistics Team | Labor |  |  | 1
Pm-t | Project Management | Labor |  |  | 1
Labt | Laboratory Team | Labor |  |  | 1
Profile | Profiling Team | Labor |  |  | 1
Place | Placement Team | Labor |  |  | 1
TSF15-PZ4 | Produce Zone 4 Rock | Material | Cubic Metres |  | 10
TSF15-Z4 | Place Zone 4 Rock | Material | Cubic Metres |  | 10
TSF15-Z1 | Zone 1 Embankment | Material | Cubic Metres |  | 10
TSF15-Z2 | Zone 2 Embankment | Material | Cubic Metres |  | 10
TSF15-MH | Manhour | Labor |  |  | 1
TSF15-FP | Foundation Preparation | Material | Square Metres |  | 10
TSF15-D10 | D10 Dozer | Nonlabor |  |  | 1
TSF15-Z5 | Place Zone 5 Rock | Material | Cubic Metres |  | 10
TSF15-D6 | D6 Dozer | Nonlabor |  |  | 1
TSF15-14M | 14M Grader | Nonlabor |  |  | 1
TSF15-16M | 16M Grader | Nonlabor |  |  | 1
TSF15-825 | 825 Compactor | Nonlabor |  |  | 1
TSF15-657 | 657 Scraper | Nonlabor |  |  | 1
TSF15-740WT | Moxy Watercart | Nonlabor |  |  | 1
TSF15-740 | Moxy Dump Truck | Nonlabor |  |  | 1
TSF15-30T | 30T Excavator | Nonlabor |  |  | 1
TSF15-50T | 50T Excavator | Nonlabor |  |  | 1
TSF15-SD | Smooth Drum Roller | Nonlabor |  |  | 1
TSF15-773 | 773 Dump Truck | Nonlabor |  |  | 1
TSF15-BC | Bobcat | Nonlabor |  |  | 1
TSF15-Z3 | Zone 3 Embankment | Material | Cubic Metres |  | 10
TTT- VEO | Contractor - Veolia | Labor |  |  | 1
Civil-1 | Civil | Labor |  |  | 1
Elect-1 | Elect | Labor |  |  | 1
Redpath Backhoe-1 | Redpath Backhoe | Labor |  |  | 1
TTT-Redpath | Redpath | Labor |  |  | 1
TTT-Mining | Mining | Labor |  |  | 1
TTT-DRC Drilling | DRC Drilling | Labor |  |  | 1
Eng-1 | Eng | Labor |  |  | 1
TTT-Wormald | Wormald | Labor |  |  | 1
TTT-CONTR | Contractor Works | Labor |  |  | 1
Elect | Elect | Labor |  |  | 1
Crane Op | Crane Op | Labor |  |  | 1
Backhoe | Backhoe | Labor |  |  | 1
Backhoe Op | Backhoe Op | Labor |  |  | 1
Clean It | Clean It | Labor |  |  | 1
Structural Eng | Structural Eng | Labor |  |  | 1
Crane | Crane | Labor |  |  | 1
Protech | Protech | Labor |  |  | 1
JTMEC | JTMEC | Labor |  |  | 1
HV Auditor | HV Auditor | Labor |  |  | 1
Chubb | Chubb | Labor |  |  | 1
Boily | Boily | Labor |  |  | 1
CSC | CSC | Labor |  |  | 1
Concrete Pump | Concrete Pump | Labor |  |  | 1
Redpath Backhoe | Redpath Backhoe | Labor |  |  | 1
TTT-EWP-1 | EWP | Labor |  |  | 1
Plumber | Plumber | Labor |  |  | 1
Fitter | Fitter | Labor |  |  | 1
Rigger | Rigger | Labor |  |  | 1
T/A | Required T/A | Labor |  |  | 1
Scaff | Scaff | Labor |  |  | 1
60t Crane | 60t Crane | Labor |  |  | 1
TTT-ForkliftOP | Forklift Operator | Labor |  |  | 1
Mancala | Mancala | Labor |  |  | 1
ISS | ISS | Labor |  |  | 1
Comms Tech | Comms Tech | Labor |  |  | 1
Civil 300% | Civil 300% | Labor |  |  | 1
Civil 400% | Civil 400% | Labor |  |  | 1
Civil200% | Civil200% | Labor |  |  | 1
Elect400% | Elect400% | Labor |  |  | 1
Elec200% | Elec200% | Labor |  |  | 1
Plumber200% | Plumber200% | Labor |  |  | 1
EWP ESCAV | EWP ESCAV | Labor |  |  | 1
Boily200% | Boily200% | Labor |  |  | 1
Rigger200% | Rigger200% | Labor |  |  | 1
Banlaw rep | Banlaw rep | Labor |  |  | 1
Elect 200% | Elect 200% | Labor |  |  | 1
TSFE5 & WSP | TSFE5 & WSP | Labor |  |  | 1
CAN_Z2_B2F | CAN Borrow to Fill (TSFE5 - Zone 2) | Material | Cubic Metres |  | 0
CAN_TS | CAN Topsoil Strip | Material | Cubic Metres |  | 0
CAN_UNS | CAN Unsuitable Removal | Material | Cubic Metres |  | 0
CAN_FP | CAN Foundation Preparation | Material | Square Metres |  | 0
CAN_Z1_B2F | CAN Borrow to Fill (TSFE5 - Zone 1) | Material | Cubic Metres |  | 0
CAN_Z4 | CAN Rock Protection (Zone 4) | Material | Cubic Metres |  | 0
CAN_Z5 | CAN Rock Fill (Zone 5) | Material | Cubic Metres |  | 0
CAN_Z6 | CAN Gravel Surfacing (Zone 6) | Material | Cubic Metres |  | 0
CAN_Z7 | CAN Topsoil & Grass (Zone 7) | Material | Cubic Metres |  | 0
CAN_C2Sp | CAN Cut to Spoil | Material | Cubic Metres |  | 0
CAN_DDEx | CAN Diversion Drain Excavation | Material | Cubic Metres |  | 0
CAN_SUMP | CAN Sump Materials | Material | Each |  | 0
CAN_GEO | CAN Geotextile | Material | Square Metres |  | 0
CAN_REO | CAN Reinforcing | Material | Square Metres |  | 0
CAN_CONC | CAN Concrete | Material | Cubic Metres |  | 0
CAN_Z4A | CAN Zone 4A Bund | Material | Lineal Metres |  | 0
CAN_SG | CAN Subgrade Preparation | Material | Square Metres |  | 0
CAN_Z2_C2F | CAN Cut to Fill (WSP - Zone 2) | Material | Cubic Metres |  | 0
CAN_HDPE | CAN HDPE Liner | Material | Square Metres |  | 11
CAN_Z2A | CAN Zone 2A Bund | Material | Cubic Metres |  | 0
TTT-CONCRETE | Concrete M3 | Material | Cubic Metres |  | 8
TSFE5WSP-MECH | Mechanical | Labor |  |  | 1
TSFE5WSP-E&I | E&I | Labor |  |  | 1
TSFE5WSP-SUP | Supervisor | Labor |  |  | 1
CAN_MAT | CANNINGTON MATERIALS | Material |  |  | 0
TTT-BLAW | Banlaw | Labor |  |  | 1
TTT-PLUM | Plumber | Labor |  |  | 1
Groote - JQEL | Groote - J Quarry & Eastern Leases | Labor |  |  | 1
JQEL - MATERIAL | J Quarry & Eastern Leases Material Resources | Material |  |  | 8
JQEL-M01 | Clearing, Grubbing & Burning | Material | Square Metres |  | 8
JQEL-M02 | Topsoil Stripping | Material | Cubic Metres |  | 8
JQEL-M04 | General Fill Activities | Material | Cubic Metres |  | 8
JQEL-M06 | Base Course - NORTH | Material | Cubic Metres |  | 8
JQEL-M07 | Wearing Course - NORTH | Material | Cubic Metres |  | 8
JQEL-M03 | Subgrade Preparation | Material | Square Metres |  | 8
JQEL-M05 | Sub Base - NORTH | Material | Cubic Metres |  | 8
JQEL-M09 | Revegetation - BATTERS | Material | Square Metres |  | 8
JQEL-M11 | Foundation Preparation | Material | Square Metres |  | 8
JQEL-M12 | Sand | Material | Cubic Metres |  | 8
JQEL-M15 | Geotextile | Material | Square Metres |  | 8
JQEL-M16 | Rip Rap | Material | Cubic Metres |  | 8
JQEL-M17 | Structural Backfill | Material | Cubic Metres |  | 8
JQEL-M10 | Drainage Structures Excavation | Material | Cubic Metres |  | 8
JQEL-M21 | Polymer Spray Seal | Material | Square Metres |  | 8
JQEL-M18 | Cement Stabilised Sand | Material | Cubic Metres |  | 8
JQEL-M22 | Road Furniture | Material |  |  | 8
JQEL-M05-1 | Sub Base - SOUTH | Material | Cubic Metres |  | 8
JQEL-M06-2 | Base Course - SOUTH | Material | Cubic Metres |  | 8
JQEL-M07-2 | Wearing Course - SOUTH | Material | Cubic Metres |  | 8
JQEL-M07-4 | Wearing Course - BRIDGE | Material | Cubic Metres |  | 8
JQEL-M07-6 | Wearing Course - POLYMER TREATED | Material | Cubic Metres |  | 8
JQEL-M07-7 | Wearing Course - POLYMER TREATED (2) | Material | Cubic Metres |  | 8
JQEL-M21-1 | Polymer Spray Seal (2) | Material | Square Metres |  | 8
JQEL-M23 | Sediment Basin Construction [J Quarry Road] | Material | Lump Sum |  | 8
JQEL-M25 | ESC Controls | Material | Lump Sum |  | 8
JQEL-M13 | Corrugated Steel Pipes (CSP) | Material |  |  | 8
JQEL-M14 | Backfill Materials | Material |  |  | 8
JQEL-M13-2 | 1800 CSP Install | Material | Lineal Metres |  | 8
JQEL-M14-1 | Flowable Backfill | Material | Cubic Metres |  | 8
JQEL-M04-1 | General Fill - Cut to FIll (North) | Material | Cubic Metres |  | 8
CG-1 | Clearing, Grubbing & Burning (North) | Material | Square Metres |  | 8
CG-2 | Clearing, Grubbing & Burning (South) | Material | Square Metres |  | 8
JQEL-M02-1 | Topsoil Stripping (North) | Material | Cubic Metres |  | 8
JQEL-M02-2 | Topsoil Stripping (South Borrow) | Material | Cubic Metres |  | 8
JQEL-M02-3 | Topsoil Stripping (South Haul Road) | Material | Cubic Metres |  | 8
JQEL-M04-2 | General Fill - Cut to Fill (South) | Material | Cubic Metres |  | 8
JQEL-M04-3 | General Fill - Borrow to Fill (North) | Material | Cubic Metres |  | 8
JQEL-M04-4 | General Fill - Borrow to Fill (South) | Material | Cubic Metres |  | 8
JQEL-M04-5 | General Fill - Safety Bund Construction | Material | Cubic Metres |  | 8
JQEL-M22-1 | Guidepost Install | Material | Each |  | 8
JQEL-M22-2 | Sign Install [J Quarry Road] | Material | Each |  | 8
JQEL-M13-1 | 900 CSP Install AND EL 900mm CSP in LV Sideroad | Material | Lineal Metres |  | 8
JQEL-M10-2 | Culvert Boxout | Material | Cubic Metres |  | 8
JQEL-M10-3 | Excavation & Replacement of Unsuitable | Material | Cubic Metres |  | 8
JQEL-M16-1 | Rip Rap Type 3 | Material | Cubic Metres |  | 8
JQEL-M09-1 | Revegetation - DRAINS & BERMS | Material | Square Metres |  | 8
JQEL-M10-4 | Batter Chute & Drain Excavation | Material | Cubic Metres |  | 8
JQEL-M04-7 | Clean Water Diversion Berms | Material |  |  | 8
MUD | MUD Washing Project | Nonlabor |  |  | 1
MUD-Budget | FS Budget Cost | Material | Australian Dollars |  | 1
S8D-NWE | New World Ecosys | Labor |  |  | 0
Worley_RSRC | Worley Resource | Labor |  |  | 1
P8DB | P8DB | Labor |  |  | 1
COPP21013 | Quindanning FS | Labor |  |  | 1
Q_ENGCV1 | Engineer Civil (Pr) | Labor |  |  | 1
Q_ENGCV2 | Engineer Civil (SPE) | Labor |  |  | 1
Q_ENGEL | Engineer Electrical | Labor |  |  | 1
Q_DOCON | Document Controller | Labor |  |  | 1
Q_COST | Cost Controller | Labor |  |  | 1
Q_SCHED | Scheduler | Labor |  |  | 1
Q_EST | Estimator | Labor |  |  | 1
WORS | Worsley Project | Labor |  |  | 1
COPP19204 | Hotham North PFS | Labor |  |  | 1
LEGAL COUNCIL | Legal Council | Labor |  |  | 1
Cost Engineer | Cost Engineer | Labor |  |  | 1
SENIOR DOCUMENT CONTROLLER | Senior Document Controller | Labor |  |  | 1
SENIOR CIVIL ENGINEER | Senior Civil Engineer | Labor |  |  | 1
SENIOR CIVIL ENGINEER COST/USE | SENIOR CIVIL ENGINEER COST/USE | Material |  |  | 8
PRINCIPLE CIVIL ENGINEER | Principle Civil Engineer | Labor |  |  | 1
PRINCIPLE ELECTRICAL ENGINEER | Principle Electrical Engineer | Labor |  |  | 1
PRINCIPLE PROCESS ENGINEER COST/USE | PRINCIPLE PROCESS ENGINEER COST/USE | Material |  |  | 8
PRINCIPLE MECHANICAL ENGINEER COST/USE | PRINCIPLE MECHANICAL ENGINEER COST/USE | Material |  |  | 8
LEAD COMMUNICATIONS ENGINEER | Lead Communications Engineer | Labor |  |  | 1
SENIOR MECHANICAL ENGINEER COST/USE | SENIOR MECHANICAL ENGINEER COST/USE | Material |  |  | 8
HNP1 | Hotham North PFS | Labor |  |  | 1
19204-PMGR | Project Manager | Labor |  |  | 1
19204-SPER | Senior Project Engineer | Labor |  |  | 1
19204-SPLN | Senior Planner | Labor |  |  | 1
19204-CTER | Cost Engineer | Labor |  |  | 1
19204-SEST | Senior Estimator | Labor |  |  | 1
19204-SDOC | Senior Document Controller | Labor |  |  | 1
19204-SMER | Specialist Mining Engineer | Labor |  |  | 1
19204-PPER | Principal Process Engineer | Labor |  |  | 1
19204-PCER | Principal Civil Engineer | Labor |  |  | 1
19204-PMER | Principal Mechanical Engineer | Labor |  |  | 1
19204-PEER | Principal Electrical Engineer | Labor |  |  | 1
19204-ELER | Electrical Engineer | Labor |  |  | 1
19204-LCER | Lead Communications Engineer | Labor |  |  | 1
19204-SGER | Senior Geotechnical Engineer | Labor |  |  | 1
19204-PRER | Principal Risk Engineer | Labor |  |  | 1
19204-LCDE | Lead Civil Designer | Labor |  |  | 1
19204-LMDE | Lead Mechanical Designer | Labor |  |  | 1
19204-SEDE | Senior Electrical Designer | Labor |  |  | 1
19204-SCER | Senior Civil Engineer | Labor |  |  | 1
NeM | Neil McDaid | Labor |  |  | 1
LiB | Liezl Bezuidenhout | Labor |  |  | 1
PT | Peter Trewhella | Labor |  |  | 1
CAL | Calibre | Labor |  |  | 1
JaS | Jade Singleton | Labor |  |  | 1
MaP | Mark Paulton | Labor |  |  | 1
COPP18134 | Hotham Mine Development | Labor |  |  | 1
Nullaga_1 | Cost | Nonlabor
S32-HON FS | S32 HON FS Manhours | Labor |  |  | 1
DIRC | Direct Labour | Labor |  |  | 1
NU-CE | Construction Equipment | Nonlabor |  |  | 1
NU-DS | Contracts Distribution | Nonlabor |  |  | 1
NU-LB | Labour Cost | Nonlabor |  |  | 1
NU-BM | Bulk Material | Nonlabor |  |  | 1
CS | Contract Specialist | Labor |  |  | 1
G-2010 | Project Management | Labor |  | A | 1
G-2020 | Project Engineering | Labor |  | A | 1
G-3071 | Structural Engineering | Labor |  | A | 1
G-3051 | Instrumentation Engineering | Labor |  | A | 1
G-3042 | Electrical Design | Labor |  | A | 1
G-3041 | Electrical Engineering | Labor |  | A | 1
Worley-Global-RSRC | Worley Global Resource | Labor |  | Global | 1
G-0000 | Labour Resource Pool | Labor |  | Global | 1
G-2000 | Project Management & Coordination | Labor |  | A | 1
G-3000 | Engineering | Labor |  | A | 1
G-3070 | Structural | Labor |  | A | 1
G-3050 | Instrumentation | Labor |  | A | 1
G-3040 | Electrical | Labor |  | A | 1
CTG-Budget | CTG FS Budget Cost 2022 | Material | Australian Dollars |  | 1
Worley-RSRC | Worley Resources | Labor |  |  | 1
WHD-Budget | WHD PFS Budget Cost 2022 | Material | Australian Dollars |  | 1
Worley-Canada-RSRC | Worley Canada Resources | Labor |  |  | 1
WP-Cal-RSRC | WorleyPArsons Calgary Resources | Labor |  |  | 1
218001-00026 | Aemetis Carbon Zero 1 Resource | Labor |  |  | 1
GID SO | GID Resource | Labor |  |  | 1
GID Process | GID Process | Labor |  |  | 1
WHD-Budget-1 | WHD PFS Budget Hours 2022 | Labor |  |  | 0
Q_SDESCV | Designer Senior Civil | Labor |  |  | 1
Q_PLN | Planner | Labor |  |  | 1
Q_SDESEL | Designer Senior Electrical | Labor |  |  | 1
Q_LDESME | Designer Lead Mechanical | Labor |  |  | 1
Q_LENGST | Engineer Lead Structural | Labor |  |  | 1
Q_LDESCV | Designer Lead Civil | Labor |  |  | 1
Q_SENGEL | Engineer Senior Electrical | Labor |  |  | 1
Q_SDESST | Designer Senior Structural | Labor |  |  | 1
Q_SENGCV | Engineer Senior Civil | Labor |  |  | 1
Q_GENG | Engineer Graduate | Labor |  |  | 1
Q_SENGME | Engineer Senior Mechanical | Labor |  |  | 1
TR3-Budget | TR3 FS Budget Cost 2022 | Material | Australian Dollars |  | 1
TR3-Budget-1 | TR3 PFS Budget Hours 2022 | Labor |  |  | 0
LU | Labour_Unit | Labor |  |  | 1
Mining %200 | Mining %200 | Labor |  |  | 1
Mining %300 | Mining %300 | Labor |  |  | 1
Skidsteer | Skidsteer | Labor |  |  | 1
Construction Crew %3 | Construction Crew %300 | Labor |  |  | 1
Diesel Welder | Diesel Welder | Labor |  |  | 1
IT | IT | Labor |  |  | 1
Civil %200 | Civil %200 | Labor |  |  | 1
Civil %300 | Civil %300 | Labor |  |  | 1
Boilermaker | Boilermaker | Labor |  |  | 1
Fitter %200 | Fitter %200 | Labor |  |  | 1
TTT-EXVOP | Excavator Operator | Labor |  |  | 1
Surveyor 100% | Surveyor 100% | Labor |  |  | 1
Surface Drilling %3 | Surface Drilling %300 | Labor |  |  | 1
UG Drilling %300 | UG Drilling %300 | Labor |  |  | 1
Draftsman-1 | Draftsman | Labor |  |  | 1
HMD_MHR | Caliber HON Execution Manhours | Labor |  |  | 1
19204-CE | Civil Engineer | Labor |  |  | 1
19204-CDE | Civil Designer | Labor |  |  | 1
19204-STE | Structural Engineer | Labor |  |  | 1
19204-STDE | Structural Designer | Labor |  |  | 1
19204-ARCH | Architect | Labor |  |  | 1
19204-ARCHDE | Architect Designer | Labor |  |  | 1
19204-GENE | General Engineer | Labor |  |  | 1
19204-GENDE | General Designer | Labor |  |  | 1
19204-MEE | Mechanical Engineer | Labor |  |  | 1
19204-MEDE | Mechanical Designer | Labor |  |  | 1
19204-ELE | Electrical Engineer | Labor |  |  | 1
19204-ELDE | Electrical Designer | Labor |  |  | 1
19204-CODE | Controls Designer | Labor |  |  | 1
19204-COE | Controls Engineer | Labor |  |  | 1
TTT-SKIDSTOP | Skid Steer Operator | Labor |  |  | 1
TTT-LV-UGOP | UG Light Vehicle Operator | Labor |  |  | 1
TTT-IT-UGOP | UG Integrated Tool Carrier Operator | Labor |  |  | 1
TTT-MiningCC-UG | UG Mining Cons Crew | Labor |  |  | 1
TTT-UGDrill | UG Drilling | Labor |  |  | 1
TTT-SurfDrill | Surface Drilling | Labor |  |  | 1
TTT-WEL | Welder | Labor |  |  | 1
Eng | Eng | Labor |  |  | 1
DRC Drilling %300 | DRC Drilling %300 | Labor |  |  | 1
Redparth C/Crew %300 | Redparth C/Crew %300 | Labor |  |  | 1
Geotech | Geotech | Labor |  |  | 1
Survey 100% | Survey 100% | Labor |  |  | 1
UG LV | UG LV | Labor |  |  | 1
Engineer | Engineer | Labor |  |  | 1
Draftsman | Draftsman | Labor |  |  | 1
20 | 20 | Labor |  |  | 1
21 | 21 | Labor |  |  | 1
22 | 22 | Labor |  |  | 1
23 | 23 | Labor |  |  | 1
24 | 24 | Labor |  |  | 1
25 | 25 | Labor |  |  | 1
26 | 26 | Labor |  |  | 1
27 | 27 | Labor |  |  | 1
28 | 28 | Labor |  |  | 1
29 | 29 | Labor |  |  | 1
32 | 32 | Labor |  |  | 1
33 | 33 | Labor |  |  | 1
TA | TA | Labor |  |  | 1
Franna | Franna | Labor |  |  | 1
TTT-TruckOP | Truck Driver | Labor |  |  | 1
TTT-Spotter | Spotter | Labor |  |  | 1
QBirt -Groote - JQEL | QBirt - Groote - J Quarry & Eastern Leases | Labor |  |  | 1
Qbirt-Labour | Qbirt Eastern Leases Labour | Labor |  |  | 1
Qbirt - MATERIAL | Qbirt - J Quarry & Eastern Leases Material Resources | Material |  |  | 8
QBirt | Qbirt - J Quarry & Eastern Leases Fleet Resources | Labor |  |  | 1
QBirt - JQEL - PLANT | QBirt - J Quarry & Eastern Leases Plant | Nonlabor |  |  | 1
QB Directs | QBirt - Directs | Labor |  |  | 1
QBirt Indirects | QBirt - Indirects | Labor |  |  | 1
JQEL-M19 | Blinding 50mm thk | Material | Cubic Metres |  | 8
JQEL-P04 | Excavator <20T | Nonlabor |  |  | 1
JQEL-P05 | Excavator 20T-40T | Nonlabor |  |  | 1
JQEL-P06 | Excavator 60T-80T | Nonlabor |  |  | 1
JQEL-P09 | Articulated Dump Truck | Nonlabor |  |  | 1
JQEL-P12 | Rigid Water Truck | Nonlabor |  |  | 1
JQEL-P13 | Grader 14 | Nonlabor |  |  | 1
JQEL-P16 | Roller | Nonlabor |  |  | 1
JQEL-P17 | Loader | Nonlabor |  |  | 1
JQEL-OP | QBirt - Operator Manhours | Labor |  |  | 1
JQEL-M06-4 | Base Course - EMERALD RIVER ROAD | Material | Cubic Metres |  | 8
JQEL-M07-5 | Wearing Course - EMERALD RIVER ROAD | Material | Cubic Metres |  | 8
JQEL-M26 | Miscellaneous Supply Items | Material |  |  | 8
JQEL-M27 | Subcontracted Services | Material |  |  | 8
JQEL-M06a | Base Course - EASTERN LEASES | Material | Cubic Metres |  | 8
JQEL-M07-8 | Wearing Course - EASTERN LEASES Avg. Rate | Material | Cubic Metres |  | 8
JQEL-M28 | Eastern Leases Concrete Structures | Material |  |  | 8
JQEL-M29 | Sand Bridge Construction - EMERALD RIVER CROSSING | Material |  |  | 8
JQEL-M30 | Arch Structure Access - REMOVAL OF MUD MATS | Material | Lump Sum |  | 8
JQEL-P18 | Dozer D8 | Nonlabor |  |  | 1
QB-Civ | QBirt - Civil Crews | Labor |  |  | 1
Hully P&E | Hully P&E | Labor |  |  | 1
QB-PM | QBirt - PM | Labor |  |  | 1
QB-Survey | QBirt - Survey | Labor |  |  | 1
QB-Main | QBirt - Service and Maintenance | Labor |  |  | 1
QB-Soil | QBirt - Soil testing | Labor |  |  | 1
ELS MS | ELS - Measured Commodities | Material |  |  | 8
Cm-1 | N4020100-GP | Nonlabor |  |  | 1
Cm-2 | N4020150-GP | Nonlabor |  |  | 1
Cm-3 | N4020120-LH | Nonlabor |  |  | 1
Cm-8 | S5010600-LH | Nonlabor |  |  | 1
Cm-9 | N2020100-GP | Nonlabor |  |  | 1
BW | Batching Water | Nonlabor |  |  | 1
Rft | Reinforcement | Nonlabor |  |  | 1
JQEL-M10-1 | Rock Boxout | Material | Cubic Metres |  | 8
JQEL-M02-4 | Topsoil Stripping Borrow Areas AVERAGE Rate | Material | Cubic Metres |  | 12
JQEL-M02-5 | Topsoil Stripping All Areas [Excl. Borrows] AVERAGE Rate | Material | Cubic Metres |  | 12
JQEL-M16-2 | Rip Rap Type 2 - Check Dams AND EL Culvert Protection | Material | Cubic Metres |  | 8
JQEL-M10-5 | Detailed Excavation for Slabs & Abutments | Material | Cubic Metres |  | 8
JQEL-M26-3 | Steel Reinforcement for CFA Piles | Material | Tons |  | 8
JQEL-M26-1 | Collapsible Road Divider | Material | Each |  | 8
JQEL-M27-3 | Sheet Pile Installation (by others) | Material | Lineal Metres |  | 8
JQEL-M27-2 | W Guard Barrier - Design, supply & install | Material | Lineal Metres |  | 8
JQEL-M12-1 | Bedding Layer EL Culverts | Material | Cubic Metres |  | 8
JQEL-M13-4 | EL 900mm CSP Install in Haul Road | Material | Lineal Metres |  | 8
JQEL-M13-5 | EL 1200mm CSP Install | Material | Lineal Metres |  | 8
JQEL-M13-3 | EL 600mm CSP Install in Side Road | Material | Lineal Metres |  | 8
JQEL-M13-6 | EL 1800mm CSP Install | Material | Lineal Metres |  | 8
JQEL-M23-1 | Sediment Basin Construction [Eastern Leases] | Material | Lump Sum |  | 8
JQEL-M06a-1 | Trim Base Course - EASTERN LEASES | Material |  |  | 8
JQEL-M07-8-1 | Trim Wearing Course - EASTERN LEASES | Material | Square Metres |  | 8
JQEL-M28-1 | Spillwat Reinforced Concrete Sill | Material | Cubic Metres |  | 8
JQEL-M28-2 | Spillway Concrete Bollards | Material | Each |  | 8
JQEL-M04-9 | General Fill - EASTERN LEASES Haul Road Embankment | Material |  |  | 8
JQEL-M04-10 | Cut to Spoil 500m Zone 2 WATER STORAGE | Material | Cubic Metres |  | 8
JQEL-M27-4 | Supply & Install CFA Piles (by others) | Material | Lineal Metres |  | 8
JQEL-M27-5 | Supply & Install Corrugated Steel Arch Structure (by others) | Material | Lineal Metres |  | 8
JQEL-M04-11 | Detailed Abutment Backfill - EMERALD RIVER CROSSING | Material | Cubic Metres |  | 8
JQEL-M04-12 | Structural Backfill of ARCH STRUCTURE | Material | Cubic Metres |  | 8
JQEL-M15-2 | Emerald River ARCH Subsoil Drainage | Material | Lineal Metres |  | 8
JQEL-M27-6 | Construction of Concrete Sill Beams | Material | Cubic Metres |  | 8
JQEL-M10-6 | Truncate River Banks - EMERALD RIVER ARCH | Material | Cubic Metres |  | 8
JQEL-M29-1 | Bridging Sand | Material | Cubic Metres |  | 8
JQEL-M29-2 | Sand Bridge - GEOTEXTILE | Material | Cubic Metres |  | 8
JQEL-M29-3 | Sand Bridge - ROCK | Material | Square Metres |  | 8
JQEL-M29-4 | Sand Bridge - REMOVAL TO SPOIL | Material | Lump Sum |  | 8
JQEL-M30-1 | Arch Structure Access - SET-UP INCLUDING CRANE PADS | Material | Lump Sum |  | 8
JQEL-M10-7 | Anchor Trench Excavation - EMERALD RIVER CROSSING | Material | Lineal Metres |  | 8
JQEL-M04-13 | Backfill Anchor Trench - EMERALD RIVER CROSSING | Material | Cubic Metres |  | 8
JQEL-M27-7 | Bitumen Impregnated Geomembrane (BGM) Supply & Install | Material | Square Metres |  | 8
JQEL-M14-2 | Stabilised Sand Kerb | Material | Cubic Metres |  | 8
JQEL-M14-3 | Stabilised Sand Backfill - ANCHOR TRENCH | Material | Cubic Metres |  | 8
JQEL-M14-4 | Wearing Course Backfill - ANCHOR TRENCH | Material | Cubic Metres |  | 8
EL-E&I | Sub-Contractors - E&I | Labor |  |  | 1
EL-Comms | Sub-Contractors - Communications | Labor |  |  | 1
EL-ME | Sub-Contractors - Mechanical | Labor |  |  | 1
FEN | Sub-Contractor - Fencing | Labor |  |  | 1
GEN-OW-1 | Owners Team - Office | Labor |  |  | 1
M2 | Meters Squared Commodities | Material |  |  | 8
M3 | Cubic Meters Commodities | Material |  |  | 8
JQEL-M22-3 | Sign Install [Eastern Leases] | Material | Each |  | 8
JQEL-M04-5ii | Safety Bund Construction (Eastern Leases) Water Storage Facility | Material | Cubic Metres |  | 8
JQEL-M04-5iii | Wheel Stop Windrows [Middlings] | Material | Cubic Metres |  | 8
JQEL-M04-9i | General Fill [SHORT HAUL] | Material | Cubic Metres |  | 8
JQEL-M04-9ii | General Fill [LONG HAUL] | Material | Cubic Metres |  | 8
JQEL-M04-5iv | Common Intersection LV Safety Bund | Material | Cubic Metres |  | 8
JQEL-M27-7-1 | Fasten BGM to ARCH Structure | Material | Lineal Metres |  | 8
JQEL-M04-9(ii)a | Trimming of General Fill HAUL ROAD | Material | Square Metres |  | 8
Hully Ind | Hully Indirects | Labor |  |  | 1
JQEL - PLANT | J Quarry & Eastern Leases Plant | Nonlabor |  |  | 1
JQEL-20-40TEX | Excavator 20T-40T | Nonlabor |  |  | 1
JQEL-ADT | Articulated Dump Truck | Nonlabor |  |  | 1
JQEL-16M | 16M Grader | Nonlabor |  |  | 1
JQEL-825 | 825 Roller | Nonlabor |  |  | 1
JQEL-657 | 657 Scraper | Nonlabor |  |  | 1
JQEL-D10 | Dozer D10 | Nonlabor |  |  | 1
JQEL-SDR | Smooth Drum Roller | Nonlabor |  |  | 1
JQEL-AWT | Articulated Water Truck | Nonlabor |  |  | 1
JQEL-BCT | Bobcat | Nonlabor |  |  | 1
Cm-5 | S5020100-GP | Nonlabor |  |  | 1
Cm-6 | S5020120-LH | Nonlabor |  |  | 1
Cm-7 | S5020150-LH | Nonlabor |  |  | 1
Y1731 | Procurement | Labor |  |  | 1
Y1940 | Consultants & 3rd Parties | Labor |  |  | 1
Y1200-M102107 | GA Drawing: Construction Camp and Laydown areas 3: Drawing | Labor |  |  | 1
Y1200-M102108 | GA Drawing: Construction Camp and Laydown areas 3: Drawing | Labor |  |  | 1
Y1200-M102109 | Cross sections Drawing: Construction Camp and Laydown 3: Drawing | Labor |  |  | 1
Y1200-M102110 | Cross sections Drawing: Construction Camp and Laydown 3: Drawing | Labor |  |  | 1
Y1200-M102111 | Typical Detail Drawing: Construction Camp and Laydown 2: Drawing | Labor |  |  | 1
Y1200-M102112 | Perimeter fence and gate GA drawing 3: Drawing | Labor |  |  | 1
Y1200-M102113 | Perimeter fence and gate GA drawing 3: Drawing | Labor |  |  | 1
Y1200-M102114 | Perimeter Fence & Gate details Drawing 3: Drawing | Labor |  |  | 1
Y1200-M102115 | Perimeter Fence & Gate details Drawing 3: Drawing | Labor |  |  | 1
Y1200-M102116 | MCC Panel Design: MCC Drawing | Labor |  |  | 1
Y1200-M102117 | Gen Arrangements of MCC : MCC GA Drawing | Labor |  |  | 1
Y1200-M102118 | Single Line Diagrams: Single Line Diagrams | Labor |  |  | 1
Y1200-M102119 | Cable Schedules: Cable schedule List | Labor |  |  | 1
Y1200-M102120 | Earth Resistivity-Test & Report: Earth Resistivity-Test & Report | Labor |  |  | 1
Y1200-M102121 | New Earthing & Lightning and Protection Design: Earthing & Lighning design report | Labor |  |  | 1
Y1200-M102122 | Lighting Layout /Small Power Plan Layout: Earthing and Lightning report | Labor |  |  | 1
Y1200-M102123 | Lighting Layout /Small Power Sections/Elevations Layout: New Earthing and Lightning Dwgs | Labor |  |  | 1
Y1200-M102124 | Lighting Layout /Small Power : New Earthing and Lightning Dwgs | Labor |  |  | 1
Y1200-M102125 | Rail Indexer: Rail Indexer design & Supply package | Labor |  |  | 1
Y1200-M102126 | Rail Indexer Foundation: Rail Indexret Foundation dwgs | Labor |  |  | 1
Y1200-M102127 | Water Demand : Water demand statement | Labor |  |  | 1
Y1200-M102128 | Water reticulation Layout drawing 2: Drawing | Labor |  |  | 1
Y1200-M102129 | Water longsection drawing 2: Drawing | Labor |  |  | 1
Y1200-M102130 | Typical water detail drawing 3: Drawing | Labor |  |  | 1
Y1200-M102131 | Typical water detail drawing 3: Drawing | Labor |  |  | 1
Y1200-M102132 | Sewer discharge calculation: Sewer dischage statement | Labor |  |  | 1
Y1200-M102133 | Sewer reticulation Layout drawing 2: Drawing | Labor |  |  | 1
Y1200-M102134 | Sewer longsection drawing 2: Drawing | Labor |  |  | 1
Y1200-M102135 | Typical Sewer detail drawing 3: Drawing | Labor |  |  | 1
Y1200-M102136 | Typical Sewer detail drawing 3: Drawing | Labor |  |  | 1
Y1200-M102137 | Stormwater hydrology (run-off) report: Stormwater report | Labor |  |  | 1
Y1200-M102138 | Stormwater structures layout drawing 3: Drawing | Labor |  |  | 1
Y1200-M102139 | Stormwater structures layout drawing 3: Drawing | Labor |  |  | 1
Y1200-M102140 | Stormwater culvrt details 3: Drawing | Labor |  |  | 1
Y1200-M102141 | Stormwater culvrt details 3: Drawing | Labor |  |  | 1
Y1200-M102143 | Data & Comms sleeve layout drawing 3: Drawing | Labor |  |  | 1
Y1200-M102144 | Typical dats sleeve and draw box details: Drawing | Labor |  |  | 1
Y1200-M102149 | Earthworks Design, Drawings & Specifications: Drawings | Labor |  |  | 1
Y1200-M102150 | Roadworks Design, Drawings & Specifications: Drawings | Labor |  |  | 1
Y1200-M102151 | Crossing Blocks Design, Drawings & Specifications: Drawings | Labor |  |  | 1
Y1200-M102152 | Culverts: Detail Design & Drawings: Drawing | Labor |  |  | 1
Y1200-M102153 | Culverts: Specifications: Technical note | Labor |  |  | 1
Y1200-M102161 | Specifications: Technical note | Labor |  |  | 1
Y1200-M102162 | Design & Drawings: Drawing | Labor |  |  | 1
Y1200-M102165 | Traffic Impact Study??: | Labor |  |  | 1
Y1200-M102166 | Preliminary Design Report & A3 Drawings: | Labor |  |  | 1
Y1200-M102167 | GA Drawing: Construction roads 3: | Labor |  |  | 1
Y1200-M102168 | Long section & cross section Drawing 3: | Labor |  |  | 1
Y1200-M102169 | Typical Road drawing 1: | Labor |  |  | 1
Y1200-M102170 | In principle approval - NC Province Roads Dept: | Labor |  |  | 1
Y1200-M102171 | Intersection 1GA drawings 4: Drawing | Labor |  |  | 1
Y1200-M102172 | Intersection 1GA drawings 4: Drawing | Labor |  |  | 1
Y1200-M102173 | Long section & cross section Drawing 2: Drawing | Labor |  |  | 1
Y1200-M102174 | Typical Road drawing 2: Drawing | Labor |  |  | 1
Y1200-M102178 | PFS Review: Technical Note | Labor |  |  | 1
Y1200-M102179 | PFS BOD report review: Technical Note | Labor |  |  | 1
Y1200-M102180 | PFS SOW Review: Technical Note | Labor |  |  | 1
Y1200-M102181 | Scope of Work Report: SoW Report | Labor |  |  | 1
Y1200-M102182 | Basis of Design: Basis of Design Report | Labor |  |  | 1
Y1200-M102183 | FS Engineering Management Plan: FS Eng Man Plan | Labor |  |  | 1
Y1200-M102184 | Block Plan: Block Plan | Labor |  |  | 1
Y1200-M102185 | Topopraphical survey - LiDAR: Digital Terrain Model | Labor |  |  | 1
Y1200-M102186 | Bench Mark and Site survey Dwgs: Site Survey & BM Dwg | Labor |  |  | 1
Y1200-M102187 | Geotechnical Investigations: Geotech Report | Labor |  |  | 1
Y1200-M102188 | Site Visit Report: Technical Note | Labor |  |  | 1
Y1200-M102189 | Engineering Progress Report: Progress Report | Labor |  |  | 1
Y1200-M102190 | Design meeting: Design Minutes | Labor |  |  | 1
Y1200-M102191 | Project Registers: Issues-, Design Decision register: Updated registers | Labor |  |  | 1
Y1200-M102192 | Project Review: Review Report | Labor |  |  | 1
Y1200-M102193 | Calculations Report: Calculations Report | Labor |  |  | 1
Y1200-M102194 | Calculations Report: Calculations Report | Labor |  |  | 1
Y1200-M102195 | Calculations Report: Calculations Report | Labor |  |  | 1
Y1200-M102196 | Calculations Report: Calculations Report | Labor |  |  | 1
Y1200-M102197 | Design Report: Design Report | Labor |  |  | 1
Y1200-M102198 | Design & Verification : Design & Verification report | Labor |  |  | 1
Y1200-M102199 | HAZOP Input: HAZOP review input | Labor |  |  | 1
Y1200-M102200 | Risk Assessments: Risk Assessment input | Labor |  |  | 1
Y1200-M102201 | Lessons Learnt Report: Lessons Learnt Report | Labor |  |  | 1
Y1200-M102202 | Safety in Design : Safety in design review report | Labor |  |  | 1
Y1200-M102203 | Constructability : Constructability Review Report | Labor |  |  | 1
Y1200-M102204 | BoQ: BoQ | Labor |  |  | 1
Y1200-M102205 | Technical Specifications : Technical Specifications | Labor |  |  | 1
Y1200-M102206 | Procurement: Procurement Report input portion | Labor |  |  | 1
Y1200-M102207 | FS Report (Engineering portion): FS Report Eng Portion | Labor |  |  | 1
Y1200-M102208 | Execution Engineering Management Plan: Execution Eng Man Plan | Labor |  |  | 1
Y1200-M102209 | Model - Survey - Existing Ground Surface | Labor |  |  | 1
Y1200-M102210 | Model - Survey - Point Cloud | Labor |  |  | 1
Y1200-M102211 | Model - Survey - Structures | Labor |  |  | 1
Y1200-M102212 | Model - Rail - Corridor, VA, HA | Labor |  |  | 1
Y1200-M102214 | Model - Rail - Track Signalling | Labor |  |  | 1
Y1200-M102215 | Model - Rail - Indexer | Labor |  |  | 1
Y1200-M102216 | Model - Rail - Level Crossing | Labor |  |  | 1
Y1200-M102217 | Model - Utilities - Electrical | Labor |  |  | 1
Y1200-M102218 | Model - Utilities - Data | Labor |  |  | 1
Y1200-M102219 | Model - Utilities - Potable Water | Labor |  |  | 1
Y1200-M102220 | Model - Utilities - Sewer | Labor |  |  | 1
Y1200-M102221 | Model - Drainage - Culverts | Labor |  |  | 1
Y1200-M102222 | Model - Drainage - Network | Labor |  |  | 1
Y1200-M102223 | Model - Roads - Intersection 1 | Labor |  |  | 1
Y1200-M102224 | Model - Roads - Construction | Labor |  |  | 1
Y1200-M102225 | Model - Perimeter Fence and Gates | Labor |  |  | 1
Y1200-M102226 | Model - Federated | Labor |  |  | 1
Y1200-M101101 | GA Drawing: Construction roads 3: Drawing | Labor |  |  | 1
Y1200-M101102 | GA Drawing: Construction roads 3: Drawing | Labor |  |  | 1
Y1200-M101103 | Long section & cross section Drawing 3: Drawing | Labor |  |  | 1
Y1200-M101104 | Long section & cross section Drawing 3: Drawing | Labor |  |  | 1
Y1200-M101105 | Typical Road drawing 3: Drawing | Labor |  |  | 1
Y1200-M101106 | Typical Road drawing 3: Drawing | Labor |  |  | 1
Y1200-M101107 | GA Drawing: Construction Camp and Laydown areas 3: Drawing | Labor |  |  | 1
Y1200-M101108 | GA Drawing: Construction Camp and Laydown areas 3: Drawing | Labor |  |  | 1
Y1200-M101109 | Cross sections Drawing: Construction Camp and Laydown 3: Drawing | Labor |  |  | 1
Y1200-M101110 | Cross sections Drawing: Construction Camp and Laydown 3: Drawing | Labor |  |  | 1
Y1200-M101111 | Typical Detail Drawing: Construction Camp and Laydown 2: Drawing | Labor |  |  | 1
Y1200-M101112 | Perimeter fence and gate GA drawing 3: Drawing | Labor |  |  | 1
Y1200-M101113 | Perimeter fence and gate GA drawing 3: Drawing | Labor |  |  | 1
Y1200-M101114 | Perimeter Fence & Gate details Drawing 3: Drawing | Labor |  |  | 1
Y1200-M101115 | Perimeter Fence & Gate details Drawing 3: Drawing | Labor |  |  | 1
Y1200-M101116 | MCC Panel Design: MCC Drawing | Labor |  |  | 1
Y1200-M101117 | Gen Arrangements of MCC : MCC GA Drawing | Labor |  |  | 1
Y1200-M101118 | Single Line Diagrams: Single Line Diagrams | Labor |  |  | 1
Y1200-M101119 | Cable Schedules: Cable schedule List | Labor |  |  | 1
Y1200-M101120 | Earth Resistivity-Test & Report: Earth Resistivity-Test & Report | Labor |  |  | 1
Y1200-M101121 | New Earthing & Lightning and Protection Design: Earthing & Lighning design report | Labor |  |  | 1
Y1200-M101122 | Lighting Layout /Small Power Plan Layout: Earthing and Lightning report | Labor |  |  | 1
Y1200-M101123 | Lighting Layout /Small Power Sections/Elevations Layout: New Earthing and Lightning Dwgs | Labor |  |  | 1
Y1200-M101124 | Lighting Layout /Small Power : New Earthing and Lightning Dwgs | Labor |  |  | 1
Y1200-M101125 | Rail Indexer: Rail Indexer design & Supply package | Labor |  |  | 1
Y1200-M101126 | Rail Indexer Foundation: Rail Indexret Foundation dwgs | Labor |  |  | 1
Y1200-M101127 | Water Demand : Water demand statement | Labor |  |  | 1
Y1200-M101128 | Water reticulation Layout drawing 2: Drawing | Labor |  |  | 1
Y1200-M101129 | Water longsection drawing 2: Drawing | Labor |  |  | 1
Y1200-M101130 | Typical water detail drawing 3: Drawing | Labor |  |  | 1
Y1200-M101131 | Typical water detail drawing 3: Drawing | Labor |  |  | 1
Y1200-M101132 | Sewer discharge calculation: Sewer dischage statement | Labor |  |  | 1
Y1200-M101133 | Sewer reticulation Layout drawing 2: Drawing | Labor |  |  | 1
Y1200-M101134 | Sewer longsection drawing 2: Drawing | Labor |  |  | 1
Y1200-M101135 | Typical Sewer detail drawing 3: Drawing | Labor |  |  | 1
Y1200-M101136 | Typical Sewer detail drawing 3: Drawing | Labor |  |  | 1
Y1200-M101137 | Stormwater hydrology (run-off) report: Stormwater report | Labor |  |  | 1
Y1200-M101138 | Stormwater structures layout drawing 3: Drawing | Labor |  |  | 1
Y1200-M101139 | Stormwater structures layout drawing 3: Drawing | Labor |  |  | 1
Y1200-M101140 | Stormwater culvrt details 3: Drawing | Labor |  |  | 1
Y1200-M101141 | Stormwater culvrt details 3: Drawing | Labor |  |  | 1
Y1200-M101142 | Data & Comms sleeve layout drawing 3: Drawing | Labor |  |  | 1
Y1200-M101143 | Data & Comms sleeve layout drawing 3: Drawing | Labor |  |  | 1
Y1200-M101144 | Typical dats sleeve and draw box details: Drawing | Labor |  |  | 1
Y1200-M101150 | Roadworks Design, Drawings & Specifications: Drawings | Labor |  |  | 1
Y1200-M101152 | Culverts: Detail Design & Drawings: Drawing | Labor |  |  | 1
Y1200-M101153 | Culverts: Specifications: Technical note | Labor |  |  | 1
Y1200-M101157 | Specifications: Specification | Labor |  |  | 1
Y1200-M101158 | Design & Drawings: Drawing | Labor |  |  | 1
Y1200-M101165 | Intersection 1GA drawings 4: Drawing | Labor |  |  | 1
Y1200-M101166 | Intersection 1GA drawings 4: Drawing | Labor |  |  | 1
Y1200-M101167 | Long section & cross section Drawing 2: Drawing | Labor |  |  | 1
Y1200-M101169 | Construction camp layout Drawing 2: Drawing | Labor |  |  | 1
Y1200-M101170 | Water, sewer and electrical layout drawing: Drawing | Labor |  |  | 1
Y1200-M101171 | Typical Detail drawing 2: Drawing | Labor |  |  | 1
Y1200-M101172 | PFS Review: Technical Note | Labor |  |  | 1
Y1200-M101173 | PFS BOD report review: Technical Note | Labor |  |  | 1
Y1200-M101174 | PFS SOW Review: Technical Note | Labor |  |  | 1
Y1200-M101175 | Scope of Work Report: SoW Report | Labor |  |  | 1
Y1200-M101176 | Basis of Design: Basis of Design Report | Labor |  |  | 1
Y1200-M101177 | FS Engineering Management Plan: FS Eng Man Plan | Labor |  |  | 1
Y1200-M101178 | Block Plan: Block Plan | Labor |  |  | 1
Y1200-M101179 | Topopraphical survey - LiDAR: Digital Terrain Model | Labor |  |  | 1
Y1200-M101180 | Bench Mark and Site survey Dwgs: Site Survey & BM Dwg | Labor |  |  | 1
Y1200-M101181 | Geotechnical Investigations: Geotech Report | Labor |  |  | 1
Y1200-M101182 | Site Visit Report: Technical Note | Labor |  |  | 1
Y1200-M101183 | Engineering Progress Report: Progress Report | Labor |  |  | 1
Y1200-M101184 | Design meeting: Design Minutes | Labor |  |  | 1
Y1200-M101185 | Project Registers: Issues-, Design Decision register: Updated registers | Labor |  |  | 1
Y1200-M101186 | Project Registers: Issues-, Design Decision register: Updated registers | Labor |  |  | 1
Y1200-M101187 | Project Registers: Issues-, Design Decision register: Updated registers | Labor |  |  | 1
Y1200-M101188 | Project Registers: Issues-, Design Decision register: Updated registers | Labor |  |  | 1
Y1200-M101189 | Project Review: Review Report | Labor |  |  | 1
Y1200-M101190 | Calculations Report: Calculations Report | Labor |  |  | 1
Y1200-M101191 | Design Report: Design Report | Labor |  |  | 1
Y1200-M101192 | Design & Verification : Design & Verification report | Labor |  |  | 1
Y1200-M101193 | HAZOP Input: HAZOP review input | Labor |  |  | 1
Y1200-M101194 | Risk Assessments: Risk Assessment input | Labor |  |  | 1
Y1200-M101195 | Lessons Learnt Report: Lessons Learnt Report | Labor |  |  | 1
Y1200-M101196 | Safety in Design : Safety in design review report | Labor |  |  | 1
Y1200-M101197 | Constructability : Constructability Review Report | Labor |  |  | 1
Y1200-M101198 | BoQ: BoQ | Labor |  |  | 1
Y1200-M101199 | Technical Specifications : Technical Specifications | Labor |  |  | 1
Y1200-M101200 | Procurement: Procurement Report input portion | Labor |  |  | 1
Y1200-M101201 | FS Report (Engineering portion): FS Report Eng Portion | Labor |  |  | 1
Y1200-M101202 | Execution Engineering Management Plan: Execution Eng Man Plan | Labor |  |  | 1
Y1200-M101203 | Model - Survey - Existing Ground Surface | Labor |  |  | 1
Y1200-M101204 | Model - Survey - Point Cloud | Labor |  |  | 1
Y1200-M101205 | Model - Survey - Structures | Labor |  |  | 1
Y1200-M101206 | Model - Rail - Corridor, VA, HA | Labor |  |  | 1
Y1200-M101207 | Model - Rail - Track Overhead Equipment | Labor |  |  | 1
Y1200-M101208 | Model - Rail - Track Signalling | Labor |  |  | 1
Y1200-M101209 | Model - Rail - Indexer | Labor |  |  | 1
Y1200-M101210 | Model - Rail - Level Crossing | Labor |  |  | 1
Y1200-M101211 | Model - Utilities - Electrical | Labor |  |  | 1
Y1200-M101212 | Model - Utilities - Data | Labor |  |  | 1
Y1200-M101213 | Model - Utilities - Potable Water | Labor |  |  | 1
Y1200-M101214 | Model - Utilities - Sewer | Labor |  |  | 1
Y1200-M101215 | Model - Drainage - Culverts | Labor |  |  | 1
Y1200-M101216 | Model - Drainage - Network | Labor |  |  | 1
Y1200-M101217 | Model - Roads - Intersection 1 | Labor |  |  | 1
Y1200-M101218 | Model - Roads - Construction | Labor |  |  | 1
Y1200-M101219 | Model - Perimeter Fence and Gates | Labor |  |  | 1
Y1200-M101220 | Model - Federated | Labor |  |  | 1
Y1200-M101221 | Model - Test Model | Labor |  |  | 1
Y1200-M100101 | Setup (Initial Actions to Finalise) | Labor |  |  | 1
Y1200-M100102 | PEP | Labor |  |  | 1
Y1200-M100103 | WBS | Labor |  |  | 1
Y1200-M100104 | PCP | Labor |  |  | 1
Y1200-M100105 | Eng M Pln | Labor |  |  | 1
Y1200-M100106 | BIM plan | Labor |  |  | 1
Y1200-M100107 | BIM setup | Labor |  |  | 1
Y1200-M100108 | Initial meeting | Labor |  |  | 1
Y1200-M100109 | Kick off meeting | Labor |  |  | 1
Y1200-M100110 | Schedule | Labor |  |  | 1
Y1200-M100111 | Risk Register | Labor |  |  | 1
Y1200-M100112 | Site Visit 1 | Labor |  |  | 1
Y1200-M100113 | Site Visit 2 | Labor |  |  | 1
Y1200-M100114 | Monthly Report - May | Labor |  |  | 1
Y1200-M100115 | Monthly Report - Jun | Labor |  |  | 1
Y1200-M100116 | Monthly Report - Jul | Labor |  |  | 1
Y1200-M100117 | Monthly Report - Aug | Labor |  |  | 1
Y1200-M100118 | Monthly Report - Sep | Labor |  |  | 1
Y1200-M100119 | Monthly Report - Oct | Labor |  |  | 1
Y1200-M100120 | Monthly Report - Nov | Labor |  |  | 1
Y1200-M100121 | BIM Maintenance - May | Labor |  |  | 1
Y1200-M100122 | BIM Maintenance - Jun | Labor |  |  | 1
Y1200-M100123 | BIM Maintenance - Jul | Labor |  |  | 1
Y1200-M100124 | BIM Maintenance - Aug | Labor |  |  | 1
Y1200-M100125 | BIM Maintenance - Sep | Labor |  |  | 1
Y1200-M100126 | BIM Maintenance - Oct | Labor |  |  | 1
Y1200-M100127 | BIM Maintenance - Nov | Labor |  |  | 1
Y1200-M100128 | Monthly Invoice - May | Labor |  |  | 1
Y1200-M100129 | Monthly Invoice - Jun | Labor |  |  | 1
Y1200-M100130 | Monthly Invoice - Jul | Labor |  |  | 1
Y1200-M100131 | Monthly Invoice - Aug | Labor |  |  | 1
Y1200-M100132 | Monthly Invoice - Sep | Labor |  |  | 1
Y1200-M100133 | Monthly Invoice - Oct | Labor |  |  | 1
Y1200-M100134 | Monthly Invoice - Nov | Labor |  |  | 1
Y1200-M100135 | Weekly progress - Jun - 1 | Labor |  |  | 1
Y1200-M100136 | Weekly progress - Jun - 2 | Labor |  |  | 1
Y1200-M100137 | Weekly progress - Jun - 3 | Labor |  |  | 1
Y1200-M100138 | Weekly progress - Jul - 1 | Labor |  |  | 1
Y1200-M100139 | Weekly progress - Jul - 2 | Labor |  |  | 1
Y1200-M100140 | Weekly progress - Jul - 3 | Labor |  |  | 1
Y1200-M100141 | Weekly progress - Jul - 4 | Labor |  |  | 1
Y1200-M100142 | Weekly progress - Aug - 1 | Labor |  |  | 1
Y1200-M100143 | Weekly progress - Aug - 2 | Labor |  |  | 1
Y1200-M100144 | Weekly progress - Aug - 3 | Labor |  |  | 1
Y1200-M100145 | Weekly progress - Sep - 1 | Labor |  |  | 1
Y1200-M100146 | Weekly progress - Sep - 2 | Labor |  |  | 1
Y1200-M100147 | Weekly progress - Sep - 3 | Labor |  |  | 1
Y1200-M100148 | Weekly progress - Oct - 1 | Labor |  |  | 1
Y1200-M100149 | Weekly progress - Oct - 2 | Labor |  |  | 1
Y1200-M100150 | Weekly progress - Oct - 3 | Labor |  |  | 1
Y1200-M100151 | Weekly progress - Oct - 4 | Labor |  |  | 1
Y1200-M100152 | Weekly progress - Nov - 1 | Labor |  |  | 1
Y1200-M100153 | Weekly progress - Nov - 2 | Labor |  |  | 1
Y1200-M100154 | Weekly progress - Nov - 3 | Labor |  |  | 1
Y1200-M100155 | Minutes Weekly Technical - Jun - 1 | Labor |  |  | 1
Y1200-M100156 | Minutes Weekly Technical - Jun - 2 | Labor |  |  | 1
Y1200-M100157 | Minutes Weekly Technical - Jun - 3 | Labor |  |  | 1
Y1200-M100158 | Minutes Weekly Technical - Jul - 1 | Labor |  |  | 1
Y1200-M100159 | Minutes Weekly Technical - Jul - 2 | Labor |  |  | 1
Y1200-M100160 | Minutes Weekly Technical - Jul - 3 | Labor |  |  | 1
Y1200-M100161 | Minutes Weekly Technical - Jul - 4 | Labor |  |  | 1
Y1200-M100162 | Minutes Weekly Technical - Aug - 1 | Labor |  |  | 1
Y1200-M100163 | Minutes Weekly Technical - Aug - 2 | Labor |  |  | 1
Y1200-M100164 | Minutes Weekly Technical - Aug - 3 | Labor |  |  | 1
Y1200-M100165 | Minutes Weekly Technical - Sep - 1 | Labor |  |  | 1
Y1200-M100166 | Minutes Weekly Technical - Sep - 2 | Labor |  |  | 1
Y1200-M100167 | Minutes Weekly Technical - Sep - 3 | Labor |  |  | 1
Y1200-M100168 | Minutes Weekly Technical - Oct - 1 | Labor |  |  | 1
Y1200-M100169 | Minutes Weekly Technical - Oct - 2 | Labor |  |  | 1
Y1200-M100170 | Minutes Weekly Technical - Oct - 3 | Labor |  |  | 1
Y1200-M100171 | Minutes Weekly Technical - Oct - 4 | Labor |  |  | 1
Y1200-M100172 | Minutes Weekly Technical - Nov - 1 | Labor |  |  | 1
Y1200-M100173 | Minutes Weekly Technical - Nov - 2 | Labor |  |  | 1
Y1200-M100174 | Minutes Weekly Technical - Nov - 3 | Labor |  |  | 1
Y1200-M100175 | Meetings Monthly Commercial - Jun | Labor |  |  | 1
Y1200-M100176 | Meetings Monthly Commercial - Jul | Labor |  |  | 1
Y1200-M100177 | Meetings Monthly Commercial - Aug | Labor |  |  | 1
Y1200-M100178 | Meetings Monthly Commercial - Sep | Labor |  |  | 1
Y1200-M100179 | Meetings Monthly Commercial - Oct | Labor |  |  | 1
Y1200-M100180 | Meetings Monthly Commercial - Nov | Labor |  |  | 1
Y1200-M100181 | Minutes monthly progress - May | Labor |  |  | 1
Y1200-M100182 | Minutes monthly progress - Jun | Labor |  |  | 1
Y1200-M100183 | Minutes monthly progress - Jul | Labor |  |  | 1
Y1200-M100184 | Minutes monthly progress - Aug | Labor |  |  | 1
Y1200-M100185 | Minutes monthly progress - Sep | Labor |  |  | 1
Y1200-M100186 | Minutes monthly progress - Oct | Labor |  |  | 1
Y1200-M100187 | Minutes monthly progress - Nov | Labor |  |  | 1
Y1200-M100188 | Weekly tracking schedule - Jun - 1 | Labor |  |  | 1
Y1200-M100189 | Weekly tracking schedule - Jun - 2 | Labor |  |  | 1
Y1200-M100190 | Weekly tracking schedule - Jun - 3 | Labor |  |  | 1
Y1200-M100191 | Weekly tracking schedule - Jun - 4 | Labor |  |  | 1
Y1200-M100192 | Weekly tracking schedule - Jul - 1 | Labor |  |  | 1
Y1200-M100193 | Weekly tracking schedule - Jul - 2 | Labor |  |  | 1
Y1200-M100194 | Weekly tracking schedule - Jul - 3 | Labor |  |  | 1
Y1200-M100195 | Weekly tracking schedule - Jul - 4 | Labor |  |  | 1
Y1200-M100196 | Weekly tracking schedule - Aug - 1 | Labor |  |  | 1
Y1200-M100197 | Weekly tracking schedule - Aug - 2 | Labor |  |  | 1
Y1200-M100198 | Weekly tracking schedule - Aug - 3 | Labor |  |  | 1
Y1200-M100199 | Weekly tracking schedule - Aug - 4 | Labor |  |  | 1
Y1200-M100200 | Weekly tracking schedule - Sep - 1 | Labor |  |  | 1
Y1200-M100201 | Weekly tracking schedule - Sep - 2 | Labor |  |  | 1
Y1200-M100202 | Weekly tracking schedule - Sep - 3 | Labor |  |  | 1
Y1200-M100203 | Weekly tracking schedule - Sep - 4 | Labor |  |  | 1
Y1200-M100204 | Weekly tracking schedule - Oct - 1 | Labor |  |  | 1
Y1200-M100205 | Weekly tracking schedule - Oct - 2 | Labor |  |  | 1
Y1200-M100206 | Weekly tracking schedule - Oct - 3 | Labor |  |  | 1
Y1200-M100207 | Weekly tracking schedule - Oct - 4 | Labor |  |  | 1
Y1200-M100208 | Weekly tracking schedule - Nov - 1 | Labor |  |  | 1
Y1200-M100209 | Weekly tracking schedule - Nov - 2 | Labor |  |  | 1
Y1200-M100210 | Weekly tracking schedule - Nov - 3 | Labor |  |  | 1
Y1200-M100211 | Weekly tracking schedule - Nov - 4 | Labor |  |  | 1
Y1200-M100212 | Site Visit 3 | Labor |  |  | 1
Y1200-M100213 | Site Visit 4 | Labor |  |  | 1
Y1200-M100214 | Site Visit 5 | Labor |  |  | 1
Y1200-M100215 | Procurement Strategy | Labor |  |  | 1
Y1200-M100216 | Preparation for Gate Review | Labor |  |  | 1
Y1200-M100217 | PEP Construction | Labor |  |  | 1
Y1200-M100218 | PCP Construction | Labor |  |  | 1
Y1200-M100219 | PEmP Construction | Labor |  |  | 1
Y1200-M100220 | CMP | Labor |  |  | 1
Y1200-M100221 | Safety MP | Labor |  |  | 1
Y1200-M100222 | Risk MP | Labor |  |  | 1
Y1200-M100223 | Quality MP | Labor |  |  | 1
Y1200-M100224 | Comms Plan | Labor |  |  | 1
Y1200-M100225 | Site BIM Plan | Labor |  |  | 1
Y1200-M100226 | Schedule | Labor |  |  | 1
Y1200-M100227 | Project Registers: Procurement Register | Labor |  |  | 1
Y1200-M100228 | Project Registers: Decision Register | Labor |  |  | 1
Y1200-M100229 | Project Registers: Issue Register | Labor |  |  | 1
Y1200-M100230 | Project Registers: Stakeholder Register | Labor |  |  | 1
Y1200-M100231 | Project Registers: Risk Register | Labor |  |  | 1
Y1200-M100232 | Project Registers: Local Enterprise Register | Labor |  |  | 1
Y1200-M100233 | Project Registers: Package Register | Labor |  |  | 1
Y1200-M101149 | Earthworks Design, Drawings & Specifications: Drawings | Labor |  |  | 1
Y1200-M101148 | Specifications: Technical note | Labor |  |  | 1
Y1200-M102106 | Typical Road drawing 3: Drawing | Labor |  |  | 1
Y1200-M102105 | Typical Road drawing 3: Drawing | Labor |  |  | 1
Y1200-M102104 | Long section & cross section Drawing 3: Drawing | Labor |  |  | 1
Y1200-M102103 | Long section & cross section Drawing 3: Drawing | Labor |  |  | 1
Y1200-M102102 | GA Drawing: Construction roads 3: Drawing | Labor |  |  | 1
Y1200-M102101 | GA Drawing: Construction roads 3: Drawing | Labor |  |  | 1
Y1200-M101229 | Mamatwan Mine - Rail Plan and Longitudinal Section ( 3000 - 4000) | Labor |  |  | 1
Y1200-M101230 | Mamatwan Mine - Rail Plan and Longitudinal Section ( 4000 - 5000) | Labor |  |  | 1
Y1200-M101231 | Mamatwan Mine - Rail Plan and Longitudinal Section ( 5000 - 6000) | Labor |  |  | 1
Y1200-M101232 | Mamatwan Mine - Rail Plan and Longitudinal Section ( 6000 - 6300) | Labor |  |  | 1
Y1200-M101233 | Mamatwan Mine - Rail Line Plan and Longitudinal Section ( 0 - 600) | Labor |  |  | 1
Y1200-M101234 | Mamatwan Mine -Rail Diagrammatic Layout (Rail Type Usage) | Labor |  |  | 1
Y1200-M101235 | Mamatwan Mine - Proposed Balloon Typical Details (Rail Track Signage Details) | Labor |  |  | 1
Y1200-M101236 | Mamatwan Mine - Level Crossings | Labor |  |  | 1
Y1200-M101223 | MMT Construction Roads Layout and Profile Sheet 4 of 4 | Labor |  |  | 1
Y1200-M101224 | Mamatwan Mine - Rail Site plan | Labor |  |  | 1
Y1200-M101225 | Mamatwan Mine - Rail General Arangement | Labor |  |  | 1
Y1200-M101226 | Mamatwan Mine - Rail Plan and Longitudinal Section ( 0 - 1000) | Labor |  |  | 1
Y1200-M101227 | Mamatwan Mine - Rail Plan and Longitudinal Section ( 1000 - 2000) | Labor |  |  | 1
Y1200-M101228 | Mamatwan Mine - Rail Plan and Longitudinal Section ( 2000 - 3000) | Labor |  |  | 1
Y1200-M102227 | WSL Geotech Test Locations Layout Plan | Labor |  |  | 1
Y1200-M102236 | Wessels Mine - Rail Plan and Longitudinal Section ( 2000 - 3000) | Labor |  |  | 1
Y1200-M102237 | Wessels Mine - Rail Plan and Longitudinal Section ( 3000 - 4000) | Labor |  |  | 1
Y1200-M102238 | Wessels Mine - Rail Plan and Longitudinal Section ( 4000 - 4595) | Labor |  |  | 1
Y1200-M102239 | Wessels Mine - Rail Site plan | Labor |  |  | 1
Y1200-M102240 | Wessels Mine - Rail Typical Details (Rail Track Signage Details) | Labor |  |  | 1
Y1200-M102230 | Wessels Mine - Rail (Link Line) Plan and Longitudinal Section ( 0 - 682) | Labor |  |  | 1
Y1200-M102231 | Wessels Mine - Rail Diagrammatic Layout (Rail Type Usage) | Labor |  |  | 1
Y1200-M102232 | Wessels Mine - Rail General Arangement | Labor |  |  | 1
Y1200-M102233 | Wessels Mine - Rail Level Crossings | Labor |  |  | 1
Y1200-M102234 | Wessels Mine - Rail Plan and Longitudinal Section ( 0 - 1000) | Labor |  |  | 1
Y1200-M102235 | Wessels Mine - Rail Plan and Longitudinal Section ( 1000 - 2000) | Labor |  |  | 1
Y1200-M101300 | Design Name Change | Labor |  |  | 1
RAPTOR | Commodity Code Name | Material |  |  | 8
Y60 | Y60 - Temporary facilities | Material |  |  | 8
Y30 | Y30 - Construction Expenses/ Overheads/ Fees | Nonlabor |  |  | 1
Y20 | Y20 - Construction Management & Support (Site) | Labor |  |  | 1
B05 | B05 - Storm Drainage - Lining and Structures | Material |  |  | 8
A04 | A04 - Bulk Earthworks | Material |  |  | 8
N04 | N04 - Crushing & Screening | Material |  |  | 8
R01 | R01 - Trackwork | Material |  |  | 8
A08 | A08 - Site Improvements | Material |  |  | 8
C03 | C03 - Precast Concrete | Material |  |  | 8
A01 | A01 - Site Investigation | Material |  |  | 8
A06 | A06 - Trenching | Material |  |  | 8
P01 | P01 - Field Run | Material |  |  | 8
P07 | P07 - Valves | Material |  |  | 8
M01 | M01 - Mechanical Bulks - Metallic | Material |  |  | 8
N03 | N03 - Pumps | Material |  |  | 8
U02 | U02 - Conduit | Material |  |  | 8
X03 | X03 - Signalling | Material |  |  | 8
T01 | T01 - Electrical Equipment | Material |  |  | 8
W03 | W03 - Other Cables | Material |  |  | 8
W02 | W02 - Control and Data Cables | Material |  |  | 8
X02 | X02 - Control Devices | Material |  |  | 8
T02 | T02 - Electrical Fittings | Material |  |  | 8
C02 | C02 - Reinforced In-Situ Concrete | Material |  |  | 8
E03 | E03 - Structure | Material |  |  | 8
Y10 | Y10 - Home Office / Engineering/ EPCM Services | Labor |  |  | 1
Z03 | Z03 - Provision | Material |  |  | 8
Z01 | Z01 - Escalation | Material |  |  | 8
Z02 | Z02 - Contingency | Material |  |  | 8
B06 | B06 - Roads | Material |  |  | 8
A03 | A03 - Site Preparation | Material |  |  | 8
B07 | B07 - Security | Material |  |  | 8
BRDA-Budget | BRDA PFS Budget Cost 2022 | Material | Australian Dollars |  | 1
CTG-Budget-1 | CTG FS Budget Hours 2022 | Labor |  |  | 0
EASTL-03 | ELS Execution | Labor |  |  | 1
ELS | ELS - Measured Commodities | Material |  |  | 8
R-1 | Logistics Team | Labor |  |  | 1
R-2 | Civils Team | Labor |  |  | 1
R-5 | EC&I Team | Labor |  |  | 1
R-6 | Mechanical Team | Labor |  |  | 1
R-7 | Piping Team | Labor |  |  | 1
R-10 | Mining Team | Labor |  |  | 1
S8DB | S8DB | Labor |  |  | 64
S8D-GC03 | Construction (Hours) | Labor |  |  | 80
G-2070 | Project Estimating | Labor |  | A | 1
G-2082 | Scheduling / Planning | Labor |  | A | 1
G-2081 | Cost Engineering | Labor |  | A | 1
G-3072 | Structural Design | Labor |  | A | 1
G-3052 | Instrumentation Design | Labor |  | A | 1
BM | Bill Milne | Labor |  |  | 1
PF | Peter Fortington | Labor |  |  | 1
EO | Eddie O'Brien | Labor |  |  | 1
DR | Drawing Resource | Labor |  |  | 1
S8D-IPCS-L4 | IPCS- L4 | Labor |  |  | 64
G-2080 | Project Controls | Labor |  | A | 1
JQEL-60-80TEX | Excavator 60T-80T | Nonlabor |  |  | 1
JQEL-LDR | Loader | Nonlabor |  |  | 1
ARCH | Arch Contractor | Labor |  |  | 1
TTT-COMMI | Commissioning | Labor |  |  | 1
TTT-OPR Lead | OPR Lead | Labor |  |  | 1
TTT-CIV/STR Cr | Civil/Structural Crew | Labor |  |  | 1
TTT-CIV/STR Sup | Civil/Structural Supervisor | Labor |  |  | 1
TTT-COMM Lead | Commissioning Lead | Labor |  |  | 1
TTT-ELEC Crew | Electrical Crew | Labor |  |  | 1
TTT-ELEC Sup | Electrical Supervisor | Labor |  |  | 1
TTT-MECH Crew | Mechanical Crew | Labor |  |  | 1
TTT-MECH Sup | Mechanical Supervisor | Labor |  |  | 1
TTT-ThirdPVen | Third Party Vendor | Labor |  |  | 1
JQEL - LABOUR | J Quarry & Eastern Leases Fleet Resources | Labor |  |  | 1
G-1110 | General Management Services | Labor |  | A | 1
G-2982 | Document Control | Labor |  | A | 1
G-3061 | Civil Engineering | Labor |  | A | 1
G-3062 | Civil Design | Labor |  | A | 1
G-3032 | Piping Design | Labor |  | A | 1
G-3031 | Piping Engineering | Labor |  | A | 1
G-3021 | Mechanical Engineering | Labor |  | A | 1
G-3022 | Mechanical Design | Labor |  | A | 1
G-3012 | Process Design | Labor |  | A | 1
G-3011 | Process Engineering | Labor |  | A | 1
NLU | Nullaga Labour Unit | Labor |  |  | 1
Commodity code | Commodity Name | Nonlabor |  |  | 1
R02 | R02 - Track components | Material |  |  | 8
A10 | A10 - Dayworks | Nonlabor |  |  | 1
Y10-7 | Y10 - Home Office / Engineering/ EPCM Services 07 | Nonlabor |  |  | 1
Y10-6 | Y10 - Home Office / Engineering/ EPCM Services 06 | Nonlabor |  |  | 1
Y10-5 | Y10 - Home Office / Engineering/ EPCM Services 05 | Nonlabor |  |  | 1
Y10-4 | Y10 - Home Office / Engineering/ EPCM Services 04 | Nonlabor |  |  | 1
Y10-3 | Y10 - Home Office / Engineering/ EPCM Services 03 | Nonlabor |  |  | 1
Y10-2 | Y10 - Home Office / Engineering/ EPCM Services 02 | Nonlabor |  |  | 1
Y10-1 | Y10 - Home Office / Engineering/ EPCM Services 01 | Nonlabor |  |  | 1
Z03-3 | Z03 - Provision 03 | Nonlabor |  |  | 1
Z03-2 | Z03 - Provision 02 | Nonlabor |  |  | 1
Z03-1 | Z03 - Provision 01 | Nonlabor |  |  | 1
Y30-3 | Y30 - Construction Expenses/ Overheads/ Fees 03 | Nonlabor |  |  | 1
Y30-2 | Y30 - Construction Expenses/ Overheads/ Fees 02 | Nonlabor |  |  | 1
Y30-1 | Y30 - Construction Expenses/ Overheads/ Fees 01 | Nonlabor |  |  | 1
Y60-2 | Y60 - Temporary facilities 02 | Nonlabor |  |  | 1
Y60-1 | Y60 - Temporary facilities 01 | Nonlabor |  |  | 1
19204-CDES | Civil Designer | Labor |  |  | 1
19204-STDES | Structural Designer | Labor |  |  | 1
19204-ARCHDES | Architect Designer | Labor |  |  | 1
19204-GENDES | General Designer | Labor |  |  | 1
19204-MDES | Mechanical Designer | Labor |  |  | 1
19204-ELDES | Electrical Designer | Labor |  |  | 1
19204-CODES | Controls Designer | Labor |  |  | 1
Histo | EWP HRS | Labor |  |  | 1
Cost | EWP Cost | Labor |  |  | 1
CANNINGTON | CANNINGTON TSFE5 & WSP | Labor |  |  | 1
Hully Indirects | Hully Indirects | Labor |  |  | 1
Q_DESCV | Designer Civil | Labor |  |  | 1
Q_CS | Contract Specialist | Labor |  |  | 1
Q_ENGGEO | Engineer Geotechnical | Labor |  |  | 1
Z01-1 | Z01 - Escalation-01 | Nonlabor |  |  | 1
Z01-2 | Z01 - Escalation-02 | Nonlabor |  |  | 1
A0301 | A0301-Clearing & grubbing | Material | Square Metres |  | 8
A0303 | A0303-Strip Topsoil | Material | Cubic Metres |  | 8
A0405 | A0405-Cut, Fill & Compaction | Material | Cubic Metres |  | 8
A0406 | A0406-Borrow, Fill & Compaction - Base Course/General Fill | Material | Cubic Metres |  | 8
A0407 | A0407-Disposal of materials on site (Cut to spoil) | Material | Cubic Metres |  | 8
A0501 | A0501-Detailed Excavation | Material | Cubic Metres |  | 8
A0504 | A0504-Trim, grade and compact (no fill) | Material | Square Metres |  | 8
B0602 | B0602-Gravel Roads (including subgrade prep) | Material | Square Metres |  | 8
B0602W | B0602W-Wearing course | Material | Cubic Metres |  | 8
B0605-m | B0605-Barriers installed | Material | Lineal Metres |  | 8
B0106 | B0106 Bored Concrete Piles | Material | Each |  | 8
Sheet Piles EA | B0103 Driven Sheet Piles | Material | Each |  | 8
B0605-m3 | B0605 Barriers M3 cleared | Material | Cubic Metres |  | 8
A0502 | A0502-Detailed Fill/Compaction | Material | Cubic Metres |  | 8
B0302 | B0302 - CSP Culvert M3 | Material | Cubic Metres |  | 8
Sheet Piles m3 | B0103 Sheet Piles M3 | Material | Cubic Metres |  | 8
ELCF | Eastern Lease South - Package Budget | Nonlabor |  |  | 1
Other Q | Other Quantites | Material |  |  | 8
B0605 | B0605 Barriers M3 cleared | Material | Cubic Metres |  | 8
P0133 | P0133 Piping | Material | Lineal Metres |  | 8
C0207 | C0207 Walls | Material | Cubic Metres |  | 8
P0601 | P0601 Hydro testing | Material | Lineal Metres |  | 8
A0705 | A0705 - Earth Stablisation | Material | Cubic Metres |  | 8
C0300 | C0300 Precast Concrete | Material | Each |  | 8
12577507 | 12577507 - IMC VAMMIT PFS | Labor |  |  | 1
IMC001 | Project Director | Labor |  | MGS | 1
IMC002 | Project Manager | Labor |  | MGS | 1
IMC003 | Project Engineer | Labor |  | MGS | 1
IMC004 | Engineering Manager | Labor |  | MGS | 1
IMC005 | Risk / HAZOP lead | Labor |  | MGS | 1
IMC006 | Challenge Team / Peer reviewer | Labor |  | MGS | 1
IMC007 | Challenge Team / Peer Reviewer | Labor |  | MGS | 1
IMC008 | Operational Readiness Lead | Labor |  | MGS | 1
IMC009 | Mining Specialist | Labor |  | MGS | 1
IMC010 | Senior Estimator | Labor |  | MGS | 1
IMC011 | Senior Scheduler | Labor |  | MGS | 1
IMC012 | Technical Reviewer (Mech) | Labor |  | MEC | 1
IMC013 | Senior Engineer (Mech) | Labor |  | MEC | 1
IMC014 | Junior Engineer (Mech) | Labor |  | MEC | 1
IMC015 | Senior Engineer (Structural) | Labor |  | STR | 1
IMC016 | Engineer (Structural) | Labor |  | STR | 1
IMC017 | Senior Engineer (Civil) | Labor |  | CIV | 1
IMC018 | Engineer (Civil) | Labor |  | CIV | 1
IMC019 | Technical Reviewer (Geotechnical) | Labor |  | GEO | 1
IMC020 | Senior Engineer (Geotechnical) | Labor |  | GEO | 1
IMC021 | Engineer (Geotechnical) | Labor |  | GEO | 1
IMC023 | Senior Engineer (Electrical) | Labor |  | ELE | 1
IMC024 | Engineer (Electrical) | Labor |  | ELE | 1
IMC025 | Project Lead Drafter | Labor |  | DFT | 1
IMC026 | Mechanical Designer | Labor |  | DFT | 1
IMC027 | Electrical Drafter | Labor |  | DFT | 1
IMC028 | Structural Designer | Labor |  | DFT | 1
IMC100 | Labor Cost | Nonlabor |  |  | 1
IMC022 | Engineer (Geotechnical) | Labor |  | GEO | 1
Senior Estimator | Senior Estimator | Labor |  |  | 1
MSP FIXED COST | MSP Fixed Cost | Material |  |  | 10
PROJECT MANAGER | Project Manager | Labor |  |  | 1
SENIOR PROJECT ENGINEER | Senior Project Engineer | Labor |  |  | 1
Senior Planner | Senior Planner | Labor |  |  | 1
SMAD | SMAD | Labor |  |  | 1
PROJECT MANAGER COST/USE | PROJECT MANAGER COST/USE | Material |  |  | 8
PROJECT SPONSOR | Project Sponsor | Labor |  |  | 1
COST ENGINEER COST/USE | COST ENGINEER COST/USE | Material |  |  | 8
SENIOR ESTIMATOR COST/USE | SENIOR ESTIMATOR COST/USE | Material |  |  | 8
SENIOR DOCUMENT CONTROLLER COST/USE | SENIOR DOCUMENT CONTROLLER COST/USE | Material |  |  | 8
SENIOR PROCESS ENGINEER | Senior Process Engineer | Labor |  |  | 1
SENIOR PROCESS ENGINEER COST/USE | SENIOR PROCESS ENGINEER COST/USE | Material |  |  | 8
PRINCIPLE CIVIL ENGINEER COST/USE | PRINCIPLE CIVIL ENGINEER COST/USE | Material |  |  | 8
PRINCIPLE ELECTRICAL ENGINEER COST/USE | PRINCIPLE ELECTRICAL ENGINEER COST/USE | Material |  |  | 8
PRINCIPLE PROCESS ENGINEER | Principle Process Engineer | Labor |  |  | 1
PRINCIPLE MECHANICAL ENGINEER | Principle Mechanical Engineer | Labor |  |  | 1
SPECIALIST MINING ENGINEER | Specialist Mining Engineer | Labor |  |  | 1
SPECIALIST MINING ENGINEER COST/USE | SPECIALIST MINING ENGINEER COST/USE | Material |  |  | 8
SENIOR PE - AUXILIARY INFRASTRUCTURE COST/USE | SENIOR PE - AUXILIARY INFRASTRUCTURE COST/USE | Material |  |  | 8
LEAD COMMUNICATIONS ENGINEER COST/USE | LEAD COMMUNICATIONS ENGINEER COST/USE | Material |  |  | 8
ELECTRICAL ENGINEER COST/USE | ELECTRICAL ENGINEER COST/USE | Material |  |  | 8
PRINCIPLE RISK ENGINEER | Principle Risk Engineer | Labor |  |  | 1
PRINCIPLE RISK ENGINEER COST/USE | PRINCIPLE RISK ENGINEER COST/USE | Material |  |  | 8
SENIOR GENERAL DESIGNER COST/USE | SENIOR GENERAL DESIGNER COST/USE | Material |  |  | 8
SENIOR ELECTRICAL DESIGNER COST/USE | SENIOR ELECTRICAL DESIGNER COST/USE | Material |  |  | 8
RPM SENIOR MINING ENG | RPM Senior Mining Eng | Labor |  |  | 1
RPM SOFTWARE LICENCE | RPM Software Licence | Labor |  |  | 1
SENIOR GEOTECHNICAL ENGINEER | Senior Geotechnical Engineer | Labor |  |  | 1
500/MONTH) | 500/month) | Labor |  |  | 1
19204-MPM | Project Manager | Labor |  |  | 1
19204-PCE | Principal Civil Engineer | Labor |  |  | 1
19204-PEE | Principal Electrical Engineer | Labor |  |  | 1
19204-LEE | Lead Electrical Engineer | Labor |  |  | 1
19204-LCOME | Lead Communications Engineer | Labor |  |  | 1
19204-SGEO | Senior Geology Engineer | Labor |  |  | 1
19204-LMDES | Lead Mechanical Designer | Labor |  |  | 1
19204-SELDES | Senior Electrical Designer | Labor |  |  | 1
19204-SCE | Senior Civil Engineer | Labor |  |  | 1
MP-1 | Mining Plus Resources | Labor |  |  | 1
19204-MGRPC | Project Controls Manager | Labor |  |  | 1
19204-PROC | Contracts and Procurement Officer | Labor |  |  | 1
19204-LCM | Lead Construction Manager | Labor |  |  | 1
19204-LSTE | Lead Structural Engineer | Labor |  |  | 1
RPMC1 | RPM Principal Mining Engineer (Consultant) | Labor |  |  | 1
RPMC2 | RPM Senior Mining Engineer (Consultant) | Labor |  |  | 1
19204-CER | Communications Engineer | Labor |  |  | 1
Accommodation and meals | Accommodation and meals | Nonlabor |  |  | 1
A0701 | A0701 Geotextile Liners | Material | Square Metres |  | 8
P0000 | P0000 Piping | Material | Lineal Metres |  | 8
C0000 | C0000 Concretre | Material | Cubic Metres |  | 8
B0608 | B0608 Road Signs | Material | Each |  | 8
Hully-1 | Hully Indirects | Labor |  |  | 1
ConP | Concrete Pump | Nonlabor |  |  | 1
Excav | Excavator | Nonlabor |  |  | 1
Plant-01 | Prime Mover | Nonlabor |  |  | 1
Plant-07 | Compressor | Nonlabor |  |  | 1
Plant-08 | Pile Breakback | Nonlabor |  |  | 1
Plant-10 | CFA Rig | Nonlabor |  |  | 1
Plant-11 | Tracked Concrete Pump | Nonlabor |  |  | 1
Plant-12 | Sheet Plant | Nonlabor |  |  | 1
Plant-13 | 320t Crawler | Nonlabor |  |  | 1
Plant-14 | 160t Crane | Nonlabor |  |  | 1
Plant-15 | 110t Crane | Nonlabor |  |  | 1
Plant-16 | 25t Franna | Nonlabor |  |  | 1
Plant-17 | Boom Pump | Nonlabor |  |  | 1
TTT-EQUIPOP | Equipment Operator | Labor |  |  | 1
GEN-SC | General - Sub-Contractors | Labor |  |  | 1
TTT-EQUIP | Equipment | Nonlabor |  |  | 0
TTT-LV | Light Vehicle | Nonlabor |  |  | 0
TTT-IT | Integrated Tool Carrier | Nonlabor |  |  | 0
TTT-FLIFT | Forklift | Nonlabor |  |  | 0
TTT-TRUCK | Truck | Nonlabor |  |  | 0
TTT-EXCAV | Excavator | Nonlabor |  |  | 0
TTT-SKIDST | Skid Steer | Nonlabor |  |  | 0
TTT-FRA | Franna | Nonlabor |  |  | 0
TTT-CR | Crane | Nonlabor |  |  | 0
TTT-EWP | EWP | Nonlabor |  |  | 0
TTT-HYDRO | Hydrovac | Nonlabor |  |  | 0
TTT-HydroOP | Hydrovac Operator | Labor |  |  | 1
TTT-DEMOSAW | Demolition Saw | Nonlabor |  |  | 0
TTT-NQCR | NQ Cranes | Labor |  |  | 1
TTT-MOFFICE | Maintenance Office Contractor | Labor |  |  | 1
TTT-LVUG | Light Vehicle - UG | Nonlabor |  |  | 0
TTT-TruckCEZAOP | CEZA Truck Driver | Labor |  |  | 1
TTT-TRUCKCEZA | CEZA Truck | Nonlabor |  |  | 0
TTT-FRAUG | UG Franna | Nonlabor |  |  | 0
TTT-WEL-POLY | Welder - Poly Pipe | Labor |  |  | 1
TTT-WELD | Welding Machine | Nonlabor |  |  | 0
TTT-Schneider | Schneider | Labor |  |  | 1
TTT-GRATOR | Grator | Nonlabor |  |  | 0
TTT-AUGER | Auger | Nonlabor |  |  | 0
HMD_COST | Cost | Nonlabor |  |  | 1
19204-LCDES | Lead Civil Designer | Labor |  |  | 1
19204-LEST | Lead Estimator | Labor |  |  | 1
19204-SCTRE | Senior Contracts Engineer | Labor |  |  | 1
19204-MENG | Engineering Manager | Labor |  |  | 1
19204-LGEO | Lead Geology Engineer | Labor |  |  | 1
19204-LCE | Lead Civil Engineer | Labor |  |  | 1
19204-BRENG | Bridge Specialist | Labor |  |  | 1
19204-SMEE | Senior Mechanical Engineer | Labor |  |  | 1
19204-LMEE | Lead Mechanical Engineer | Labor |  |  | 1
19204-SCOME | Senior Communications Engineer | Labor |  |  | 1
19204-MRDES | Design Manager | Labor |  |  | 1
19204-LCODES | Lead Controls Designer | Labor |  |  | 1
19204-SCODES | Senior Controls Designer | Labor |  |  | 1
R | Hully Girders | Labor |  |  | 1
IMC029 | RTO Specialist | Labor |  | RTO | 1
IMC030 | Senior Engineer (Proc) | Labor |  | PRO | 1
IMC031 | Junior Engineer (Proc) | Labor |  | PRO | 1
Mud-Hours | FS Budget Hours | Labor |  |  | 1
3012 | Process Design | Labor |  |  | 1
TTT-SMPSUPER | Supervisor SMP | Labor |  |  | 1
TTT-PERM | Permit Issuer | Labor |  |  | 1
TTT-BELT | Belt Splicer | Labor |  |  | 1
TTT-CROP-1 | EWP Operator | Labor |  |  | 1
TTT-ELECSUP | Supervisor E&I | Labor |  |  | 1
MUD-SC | EW Sub-Contractors | Labor |  |  | 1
PKG338-1 | PKG338_FOCUS Labour | Labor |  |  | 8
PKG338-2 | PKG338_FOCUS Equipment | Nonlabor |  |  | 1
PKG338-1.1 | FOCUS-Boomlift | Nonlabor |  |  | 1
PKG338-1.2 | FOCUS-EWP | Nonlabor |  |  | 1
PKG338-1.3 | FOCUS-Crane | Nonlabor |  |  | 1
11 | Contractor - Senior Process Engineer | Labor |  |  | 1
12 C | Contractor - Senior Mechanical Engineer 1 | Labor |  |  | 1
13 | Contractor - Senior Structural Engineer | Labor |  |  | 1
18 | Contractor - Consultant Process Engineer | Labor |  |  | 1
20 C | Contractor - Process Modelling Specialist | Labor |  |  | 1
29 C | Contractor - Study Lead | Labor |  |  | 1
31 C | Contractor - Lead Process Engineer | Labor |  |  | 1
32 C | Contractor - Lead Mechanical Engineer | Labor |  |  | 1
33 C | Contractor - Senior Mechanical Engineer 2 | Labor |  |  | 1
34 C | Contractor - Lead Structural Engineer | Labor |  |  | 1
35 C | Contractor - Structural Engineer | Labor |  |  | 1
36 C | Contractor - Lead Designer | Labor |  |  | 1
37 C | Contractor - Senior SMP Designer 1 | Labor |  |  | 1
38 C | Contractor - Senior SMP Designer 2 | Labor |  |  | 1
39 C | Contractor - Lead EIC Engineer | Labor |  |  | 1
40 C | Contractor - Senior EIC Engineer | Labor |  |  | 1
41 C | Contractor - Senior EIC Designer | Labor |  |  | 1
42 C | Contractor - Scheduler / Estimator | Labor |  |  | 1
43 C | Consultant - Cost & Schedule Range Analysis | Labor |  |  | 1
R-ELECLAB | Electrician-Labelling Crew | Labor |  |  | 1
99324-WOR | CTG - Execution | Labor |  |  | 1
CTG-PIP | Piping Team | Labor |  |  | 24
CTG-MECH | Mechanical Team | Labor |  |  | 16
CTG-E&I | E&I Team | Labor |  |  | 16
CTG-CIV | Civils Team | Labor |  |  | 24
CTG-CARP | Steelwork Team | Labor |  |  | 24
CTG-SCAFF | Scaffolding Team | Labor |  |  | 24
CTG-COMM | Commissioning Team | Labor |  |  | 24
CTG-DECOMM | Demolition Team | Labor |  |  | 16
3000 | Engineering | Labor |  |  | 1
G-1000 | General Management Services | Labor |  | A | 1
G-3060 | Civil | Labor |  | A | 1
G-3030 | Piping | Labor |  | A | 1
G-3020 | Mechanical | Labor |  | A | 1
G-3010 | Process | Labor |  | A | 1
A0105 | A0105 - Tests including reports | Nonlabor |  |  | 1
A0203 | A0203 - Dust Control | Nonlabor |  |  | 1
A0401 | A0401 - Mass / Area Excavation | Nonlabor |  |  | 1
A0405a | A0405 - Overhaul | Nonlabor |  |  | 1
A0408 | A0408 - Rock Fill | Nonlabor |  |  | 1
A0601 | A0601 - Trenching Excavation_Conventional | Nonlabor |  |  | 1
A0602 | A0602 - Trenching Excavation_Rock | Nonlabor |  |  | 1
A0604 | A0604 - Pipe Bed and/or surround | Nonlabor |  |  | 1
A0605 | A0605 - Trenching Backfill | Nonlabor |  |  | 1
A0802 | A0802 - Erosion Control | Nonlabor |  |  | 1
A0902 | A0902 - Demolition - Site Preparation | Nonlabor |  |  | 1
B0201 | B0201 - Gabion system | Nonlabor |  |  | 1
B0402 | B0402 - Liner - Geotextile | Nonlabor |  |  | 1
B0404 | B0404 - Outlet structures | Nonlabor |  |  | 1
B0504 | B0504 - Stormwater pipework | Nonlabor |  |  | 1
B0505 | B0505 - Subsoil drains | Nonlabor |  |  | 1
B0601 | B0601 - Layerworks - Rail | Nonlabor |  |  | 1
B0610 | B0610 - Traffic Control | Nonlabor |  |  | 1
B0701 | B0701 - Fencing | Nonlabor |  |  | 1
C0101 | C0101 - Mass Concrete Fill | Nonlabor |  |  | 1
C0201 | C0201 - Structure Foundations | Nonlabor |  |  | 1
C0203 | C0203 - Ground Slab | Nonlabor |  |  | 1
C0204 | C0204 - Elevated Slabs | Nonlabor |  |  | 1
C0208 | C0208 - Stairs | Nonlabor |  |  | 1
C0303 | C0303 - Ground Slab | Nonlabor |  |  | 1
C0502 | C0502 - Waterproofing | Nonlabor |  |  | 1
C0504 | C0504 - Steel Reinforcement - Mild Steel | Nonlabor |  |  | 1
C0505 | C0505 - Steel Reinforcement - High Tensile | Nonlabor |  |  | 1
C0506 | C0506 - Welded Steel Mech Fabric | Nonlabor |  |  | 1
C0507 | C0507 - Materials Testing | Nonlabor |  |  | 1
D0106 | D0106 - Hollow Core Sections | Nonlabor |  |  | 1
D0206 | D0206 - Hollow Core Sections | Nonlabor |  |  | 1
D0306 | D0306 - Handrails | Nonlabor |  |  | 1
E0303 | E0303 - Exterior Walls | Nonlabor |  |  | 1
N0401 | N0401 - Screens and Grizzleys | Nonlabor |  |  | 1
N0402 | N0402 - Crushers | Nonlabor |  |  | 1
O0101 | O0101 - Concrete Mast Foundation | Nonlabor |  |  | 1
O0102 | O0102 - Concrete Mast - 64kNm Pole | Nonlabor |  |  | 1
O0103 | O0103 - Concrete Mast - 84kNm Pole | Nonlabor |  |  | 1
O0104 | O0104 - PushPull Registration | Nonlabor |  |  | 1
O0106 | O0106 - Double Boom | Nonlabor |  |  | 1
O0107 | O0107 - Contact Wire | Nonlabor |  |  | 1
O0108 | O0108 - Cantenary Wire | Nonlabor |  |  | 1
O0111 | O0111 - Stay Wire | Nonlabor |  |  | 1
O0116 | O0116 - Droppers | Nonlabor |  |  | 1
P0110 | P0110 - HDPE (51mm to 150mm) | Nonlabor |  |  | 1
P0111 | P0111 - HDPE (151mm to 600mm) | Nonlabor |  |  | 1
P0202 | P0202 - Carbon Steel (51mm to 150mm) | Nonlabor |  |  | 1
P0203 | P0203 - Carbon Steel (151mm to 600mm) | Nonlabor |  |  | 1
P0701 | P0701 - Valves | Nonlabor |  |  | 1
P0702 | P0702 - Valve Chambers | Nonlabor |  |  | 1
R0101 | R0101 - 48kg/m rails | Nonlabor |  |  | 1
R0102 | R0102 - 60kg/m rails | Nonlabor |  |  | 1
R0103 | R0103 - Miscellaneous | Nonlabor |  |  | 1
R0104 | R0104 - PY Sleeper | Nonlabor |  |  | 1
R0105 | R0105 - P2 Sleeper | Nonlabor |  |  | 1
R0106 | R0106 - 48kg/m 1:9 (S) Turnout | Nonlabor |  |  | 1
R0110 | R0110 - 60kg/m 1:12 (T) Turnout | Nonlabor |  |  | 1
R0111 | R0111 - Ballast | Nonlabor |  |  | 1
R0113 | R0113 - Level crossing | Nonlabor |  |  | 1
R0114 | R0114 - Sign Boards & Posts | Nonlabor |  |  | 1
R0115 | R0115 - Grit walkway | Nonlabor |  |  | 1
T0105 | T0105 - Distribution Boards (Medium Voltage) | Nonlabor |  |  | 1
T0109 | T0109 - Cable ducts | Nonlabor |  |  | 1
T0206 | T0206 - Lighting Fixtures & Panels | Nonlabor |  |  | 1
U0201 | U0201 - Conduit; Above Ground | Nonlabor |  |  | 1
W0301 | W0301 - Special Cable | Nonlabor |  |  | 1
X0204 | X0204 - Level Switch | Nonlabor |  |  | 1
X0303 | X0303 - Signals | Nonlabor |  |  | 1
Y1210 | Y1210 - Construction Management | Nonlabor |  |  | 1
Y1300 | Y1300 - Project Administration | Nonlabor |  |  | 1
Y1460 | Y1460 - Procurement | Nonlabor |  |  | 1
Y2100 | Y2100 - Construction Management | Nonlabor |  |  | 1
Y2114 | Y2114 - Site Contracts Administration | Nonlabor |  |  | 1
Y2116 | Y2116 - Site Planner | Nonlabor |  |  | 1
Y2315 | Y2315 - Operations Support | Nonlabor |  |  | 1
Y3100 | Y3100 - Flights & Accomodation | Nonlabor |  |  | 1
Y3130 | Y3130 - Accommodation | Nonlabor |  |  | 1
Y3240 | Y3240 - Small Tools | Nonlabor |  |  | 1
Y3250 | Y3250 - PPE | Nonlabor |  |  | 1
Y3300 | Y3300 - Consumable\ Expendables | Nonlabor |  |  | 1
Y3410 | Y3410 - Mobilisation/ demobilisation | Nonlabor |  |  | 1
Y3423 | Y3423 - Safety Issues | Nonlabor |  |  | 1
Y3430 | Y3430 - Training | Nonlabor |  |  | 1
Y3940 | Y3940 - Insurances | Nonlabor |  |  | 1
Y4010 | Y4010 - Light Vehicles | Nonlabor |  |  | 1
Y4030 | Y4030 - Plant & Equipment | Nonlabor |  |  | 1
Y5010 | Y5010 - Site Security | Nonlabor |  |  | 1
Y6120 | Y6120 - Site Buildings | Nonlabor |  |  | 1
Y7110 | Y7110 - Construction Water Supply | Nonlabor |  |  | 1
Z02-01 | Z02 - Contingency01 | Nonlabor |  |  | 1
37 | 37 | Labor |  |  | 1
38 | 38 | Labor |  |  | 1
Worley_RSRC-TBDS | Worley Resource- To Be Deleted Soon | Labor |  | Global | 1
T11916 | South32 Quindanning Rd | Labor |  |  | 1
T11916.QTY | Quantities | Material |  |  | 12
T11916.MHR | Manhours | Labor |  |  | 1
SL-1 | Southern Leases Study | Labor |  |  | 1
A700.C.86059 | [BAUXITE] Quindanning Mine Enabling Infrastructure | Labor |  |  | 1
86059.MHRC | Manhours (Contractor) | Labor |  |  | 1
86059.C&G | Clear & Grub | Material | Hectare |  | 8
86059.TS | Topsoil | Material | Cubic Metres |  | 8
86059.FP | Foundation Preparation | Material | Square Metres |  | 8
86059.CTF | Cut to Fill | Material | Cubic Metres |  | 8
86059.CTS | Cut to Spoil | Material | Cubic Metres |  | 8
86059.TC | Trim Cut | Material | Square Metres |  | 8
86059.CF | Common Fill | Material | Cubic Metres |  | 8
86059.BTF | Borrow to Fill | Material | Cubic Metres |  | 8
86059.TF | Trim Fill | Material | Square Metres |  | 8
86059.SG | Subgrade Preparation | Material | Square Metres |  | 8
86059.BC | Basecourse | Material | Cubic Metres |  | 8
86059.CSP | CSP Culvert | Material | Lineal Metres |  | 8
86059.FR | Facing Rock | Material | Square Metres |  | 8
86059.RS | Road Surfacing | Material | Square Metres |  | 8
86059.RM | Road Marking | Material | Lineal Metres |  | 8
86059.GP | Guide Post | Material | Each |  | 8
86059.RSG | Road Sign | Material | Each |  | 8
86059.DR | Demolition Road | Material | Square Metres |  | 8
86059.DD | Demolition Drainage | Material | Items |  | 8
86059.RED | Rehabilitation Road | Material | Square Metres |  | 8
86059.ELH | Excavate Load & Haul | Material | Cubic Metres |  | 8
86059.IC | Insitu Concrete | Material | Cubic Metres |  | 8
86059.GF | Gravel Footpath | Material | Lineal Metres |  | 8
86059.CK | Concrete Kerb | Material | Lineal Metres |  | 8
86059.KEB | Kerb End Batter | Material | Each |  | 8
86059.YB | Yellow Bi-Directional | Material | Each |  | 8
86059.EX | Structural Excavation | Material | Cubic Metres |  | 8
86059.SB | Structural Backfill | Material | Cubic Metres |  | 8
86059.BL | Blinding Concrete | Material | Cubic Metres |  | 8
86059.PCA | Precast Concrete Arch | Material | Each |  | 8
86059.WW | MSE Wingwalls | Material | Each |  | 8
86059.SP | MSE Spandrels | Material | Each |  | 8
86059.HR | Handrails | Material | Lineal Metres |  | 8
86059.RF | Rock Fence | Material | Lineal Metres |  | 8
86059.GA | Gates | Material | Each |  | 8
86059.PC | Protective Coating | Material | Each |  | 8
86059.WC | Wearing Coarse | Material | Cubic Metres |  | 8
86059.BI | Bitumen Seal | Material | Cubic Metres |  | 8
86059.GRB | Grading Rails Barrier | Material | Lineal Metres |  | 8
86059.WR | Windrows | Material | Cubic Metres |  | 8
86059.RP | Rock Pitching | Material | Square Metres |  | 8
86059.FS | Foam Sealant | Material | Lineal Metres |  | 8
86059.SD | Subsoil Drain | Material | Lineal Metres |  | 8
86059.RV | Revegetation | Material | Square Metres |  | 8
86059.RA | Remove Asbestos Pipe | Material | Lineal Metres |  | 8
86059.PI | PVC Pipe | Material | Lineal Metres |  | 8
86059.TE | Telstra Cables | Material | Lineal Metres |  | 8
86059.SF | Stock Fencing | Material | Lineal Metres |  | 8
86059.MFE | Mine Fencing | Material | Lineal Metres |  | 8
86059.CFE | Chain Wire Fencing | Material | Lineal Metres |  | 8
86059.CRA | Crush Rock Aggregate | Material | Lineal Metres |  | 8
86059.RTE | Remove Obsolete Telstra Cables | Material | Lineal Metres |  | 8
86059.RCP | RCP Culvert | Material | Lineal Metres |  | 8
86059.PS | Prime Seal | Material | Cubic Metres |  | 8
86059.GRE | Grading Rails End Treatment | Material | Lineal Metres |  | 8
86059.RDS | Redundant Seal | Material | Square Metres |  | 8
86059.LW | L-Walls | Material | Each |  | 8
86059.STB | Stabilisation | Material | Cubic Metres |  | 8
86059.BLD | Building | Material | Each |  | 8
86059.PTW | Potable Water System | Material | Lump Sum |  | 8
86059.WWS | Waste Water System | Material | Lump Sum |  | 8
86059.ELI | Electrical Insfrastructure | Material | Lump Sum |  | 8
TSFE6-001 | TSFE6 FS Owner Team hours | Labor |  |  | 1
R-3 | GEMCO Water Disposal | Labor |  |  | 1
S32 | HMD Feasibility Study | Labor |  |  | 1
Abdul Akle Projects | Abdul Akle Projects | Labor |  |  | 1
GGW | GGW | Labor |  |  | 1
CONTRACTOR | Contractor | Labor |  |  | 1
20047 | COPP20047 - 7 Mile RSM Workshop Phase 1 (Wheel Farm Extension) | Labor |  |  | 1
Budget | Budget Execution | Nonlabor |  |  | 1
k | Scheduling / Planning | Labor |  | A | 1
5876 ¦ S32 AMP | Generic ESP Labour | Labor |  | A | 1
86059.MHRE | Manhours (Estimate) | Labor |  |  | 1
SA | (New Resource) | Labor |  |  | 1
86059.HDPE | HDPE Pipe | Material | Lineal Metres |  | 8
86059.CT | Cable Trays | Material | Lineal Metres |  | 8
TTT-SKID | Skid | Nonlabor |  |  | 0
TTT-BOGGER | Bogger | Nonlabor |  |  | 0
TTT-UGFRA | UG Franna | Nonlabor |  |  | 0
5876 ¦ S32 | Amgard SWG Upgrade | Labor |  |  | 1
5876 ¦ S32 ¦ IND | Indirect | Labor |  |  | 1
5876 ¦ S32 ¦ ENG | Engineering ¦ Direct | Labor |  |  | 1
5876 ¦ S32 ¦ DSG | Design ¦ Direct | Labor |  |  | 1
NULL_HRDC | Drafting Civil | Labor |  |  | 1
NULL_HREC | Engineer Civil | Labor |  |  | 1
NULL_HRDM | Drafting Mechanical | Labor |  |  | 1
NULL_HRDS | Drafting Structural | Labor |  |  | 1
NULL_HRDE | Drafting Electrical | Labor |  |  | 1
NULL_HREM | Engineer Mechanical | Labor |  |  | 1
NULL_HRES | Engineer Structural | Labor |  |  | 1
NULL_HREE | Engineer Electrical | Labor |  |  | 1
NULL_HEIC | Engineer Instr & Comms | Labor |  |  | 1
NULL_HDIC | Drafting Instr & Controls | Labor |  |  | 1
NULL_HEG | Engineer General | Labor |  |  | 1
RAPFEL4 | RAPTOR_Hours | Labor |  |  | 1
RF | FABRICATION | Labor |  |  | 1
RE | ENGINEERING | Labor |  |  | 1
RP | PROCUREMENT | Labor |  |  | 1
RC | CONSTRUCTION | Labor |  |  | 1
RCO | COMMISSIONING | Labor |  |  | 1
COPP22344 | COPP22344 - S32 Water Exploration | Labor |  |  | 1
CBRE | Calibre | Labor |  |  | 1
STH32 | South 32 | Labor |  |  | 1
CTR | Contractor | Labor |  |  | 1
GG | Global Groundwater | Labor |  |  | 1
R-90 | Earthworks & Pavement Crew | Labor |  |  | 1
R-91 | Drainage Crew | Labor |  |  | 1
R-92 | Asphalt Crew | Labor |  |  | 1
R-93 | Concrete Crew | Labor |  |  | 1
R-95 | Fencing Crew | Labor |  |  | 1
R-96 | W-Beam Crew | Labor |  |  | 1
R-97 | Services Crew | Labor |  |  | 1
R-99 | Painting/Linemarking Crew | Labor |  |  | 1
R-101 | Precast Crew | Labor |  |  | 1
R-103 | Project Management | Labor |  |  | 1
R-104 | Site Establishment/Building | Labor |  |  | 1
R-105 | Maintenance | Labor |  |  | 1
R-106 | Clearing & Stripping | Labor |  |  | 1
R-107 | Revetment Mattress | Labor |  |  | 1
R-108 | Kerbing Crew | Labor |  |  | 1
S32-PROMHR | South32 Procurement Manhours | Labor |  |  | 0
SUP-1 | Supply Resource | Labor |  |  | 1
PRO-1 | Project Team | Labor |  |  | 1
Str/Mech | Structural / Mechanical | Labor |  |  | 2
GGIMP | Georgiou Imported Resources | Labor |  |  | 1
GGSTD | Georgiou Standard Resources (GGSTD) | Labor |  |  | 1
GGSTD-LAB | GGSTD Labour Resources | Labor |  |  | 1
GGSTD-NL | GGSTD Non-Labour Resources | Nonlabor |  |  | 1
GGSTD-MAT | GGSTD Material Resources | Material |  |  | 10
NHU (6123) | Newell Highway Upgrade - Parkes Bypass | Nonlabor |  |  | 1
GGSTD-LABD | GGSTD Labour Resources - Direct | Labor |  |  | 1
GGSTD-NLD | GGSTD Non-Labour Resources - Direct | Nonlabor |  |  | 1
GGSTD-MATPR | GGSTD Material Resources - Productivity Rates | Material |  |  | 10
Formwork Crew | Formwork Crew | Labor |  |  | 1
GGSTD-NLD-RR15TP | Roller 15 Tonne Padfoot | Nonlabor |  |  | 1
GGSTD-LABD-CW3 | Worker Gr CW3; Spotter, Conc Finisher, Reo fixer | Labor |  |  | 1
GGSTD-NLD-CR80T | Crane 80 Tonne | Nonlabor |  |  | 1
GGSTD-LABD-CO | Crane Operator | Labor |  |  | 1
GGSTD-MATP-CONCRETE | Concrete Works | Material | Cubic Metres |  | 100
GGSTD-NLD-WLOAD | Wheel Loader | Nonlabor |  |  | 1
GGSTD-MATP-GEOFB | Geofabric | Material | Square Metres |  | 10
7068-000 | Plant List | Nonlabor |  |  | 1
GGSTD-MATP-CSUNS | Cut Unsuitable Material | Material | Cubic Metres |  | 10
GGSTD-MATP-GEOWV | Geoweb | Material | Square Metres |  | 10
GGSTD-MATP-GRFIL | Granular Fill | Material | Cubic Metres |  | 10
GGSTD-NLD-EX85T-2 | Excavator 85 Tonne - Long Reach | Nonlabor |  |  | 1
GGSTD-LABD-CO80T | Crane Operator 40-80T | Labor |  |  | 1
GGSTD-LABD-CW3-SF | Worker Gr CW3: Steel Structure Fixer | Labor |  |  | 1
GGSTD-MATP-PILES | Piles | Material | Tonnes |  | 10
R-89 | Piling Rig | Nonlabor |  |  | 1
R-9 | (New Resource) | Labor |  |  | 1
WPR | Wessels Progress Resource | Labor |  |  | 0
Elect-4 | Elect | Labor |  |  | 1
Eng-4 | Eng | Labor |  |  | 1
Wormald-1 | Wormald | Labor |  |  | 1
Elec200%-1 | Elec200% | Labor |  |  | 1
G-A-1000 | General Management Services-HO | Labor |  |  | 1
G-A-2070 | Project Estimating-HO | Labor |  |  | 1
G-A-2080 | Project Controls-HO | Labor |  |  | 1
G-A-2082 | Scheduling / Planning-HO | Labor |  |  | 1
G-A-2982 | Document Control-HO | Labor |  |  | 1
G-A-2020 | Project Engineering-HO | Labor |  |  | 1
G-A-2010 | Project Management-HO | Labor |  |  | 1
G-A-3011 | Process Engineering-HO | Labor |  |  | 1
G-A-3012 | Process Design-HO | Labor |  |  | 1
G-A-3021 | Mechanical Engineering-HO | Labor |  |  | 1
G-A-3022 | Mechanical Design-HO | Labor |  |  | 1
G-A-3031 | Piping Engineering-HO | Labor |  |  | 1
G-A-3032 | Piping Design-HO | Labor |  |  | 1
G-A-3041 | Electrical Engineering-HO | Labor |  |  | 1
G-A-3042 | Electrical Design-HO | Labor |  |  | 1
G-A-3051 | Instrumentation Engineering-HO | Labor |  |  | 1
G-A-3052 | Instrumentation Design-HO | Labor |  |  | 1
G-A-3061 | Civil Engineering-HO | Labor |  |  | 1
G-A-3062 | Civil Design-HO | Labor |  |  | 1
G-A-3071 | Structural Engineering-HO | Labor |  |  | 1
G-A-3072 | Structural Design-HO | Labor |  |  | 1
G-A-3970 | Engineering Design Systems (EDS)-HO | Labor |  |  | 1
G-B-1122 | Project HSE Management-GID | Labor |  |  | 1
G-B-2070 | Project Estimating-GID | Labor |  |  | 1
G-B-2080 | Project Controls-GID | Labor |  |  | 1
G-B-2082 | Scheduling / Planning-GID | Labor |  |  | 1
G-B-2982 | Document Control-GID | Labor |  |  | 1
G-B-2020 | Project Engineering-GID | Labor |  |  | 1
G-B-2010 | Project Management-GID | Labor |  |  | 1
G-B-3011 | Process Engineering-GID | Labor |  |  | 1
G-B-3012 | Process Design-GID | Labor |  |  | 1
G-B-3021 | Mechanical Engineering-GID | Labor |  |  | 1
G-B-3022 | Mechanical Design-GID | Labor |  |  | 1
G-B-3031 | Piping Engineering-GID | Labor |  |  | 1
G-B-3032 | Piping Design-GID | Labor |  |  | 1
G-B-3041 | Electrical Engineering-GID | Labor |  |  | 1
G-B-3042 | Electrical Design-GID | Labor |  |  | 1
G-B-3051 | Instrumentation Engineering-GID | Labor |  |  | 1
G-B-3052 | Instrumentation Design-GID | Labor |  |  | 1
G-B-3061 | Civil Engineering-GID | Labor |  |  | 1
G-B-3062 | Civil Design-GID | Labor |  |  | 1
G-B-3071 | Structural Engineering-GID | Labor |  |  | 1
G-B-3072 | Structural Design-GID | Labor |  |  | 1
G-B-3970 | Engineering Design Systems (EDS)-GID | Labor |  |  | 1
G-A-1081 | Governance and Risk-HO | Labor |  |  | 1
G-A-1122 | Project HSE Management-HO | Labor |  |  | 1
R-111 | Budget Cost Rev5C | Nonlabor |  |  | 0
GGSTD-LABI | GGSTD Labour Resources - Indirect (White Collar) | Labor |  |  | 1
GGSTD-LABS | GGSTD Labour Resources - Subcontractor | Labor |  |  | 1
GGSTD-LABI-TRF | Traffic Management | Labor |  |  | 1
GGSTD-LABSD | Subcontractor - Direct | Labor |  |  | 1
GGSTD-LABSD-NAME | Subbies | Labor |  |  | 1
GGSTD-LABSD-ELC | Electrical | Labor |  |  | 1
Portfolio Plan | Portfolio Summary Programme | Labor |  |  | 1
PMFS | Execution Project Manager 30% in FS | Labor |  |  | 0
SMC | Study Manager 70% in Concept | Labor |  |  | 1
NULL_GEO | Engineer Geotech | Labor |  |  | 1
NULL_EGIS | EGIS | Labor |  |  | 1
NULL_PCM | Manager Project Controls | Labor |  |  | 1
S657 | Scraper 657 | Nonlabor |  |  | 1
S637 | Scraper 637 | Nonlabor |  |  | 1
R-11 | CSP Linear Meters | Material |  |  | 8
E&I | Electrical & Instrumentation | Labor |  |  | 1
Civ | Civil | Labor |  |  | 1
R-94 | Stone/Rock pitching Crew | Labor |  |  | 1
R-112 | Clearing & Grubbing | Material | Square Metres |  | 10
R-113 | Earthworks | Material | Cubic Metres |  | 10
R-114 | Road Pavement - Subgrade prep | Material | Square Metres |  | 10
R-115 | Concrete | Material | Cubic Metres |  | 10
R-116 | Sealing | Material | Square Metres |  | 10
R-117 | Precast | Material | GG - units |  | 10
R-118 | Surface Finishing | Material | Square Metres |  | 10
R-119 | Drainage | Material | GG - metre (linear) |  | 10
R-120 | Fencing | Material | GG - metre (linear) |  | 10
R-121 | Stripping Top Soil | Material | Cubic Metres |  | 10
R-122 | Road Pavement - Subbase/Basecourse | Material | Cubic Metres |  | 10
G-A-0000 | Labour Resource Pool-HO | Labor |  |  | 1
G-B-0000 | Labour Resource Pool-GID | Labor |  |  | 1
G-A-2000 | Project Management & Coordination-HO | Labor |  |  | 1
G-A-3000 | Engineering-HO | Labor |  |  | 1
G-B-1000 | General Management Services-GID | Labor |  |  | 1
G-B-2000 | Project Management & Coordination-GID | Labor |  |  | 1
G-B-3000 | Engineering-GID | Labor |  |  | 1
R-148 | Budget Cost-Prelims Rev9 | Nonlabor |  |  | 0
Groote | South32 GEMCO - J Quarry & Eastern Leases | Labor |  |  | 1
ELS Materials | Eastern Leases South - Material Resources | Material |  |  | 8
ELS Plant | Eastern Leases South - Plant Resources | Nonlabor |  |  | 1
ELS-GF | General Fill (Cut or Borrow) | Material | Cubic Metres |  | 8
ELS-BC | Basecourse | Material | Cubic Metres |  | 8
ELS-WC | Wearing Course | Material | Cubic Metres |  | 8
ELS-C2S | Cut to Spoil - Unsuitable | Material | Cubic Metres |  | 8
ELS-CSP | CSP | Material | Lineal Metres |  | 8
ELS-C&G | Clear & Grub | Material | Square Metres |  | 8
ELS-TSS | Topsoil Strip | Material | Cubic Metres |  | 8
ELS-BERM | Safety Berms | Material | Lineal Metres |  | 8
ELS-FP | Foundation Preparation | Material | Square Metres |  | 8
ELS-EXC | Excavator | Nonlabor |  |  | 1
ELS-TRIM | Trimming | Material | Square Metres |  | 8
ELS-SCR | Scraper | Nonlabor |  |  | 1
ELS-EXC CV | Excavator | Nonlabor |  |  | 1
R-16 | Construction Teams | Labor |  |  | 1
WOT | W.O. Track Works - Resources | Labor
S32 Rapotor | Labour Resources | Labor |  |  | 1
R-17 | Perway Construction | Labor |  |  | 9
Labor | Labour - Resources | Labor
Dtrack-1 | Destressing of Track (per rail) | Labor |  |  | 125
Tampi-1 | Tamping | Labor |  |  | 100
BallastR-1 | Balast - Regulate | Labor |  |  | 100
BallastLD-1 | Ballasting - Loading and Distribution | Labor |  |  | 50
RailF-1 | Rail Fastening | Labor |  |  | 31
RailsL-1 | Rails Loading & Off Loading | Labor |  |  | 63
SleeperP-1 | Sleepers - Distribute to alignment on formation | Labor |  |  | 38
SleeperL-1 | Sleepers Loading & Off Loading | Labor |  |  | 63
Welds-1 | Welding | Labor |  |  | 3
TAMPO | Tamper Operator | Labor |  |  | 1
RailU-1 | Rails Uplifing & Sort & Stack | Labor |  |  | 25
LwRailsP-1 | Long Welded Rails - Placing | Labor |  |  | 63
BHP-WF | BHP Wind Fences | Labor |  |  | 1
2200 Asset Managemen-6 | 2200 Asset Management | Labor |  |  | 1
Franna-1 | Franna | Labor |  |  | 1
250T | GEMCO 250T Crane | Labor |  |  | 1
HireCrane | Hire Crane TBS | Labor |  |  | 1
MUD_S32 | MUD-S32 Owners Team | Nonlabor |  |  | 1
MUD-KE | KEvans | Labor |  |  | 1
MUD-AR | ARix | Labor |  |  | 1
MUD-MH | MHunt | Labor |  |  | 1
MUD-MG | MGiles | Labor |  |  | 1
MUD-ED | EDunn | Labor |  |  | 1
MUD-BS | BSmith | Labor |  |  | 1
MUD-AC | ACrow | Labor |  |  | 1
MUD-AP | APurchase | Labor |  |  | 1
MUD-PM | PMatheson | Labor |  |  | 1
MUD-PvM | PvdMerwe | Labor |  |  | 1
MUD-SUP | Supply | Labor |  |  | 1
ELL | ELL | Labor |  |  | 1
ME | ME | Labor |  |  | 1
Comms | Comms | Labor |  |  | 1
Concretors | Concretors | Labor |  |  | 1
GEL | GEL | Labor |  |  | 1
NPI | NPI | Labor |  |  | 1
a | a | Labor |  |  | 1
MUD_CIV | 01. Mud-Civil | Labor |  |  | 1
MUD_PIP | 02. Mud-Piping | Labor |  |  | 1
MUD_MEC | 03. Mud-Mechanical | Labor |  |  | 1
MUD_STR | 04. Mud-Structural | Labor |  |  | 1
MUD_ELE | 05. Mud-Electrical | Labor |  |  | 1
MUD_INS | 06. Mud-Instrumentation | Labor |  |  | 1
MUD-OTH | 07. Mud-Other | Labor |  |  | 1
In8-S32 | InEight-South32 | Labor |  |  | 1
In8-Vendor | InEight-Vendor | Labor |  |  | 1
In8-Contingency | InEight-Contingency | Nonlabor |  |  | 1
TTT-S32Paste-UG | S32 Paste Crew - UG | Labor |  |  | 1
DRA Global Resources | DRA Global Resource Libary | Labor |  |  | 1
AMER Resources | AMER Resource Library | Labor |  |  | 1
INDIRC-SUPV | Indirect Labour - Supervisory | Labor |  |  | 1
INDIRC-HO | Indirect Labour - Office based | Labor |  |  | 1
R-12 | Float | Nonlabor |  |  | 1
R-13 | Manitou | Nonlabor |  |  | 1
R-14 | 15T Excavator | Nonlabor |  |  | 1
Craig Richards | Craig Richards | Labor |  |  | 1
South32 | South32 | Labor |  |  | 1
Optus | Optus | Labor |  |  | 1
Julz Johnson | Julz Johnson | Labor |  |  | 1
Optus Procurement | Optus Procurement | Labor |  |  | 1
ABU EXCL TP | ABU ALL RESOURCES EXCL Technical Projects | Labor |  |  | 1
ABU JDE CMMS CRAFT CODES | ABU JDE CMMS CRAFT CODES - Imported via Legare Integration | Labor |  |  | 1
GGP | Gorgon Gas Plant | Labor |  |  | 1
KTH | Wheatstone Karratha | Labor |  |  | 1
GGP-FE-ELEC | Electrical Engineer | Labor |  |  | 1
GGP-FE-INSP | Inspector | Labor |  |  | 1
GGP-FE-INST | Instrument Engineer | Labor |  |  | 1
GGP-FE-PROC | Process Engineer | Labor |  |  | 1
GGP-MS-MECHTECH | Mechanical Tech | Labor |  |  | 1
GGP-MS-PSV | PSV Technician | Labor |  |  | 1
GGP-MS-RIGGER | Rigger | Labor |  |  | 1
GGP-EQ | GGP Equipment (Do Not Assign This Level) | Nonlabor |  |  | 1
GGP-TA-LABOUR | GGP TA Labour (Do Not Assign This Level) | Labor |  |  | 1
GGP-VENDORS | GGP Vendors (Do Not Assign This Level) | Labor |  |  | 1
KTH-MS-MECHTECH | Mechanical Tech | Labor |  |  | 1
KTH-MS-PSV | PSV Technician | Labor |  |  | 1
GGP-EQ-CRANE110T | Mobile Crane - 110T | Nonlabor |  |  | 1
GGP-EQ-CRANE50T | Mobile Crane - 50T | Nonlabor |  |  | 1
GGP-EQ-FRKLT10T | Forklift - 10T | Nonlabor |  |  | 1
GGP-EQ-FRKLT2T | Forklift - 2.5T | Nonlabor |  |  | 1
GGP-EQ-FRKLT5T | Forklift - 5T | Nonlabor |  |  | 1
GGP-VEN-GEN | Vendor - General | Labor |  |  | 1
GGP-TA-ELECTECH | TA Electrical Technician | Labor |  |  | 1
GGP-TA-GSTECH | TA General Services Technician | Labor |  |  | 1
GGP-TA-HEAT | TA Heat Technician | Labor |  |  | 1
GGP-TA-INSPEC | TA Inspector | Labor |  |  | 1
GGP-TA-LAGGR | TA Lagger/ Sheet Metal | Labor |  |  | 1
GGP-TA-MECHTECH | TA Mechanical Technician | Labor |  |  | 1
GGP-TA-NDTTECH | TA NDT Technician | Labor |  |  | 1
GGP-TA-OPS | TA Operators | Labor |  |  | 1
GGP-TA-PAINTR | TA Painter | Labor |  |  | 1
GGP-TA-PIPEFITTR | TA Pipe Fitter | Labor |  |  | 1
GGP-TA-PRCTECH | TA Process Control Technician | Labor |  |  | 1
GGP-TA-RIGGER | TA Rigger | Labor |  |  | 1
GGP-TA-ROPE | TA Rope Access | Labor |  |  | 1
GGP-TA-SAFW | TA CSE Watch / Fire Watch | Labor |  |  | 1
GGP-TA-SCAFFLD | TA Scaffolder | Labor |  |  | 1
GGP-TA-SPEC | TA Specialist | Labor |  |  | 1
GGP-TA-VLVTECH | TA Valve Technician | Labor |  |  | 1
GGP-TA-WELD | TA Welder | Labor |  |  | 1
GGP-EQ-CRANE40T | Mobile Crane - 40T | Nonlabor |  |  | 1
GGP-EQ-CRANE220T | Mobile Crane - 220T | Nonlabor |  |  | 1
GGP-EQ-FBTRK8T | Flat Bed Truck 8T | Nonlabor |  |  | 1
GGP-EQ-FBTRK12T | Flat Bed Truck 12T | Nonlabor |  |  | 1
GGP-TA-INSTTBFT | TA Instrument Tube Fitter | Labor |  |  | 1
GGP-EQ-WELDMA | Welding Machine | Nonlabor |  |  | 1
GGP-EQ-GENSET | Generator | Nonlabor |  |  | 1
GGP-EQ-COMPR | Air Compressor | Nonlabor |  |  | 1
GGP-TA-MECHSUPER | TA Mechanical Supervisor | Labor |  |  | 1
GGP-TA-VLVSUPER | TA Valve Supervisor | Labor |  |  | 1
GGP-TA-QAELEC | TA QA Inspector for Instrumentation Control and Electrical | Labor |  |  | 1
GGP-TA-QAVESSEL | TA QA Inspector for Vessels and Piping | Labor |  |  | 1
GGP-TA-QMITECH | TA QMI Technician | Labor |  |  | 1
GGP-VEN-VALVE | Vendor - Specialist Valve | Labor |  |  | 1
GGP-EQ-HEATTRMT | Pre/Post Weld Heat Treatment | Nonlabor |  |  | 1
GGP-TA-PRCTSUPE | TA Process Control Technician Supervisor | Labor |  |  | 1
GGP-TA-CRO | TA Control Room Operator | Labor |  |  | 1
Senior Professional | Senior Professional 1 | Labor |  |  | 1
Manager 3 | Manager 3 | Labor |  |  | 1
Professional 2 | Professional 2 | Labor |  |  | 1
ODC | ODC | Labor |  |  | 1
Senior Tech Officer | Senior Tech Officer 1 | Labor |  |  | 1
Senior Professiona-1 | Senior Professional 2 | Labor |  |  | 1
Principal Tech Offic | Principal Tech Officer 2 | Labor |  |  | 1
Principal Profession | Principal Professional 1 | Labor |  |  | 1
Senior Professiona-2 | Senior Professional 1 | Labor |  |  | 1
Senior Tech Office-1 | Senior Tech Officer 1 | Labor |  |  | 1
Senior Professiona-3 | Senior Professional 2 | Labor |  |  | 1
Principal Tech Off-1 | Principal Tech Officer 2 | Labor |  |  | 1
Principal Professi-1 | Principal Professional 1 | Labor |  |  | 1
NULL_PLSR | Planner Senior | Labor |  |  | 1
99618-BRDA5 | BRDA5 Decant Pond | Labor |  |  | 1
SMP-Hatch | SMP-Hatch Study Manhours | Labor |  |  | 1
CIV-LOM | CIV-LOM Study Manhours | Labor |  |  | 1
C2G_B1 | C2G - Boiller Resources | Labor |  |  | 1
EIC-GRE | Electrical (GRE) | Labor |  |  | 1
Kg | Kilogram | Nonlabor |  |  | 1
m | Meter | Nonlabor |  |  | 1
No | Number | Nonlabor |  |  | 1
MEC-MEA | Mechanical (MEA) | Labor |  |  | 1
R-150 | Plant Hours | Nonlabor |  |  | 0
LAG-ENM | Lagging (Enermech) | Labor |  |  | 1
CHEM-PC | Chemical Cleaning (Process Chemicals) | Labor |  |  | 1
LABOUR NIGHT | LABOUR RESOURCES NIGHT SHIFT | Labor |  |  | 1
MEC-BMW | Boilermakers (MEA) | Labor |  |  | 1
MEC-MF | Mechanical Fitters (MEA) | Labor |  |  | 1
MEC-TA | Trade Assistants (MEA) | Labor |  |  | 1
MEC-RIG | Riggers (MEA) | Labor |  |  | 1
MEC-CW | Coded Welders (MEA) | Labor |  |  | 1
BMW N | Boilermaker Resources | Labor |  |  | 1
CW N | Coded Welder | Labor |  |  | 1
MF N | Mechanical Fitter Resources | Labor |  |  | 1
TA N | Trade Assistant Resources | Labor |  |  | 1
RIG N | Rigger Resources | Labor |  |  | 1
MEC-PT | Painters (MEA) | Labor |  |  | 1
PF N | Pipe Fitter Resources | Labor |  |  | 1
BMW N 1 | Boilermaker | Labor |  |  | 1
BMW N 2 | Boilermaker | Labor |  |  | 1
BMW N 3 | Boilermaker | Labor |  |  | 1
CW N 1 | Coded Welder | Labor |  |  | 1
CW N 2 | Coded Welder | Labor |  |  | 1
CW N 4 | Coded Welder | Labor |  |  | 1
CW N 5 | Coded Welder | Labor |  |  | 1
MF N 1 | Mechanical Fitter | Labor |  |  | 1
MF N 2 | Mechanical Fitter | Labor |  |  | 1
TA N 1 | Trade Assistant | Labor |  |  | 1
RIG N 1 | Rigger | Labor |  |  | 1
RIG N 2 | Rigger | Labor |  |  | 1
RIG N 3 | Rigger | Labor |  |  | 1
RIG N 4 | Rigger | Labor |  |  | 1
RIG N 5 | Rigger | Labor |  |  | 1
TA N 2 | Trade Assistant | Labor |  |  | 1
TA N 3 | Trade Assistant | Labor |  |  | 1
TA N 4 | Trade Assistant | Labor |  |  | 1
PF 1 | Pipe Fitter 1 | Labor |  |  | 1
PF N 1 | Pipe Fitter | Labor |  |  | 1
BMW N 4 | Boilermaker | Labor |  |  | 1
CLS | Closure Studies | Labor |  |  | 1
CLS-PSM | Proiect Services Manager | Labor |  |  | 1
CLS-PSL | Project Services Lead | Labor |  |  | 1
CLS-PCS | Project Controls Specialist | Labor |  |  | 1
CLS- PS | Planning Specialist | Labor |  |  | 1
CLS-ES | Estimating Specialist | Labor |  |  | 1
S32R-112 | Clearing & Grubbing | Material | Square Metres |  | 10
S32R-113 | Bulk Earthworks Cut/Fill | Material | Cubic Metres |  | 10
S32R-114 | Road Pavement - Subgrade prep | Material | Square Metres |  | 10
S32R-115 | Concrete | Material | Cubic Metres |  | 10
S32R-116 | Sealing | Material | Square Metres |  | 10
S32R-117 | Precast | Material | GG - units |  | 10
S32R-118 | Surface Finishing | Material | Square Metres |  | 10
S32R-119 | Drainage | Material | GG - metre (linear) |  | 10
S32R-120 | Fencing | Material | GG - metre (linear) |  | 10
S32R-121 | Topsoil Stripping | Material | Cubic Metres |  | 10
S32R-122 | Road Pavement - Subbase/Basecourse | Material | Cubic Metres |  | 10
S32R-114B | Foundation prep | Material | Square Metres |  | 10
B1-COMM | Commissioning (S32) | Labor |  |  | 1
R-15 | S-Curve | Labor |  |  | 1
S32R-90 | Earthworks & Pavement Crew | Labor |  |  | 1
S32R-91 | Drainage Crew | Labor |  |  | 1
S32R-92 | Asphalt Crew | Labor |  |  | 1
S32R-93 | Concrete Crew | Labor |  |  | 1
S32R-95 | Fencing Crew | Labor |  |  | 1
S32R-96 | W-Beam Crew | Labor |  |  | 1
S32R-97 | Services Crew | Labor |  |  | 1
S32R-99 | Painting/Linemarking Crew | Labor |  |  | 1
S32R-101 | Precast Crew | Labor |  |  | 1
S32R-103 | Project Management | Labor |  |  | 1
S32R-104 | Site Establishment/Building | Labor |  |  | 1
S32R-105 | Maintenance | Labor |  |  | 1
S32R-106 | Clearing & Stripping | Labor |  |  | 1
S32R-107 | Revetment Mattress | Labor |  |  | 1
S32R-108 | Kerbing Crew | Labor |  |  | 1
S32R-150 | Plant Hours | Nonlabor |  |  | 0
S32-2 | Excavator | Nonlabor |  |  | 1
S32-3 | Loader - Wheel Loader | Nonlabor |  |  | 1
S32-5 | Loader - Posi Track | Nonlabor |  |  | 1
S32-6 | Dump Truck/Moxy | Nonlabor |  |  | 1
S32-7 | Roller | Nonlabor |  |  | 1
S32-8 | Grader | Nonlabor |  |  | 1
S32-9 | Water Cart | Nonlabor |  |  | 1
S32-10 | Dozer | Nonlabor |  |  | 1
S32-12 | Flat Bed Truck | Nonlabor |  |  | 1
S32-13 | Crane 50T-100T | Nonlabor |  |  | 1
S32-14 | Crane >100T | Nonlabor |  |  | 1
S32-15 | Plate Compactor | Nonlabor |  |  | 1
S32-16 | Manlift | Nonlabor |  |  | 1
PC-CHEM | HydroClean (Process Chemicals) | Labor |  |  | 1
RDA1 LOM | RDA1 LOM Tailings | Labor |  |  | 1
RDA1 LOM Eng | Engineering & Design | Labor |  |  | 1
RDA1 LOM PM & Owner | PM & Owner Scope | Labor |  |  | 1
RDA1 LOM Proc | Contracts & Procurement | Labor |  |  | 1
R-18 | GEMCO Water Disposal - Direct Hours - On shore | Labor |  |  | 1
R-19 | GEMCO Water Disposal - Direct Hours - Off shore | Labor |  |  | 1
R-20 | GEMCO Water Disposal - Direct Hours - Owners Team | Labor |  |  | 1
R-21 | GEMCO Water Disposal - Direct Hours - Laydown | Labor |  |  | 1
R-4 | Indirects | Labor |  |  | 1
R-22 | Project Manager | Labor |  |  | 1
R-23 | Labour - Quality Assurance and Control Management | Labor |  |  | 1
R-24 | Labour - Engineering Management and Support | Labor |  |  | 1
R-25 | Labour - HSEC Management | Labor |  |  | 1
R-26 | Environment Engineer | Labor |  |  | 1
R-27 | Labour - Project Services | Labor |  |  | 1
R-28 | GW Study Hours | Labor |  |  | 1
TSFE6-002 | TSFE6 EXE Owners Team | Labor |  |  | 1
BOD PFS2 | BOD S32 Resources | Labor |  |  | 1
BOD Proc | M Du Toit | Labor |  |  | 1
BOD Ops Read | S Morrow | Labor |  |  | 1
HMD_CM | QTY-Cubic Metres | Material | Cubic metres (m3) |  | 8
HMD-HA | QTY-Hectare | Material | Hectare |  | 8
HMD-LM | QTY-Linear Metre | Material | Lineal Metres |  | 8
HMD-SM | QTY-Square Metre | Material | Square Metres |  | 8
HMD-EA | QTY-Each | Material | Each Unit |  | 8
HMD-T | QTY-Tons | Material | Tonne |  | 8
HMD-L | QTY-Lot | Material | Lot |  | 8
BOD Docu | M Van Wyk | Labor |  |  | 1
BOD Diesel | J Nicolaidis | Labor |  |  | 1
BOD Eng3 | T Shah | Labor |  |  | 1
BOD App2 | D Hope | Labor |  |  | 1
BOD Rev7 | F Johnston | Labor |  |  | 1
BOD Rev8 | K Drury | Labor |  |  | 1
BOD Rev10 | K Schubert | Labor |  |  | 1
IMC_MP | IMC Major Projects | Labor |  |  | 1
UPE | Unassigned Project Engineer | Labor |  |  | 1
UDR | Unassigned Draftsperson | Labor |  |  | 1
TR | Tony Ryan | Labor |  |  | 1
R-29 | Project Engineering | Labor |  |  | 1
R-30 | Mine Access | Labor |  |  | 1
SL-2 | Shaun Lafferty | Labor |  |  | 1
R-31 | Project Management | Labor |  |  | 1
BS | Ben Skerman | Labor |  |  | 1
R-32 | ESP & Third Parties | Labor |  |  | 1
R-33 | WP01D - Demand Calculation SOW | Labor |  |  | 1
R-34 | WP01D - Scoping Study Scope | Labor |  |  | 1
R-35 | S32 Global Facilities | Labor |  |  | 1
R-36 | (New Resource) | Labor |  |  | 1
R-37 | Project Controls | Labor |  |  | 1
R-38 | Davey Cawood | Labor |  |  | 1
R-39 | QRA Service Provider | Labor |  |  | 1
R-40 | WP01G ESP | Labor |  |  | 1
WPR-1 | Development | Labor |  |  | 1
WPR-2 | Roofbolts | Labor |  |  | 1
WPR-3 | Shotcrete | Labor |  |  | 1
CTG_Cost | Budgeted Cost | Nonlabor |  |  | 1
A100 | Paddington Gold | Labor |  |  | 1
LABOUR | Paddington Gold Labour Resources | Labor |  |  | 1
Electrical | Electrical & Instrumentation Installers | Labor |  |  | 1
Civilwork | Earthworks and Concreters | Labor |  |  | 1
R-8 | Electrical Installation Crew4 (4ppl) PRE-POST | Labor |  |  | 1
TSFE6 | TSFE6 | Labor |  |  | 1
02-PKG202-79100-Y172 | Owners Costs Planning & Scheduling | Labor |  |  | 1
R-41 | TSFE6 FS Engineering Deliverable Hours | Labor |  |  | 1
SCF-CORE | Scaffold (CORE) | Labor |  |  | 1
R-42 | PKG201 Contractor | Labor |  |  | 1
R-43 | PKG202 Contractor | Labor |  |  | 1
CIV-JWC | Civil (JW CROSS) | Labor |  |  | 1
NULL | NMD | Labor |  |  | 1
NUL-DI-LBR | Direct Labour - NULLAGA | Labor |  |  | 1
NUL-IN-LBR | NULLAGA - Indirect Labor | Labor |  |  | 1
NUL-CM | QTY-Cubic Metres | Material |  |  | 8
NUL-HA | QTY-Hectare | Material |  |  | 8
NUL-LM | QTY-Linear Metre | Material |  |  | 8
NUL-SM | QTY-Square Metre | Material |  |  | 8
NUL-EA | QTY-Each | Material |  |  | 8
NUL-T | QTY-Tons | Material |  |  | 8
NUL-L | QTY-Lot | Material |  |  | 8
NUL-EQ | Equipment | Nonlabor |  |  | 1
BRDA4E | BRDA 4E | Labor |  |  | 1
R-48 | Hydrotechnical Engineer | Labor |  |  | 1
R-50 | Process Engineering Lead | Labor |  |  | 1
R-51 | Process Engineer | Labor |  |  | 1
R-52 | Process Designer | Labor |  |  | 1
R-53 | Structural Engineering Lead | Labor |  |  | 1
R-54 | Structural Engineer | Labor |  |  | 1
R-55 | Structural Designer | Labor |  |  | 1
R-57 | Mechanical Engineering Lead | Labor |  |  | 1
R-58 | Mechanical Engineer | Labor |  |  | 1
R-59 | Mechanical Designer | Labor |  |  | 1
R-63 | Electrical Engineering Lead | Labor |  |  | 1
R-64 | Electrical Engineer | Labor |  |  | 1
R-65 | Electrical Designer | Labor |  |  | 1
R-66 | Control and Instrumentation Engineering Lead | Labor |  |  | 1
R-67 | Control and Instrumentation Engineer | Labor |  |  | 1
R-68 | Control and Instrumentation Designer | Labor |  |  | 1
R-73 | Environmental Lead | Labor |  |  | 1
R-74 | Environmental Engineer | Labor |  |  | 1
R-75 | Estimating Lead | Labor |  |  | 1
R-76 | Estimator | Labor |  |  | 1
R-77 | Risk SME | Labor |  |  | 1
R-78 | Construction SME | Labor |  |  | 1
R-79 | Procurement SME | Labor |  |  | 1
FW-EL | Electrician | Labor |  |  | 1
Civil Principal Engi | Civil Principal Engineer | Labor |  |  | 1
Civil Lead Engineer | Civil Lead Engineer | Labor |  |  | 1
Civil Project Engine | Civil Project Engineer Senior | Labor |  |  | 1
Civil Senior Enginee | Civil Senior Engineer | Labor |  |  | 1
Civil Experienced En | Civil Experienced Engineer | Labor |  |  | 1
Civil Project Engi-1 | Civil Project Engineer | Labor |  |  | 1
Civil Engineer | Civil Engineer | Labor |  |  | 1
Civil Graduate Engin | Civil Graduate Engineer | Labor |  |  | 1
Civil Trainee Engine | Civil Trainee Engineer | Labor |  |  | 1
Civil Principal Desi | Civil Principal Design Drafter | Labor |  |  | 1
Civil Lead Design Dr | Civil Lead Design Drafter | Labor |  |  | 1
Civil Senior Design | Civil Senior Design Drafter | Labor |  |  | 1
Civil Design Drafter | Civil Design Drafter | Labor |  |  | 1
Civil Drafter | Civil Drafter | Labor |  |  | 1
Civil Graduate Draft | Civil Graduate Drafter | Labor |  |  | 1
Consultant Principal | Consultant Principal | Labor |  |  | 1
Consultant Senior | Consultant Senior | Labor |  |  | 1
Electrical Principal | Electrical Principal Engineer | Labor |  |  | 1
Electrical Lead Engi | Electrical Lead Engineer | Labor |  |  | 1
Electrical Project E | Electrical Project Engineer Senior | Labor |  |  | 1
Electrical Senior En | Electrical Senior Engineer | Labor |  |  | 1
Electrical Experienc | Electrical Experienced Engineer | Labor |  |  | 1
Electrical Project-1 | Electrical Project Engineer | Labor |  |  | 1
Electrical Engineer | Electrical Engineer | Labor |  |  | 1
Electrical Graduate | Electrical Graduate Engineer | Labor |  |  | 1
Electrical Trainee E | Electrical Trainee Engineer | Labor |  |  | 1
Electrical Princip-1 | Electrical Principal Designer | Labor |  |  | 1
Electrical Lead Desi | Electrical Lead Design Drafter | Labor |  |  | 1
Electrical Senior De | Electrical Senior Design Drafter | Labor |  |  | 1
Electrical Design Dr | Electrical Design Drafter | Labor |  |  | 1
Electrical Drafter | Electrical Drafter | Labor |  |  | 1
Electrical Graduat-1 | Electrical Graduate Drafter | Labor |  |  | 1
I&C Principal Engine | I&C Principal Engineer | Labor |  |  | 1
I&C Lead Engineer | I&C Lead Engineer | Labor |  |  | 1
I&C Project Engineer | I&C Project Engineer Senior | Labor |  |  | 1
I&C Senior Engineer | I&C Senior Engineer | Labor |  |  | 1
I&C Experienced Engi | I&C Experienced Engineer | Labor |  |  | 1
I&C Project Engine-1 | I&C Project Engineer | Labor |  |  | 1
I&C Engineer | I&C Engineer | Labor |  |  | 1
I&C Graduate Enginee | I&C Graduate Engineer | Labor |  |  | 1
I&C Trainee Engineer | I&C Trainee Engineer | Labor |  |  | 1
I&C Principal Design | I&C Principal Designer | Labor |  |  | 1
I&C Lead Design Draf | I&C Lead Design Drafter | Labor |  |  | 1
I&C Senior Design Dr | I&C Senior Design Drafter | Labor |  |  | 1
I&C Design Drafter | I&C Design Drafter | Labor |  |  | 1
I&C Drafter | I&C Drafter | Labor |  |  | 1
I&C Graduate Drafter | I&C Graduate Drafter | Labor |  |  | 1
Mechanical Principal | Mechanical Principal Engineer | Labor |  |  | 1
Mechanical Lead Engi | Mechanical Lead Engineer | Labor |  |  | 1
Mechanical Project E | Mechanical Project Engineer Senior | Labor |  |  | 1
Mechanical Senior En | Mechanical Senior Engineer | Labor |  |  | 1
Mechanical Experienc | Mechanical Experienced Engineer | Labor |  |  | 1
Mechanical Project-1 | Mechanical Project Engineer | Labor |  |  | 1
Mechanical Engineer | Mechanical Engineer | Labor |  |  | 1
Mechanical Graduate | Mechanical Graduate Engineer | Labor |  |  | 1
Mechanical Trainee E | Mechanical Trainee Engineer | Labor |  |  | 1
Mechanical Princip-1 | Mechanical Principal Designer | Labor |  |  | 1
Mechanical Lead Desi | Mechanical Lead Design Drafter | Labor |  |  | 1
Mechanical Senior De | Mechanical Senior Design Drafter | Labor |  |  | 1
Mechanical Design Dr | Mechanical Design Drafter | Labor |  |  | 1
Mechanical Drafter | Mechanical Drafter | Labor |  |  | 1
Mechanical Graduat-1 | Mechanical Graduate Drafter | Labor |  |  | 1
Process Principal En | Process Principal Engineer | Labor |  |  | 1
Process Lead Enginee | Process Lead Engineer | Labor |  |  | 1
Process Project Engi | Process Project Engineer Senior | Labor |  |  | 1
Process Senior Engin | Process Senior Engineer | Labor |  |  | 1
Process Experienced | Process Experienced Engineer | Labor |  |  | 1
Process Project En-1 | Process Project Engineer | Labor |  |  | 1
Process Engineer | Process Engineer | Labor |  |  | 1
Process Graduate Eng | Process Graduate Engineer | Labor |  |  | 1
Process Trainee Engi | Process Trainee Engineer | Labor |  |  | 1
Project Manager Seni | Project Manager Senior | Labor |  |  | 1
Project Engineer Pri | Project Engineer Principal | Labor |  |  | 1
Project Engineer Sen | Project Engineer Senior | Labor |  |  | 1
Project Engineer Exp | Project Engineer Experienced | Labor |  |  | 1
Project Engineer | Project Engineer | Labor |  |  | 1
Project Engineer Gra | Project Engineer Graduate | Labor |  |  | 1
Site Management | Site Management | Labor |  |  | 1
Site Supervisor | Site Supervisor | Labor |  |  | 1
Project Support Offi | Project Support Officer | Labor |  |  | 1
Document Controller | Document Controller Senior | Labor |  |  | 1
Document Controlle-1 | Document Controller | Labor |  |  | 1
Document Controlle-2 | Document Controller Junior | Labor |  |  | 1
Technical Officer Pr | Technical Officer Principal | Labor |  |  | 1
Technical Officer Le | Technical Officer Lead | Labor |  |  | 1
Technical Officer Se | Technical Officer Senior | Labor |  |  | 1
Technical Officer | Technical Officer | Labor |  |  | 1
Project Controller S | Project Controller Senior | Labor |  |  | 1
Project Controller | Project Controller | Labor |  |  | 1
Project Controller J | Project Controller Junior | Labor |  |  | 1
Project Administrato | Project Administrator | Labor |  |  | 1
Civil Trainee Drafte | Civil Trainee Drafter | Labor |  |  | 1
Electrical Trainee D | Electrical Trainee Drafter | Labor |  |  | 1
I&C Trainee Drafter | I&C Trainee Drafter | Labor |  |  | 1
Mechanical Trainee D | Mechanical Trainee Drafter | Labor |  |  | 1
Consultant | Consultant | Labor |  |  | 1
Consultant Associate | Consultant Associate | Labor |  |  | 1
Software Principal E | Software Principal Engineer | Labor |  |  | 1
Software Lead Engine | Software Lead Engineer | Labor |  |  | 1
Software Project Eng | Software Project Engineer Senior | Labor |  |  | 1
Software Senior Engi | Software Senior Engineer | Labor |  |  | 1
Software Experienced | Software Experienced Engineer | Labor |  |  | 1
Software Project E-1 | Software Project Engineer | Labor |  |  | 1
Software Engineer | Software Engineer | Labor |  |  | 1
Software Graduate En | Software Graduate Engineer | Labor |  |  | 1
Software Trainee Eng | Software Trainee Engineer | Labor |  |  | 1
Software Principal D | Software Principal Designer | Labor |  |  | 1
Software Lead Design | Software Lead Design Drafter | Labor |  |  | 1
Software Senior Desi | Software Senior Design Drafter | Labor |  |  | 1
Software Design Draf | Software Design Drafter | Labor |  |  | 1
Software Drafter | Software Drafter | Labor |  |  | 1
Software Graduate Dr | Software Graduate Drafter | Labor |  |  | 1
Software Trainee Dra | Software Trainee Drafter | Labor |  |  | 1
Civil Principal En-1 | Civil Principal Engineer | Labor |  |  | 1
Civil Project Engi-2 | Civil Project Engineer Senior | Labor |  |  | 1
Civil Senior Engin-1 | Civil Senior Engineer | Labor |  |  | 1
Civil Experienced -1 | Civil Experienced Engineer | Labor |  |  | 1
Civil Project Engi-3 | Civil Project Engineer | Labor |  |  | 1
Civil Graduate Eng-1 | Civil Graduate Engineer | Labor |  |  | 1
Civil Trainee Engi-1 | Civil Trainee Engineer | Labor |  |  | 1
Civil Principal De-1 | Civil Principal Design Drafter | Labor |  |  | 1
Civil Lead Design -1 | Civil Lead Design Drafter | Labor |  |  | 1
Civil Senior Desig-1 | Civil Senior Design Drafter | Labor |  |  | 1
Civil Graduate Dra-1 | Civil Graduate Drafter | Labor |  |  | 1
Electrical Princip-2 | Electrical Principal Engineer | Labor |  |  | 1
Electrical Lead En-1 | Electrical Lead Engineer | Labor |  |  | 1
Electrical Project-2 | Electrical Project Engineer Senior | Labor |  |  | 1
Electrical Senior -1 | Electrical Senior Engineer | Labor |  |  | 1
Electrical Experie-1 | Electrical Experienced Engineer | Labor |  |  | 1
Electrical Project-3 | Electrical Project Engineer | Labor |  |  | 1
Electrical Graduat-2 | Electrical Graduate Engineer | Labor |  |  | 1
Electrical Trainee-1 | Electrical Trainee Engineer | Labor |  |  | 1
Electrical Princip-3 | Electrical Principal Designer | Labor |  |  | 1
Electrical Lead De-1 | Electrical Lead Design Drafter | Labor |  |  | 1
Electrical Senior -2 | Electrical Senior Design Drafter | Labor |  |  | 1
Electrical Design -1 | Electrical Design Drafter | Labor |  |  | 1
Electrical Graduat-3 | Electrical Graduate Drafter | Labor |  |  | 1
I&C Principal Engi-1 | I&C Principal Engineer | Labor |  |  | 1
I&C Project Engine-2 | I&C Project Engineer Senior | Labor |  |  | 1
I&C Experienced En-1 | I&C Experienced Engineer | Labor |  |  | 1
I&C Graduate Engin-1 | I&C Graduate Engineer | Labor |  |  | 1
I&C Principal Desi-1 | I&C Principal Designer | Labor |  |  | 1
I&C Lead Design Dr-1 | I&C Lead Design Drafter | Labor |  |  | 1
I&C Senior Design -1 | I&C Senior Design Drafter | Labor |  |  | 1
Mechanical Princip-2 | Mechanical Principal Engineer | Labor |  |  | 1
Mechanical Lead En-1 | Mechanical Lead Engineer | Labor |  |  | 1
Mechanical Project-2 | Mechanical Project Engineer Senior | Labor |  |  | 1
Mechanical Senior -1 | Mechanical Senior Engineer | Labor |  |  | 1
Mechanical Experie-1 | Mechanical Experienced Engineer | Labor |  |  | 1
Mechanical Project-3 | Mechanical Project Engineer | Labor |  |  | 1
Mechanical Graduat-2 | Mechanical Graduate Engineer | Labor |  |  | 1
Mechanical Trainee-1 | Mechanical Trainee Engineer | Labor |  |  | 1
Mechanical Princip-3 | Mechanical Principal Designer | Labor |  |  | 1
Mechanical Lead De-1 | Mechanical Lead Design Drafter | Labor |  |  | 1
Mechanical Senior -2 | Mechanical Senior Design Drafter | Labor |  |  | 1
Mechanical Design -1 | Mechanical Design Drafter | Labor |  |  | 1
Mechanical Graduat-3 | Mechanical Graduate Drafter | Labor |  |  | 1
Process Principal -1 | Process Principal Engineer | Labor |  |  | 1
Process Lead Engin-1 | Process Lead Engineer | Labor |  |  | 1
Process Project En-2 | Process Project Engineer Senior | Labor |  |  | 1
Process Senior Eng-1 | Process Senior Engineer | Labor |  |  | 1
Process Experience-1 | Process Experienced Engineer | Labor |  |  | 1
Process Project En-3 | Process Project Engineer | Labor |  |  | 1
Process Graduate E-1 | Process Graduate Engineer | Labor |  |  | 1
Process Trainee En-1 | Process Trainee Engineer | Labor |  |  | 1
Project Manager Se-1 | Project Manager Senior | Labor |  |  | 1
Project Engineer P-1 | Project Engineer Principal | Labor |  |  | 1
Project Engineer S-1 | Project Engineer Senior | Labor |  |  | 1
Project Engineer E-1 | Project Engineer Experienced | Labor |  |  | 1
Project Engineer G-1 | Project Engineer Graduate | Labor |  |  | 1
Project Support Of-1 | Project Support Officer | Labor |  |  | 1
Document Controlle-3 | Document Controller Senior | Labor |  |  | 1
Document Controlle-4 | Document Controller Junior | Labor |  |  | 1
Technical Officer -1 | Technical Officer Principal | Labor |  |  | 1
Technical Officer -2 | Technical Officer Lead | Labor |  |  | 1
Technical Officer -3 | Technical Officer Senior | Labor |  |  | 1
Project Controller-1 | Project Controller Senior | Labor |  |  | 1
Project Controller-2 | Project Controller Junior | Labor |  |  | 1
Project Administra-1 | Project Administrator | Labor |  |  | 1
Civil Trainee Draf-1 | Civil Trainee Drafter | Labor |  |  | 1
Electrical Trainee-2 | Electrical Trainee Drafter | Labor |  |  | 1
Mechanical Trainee-2 | Mechanical Trainee Drafter | Labor |  |  | 1
Software Principal-1 | Software Principal Engineer | Labor |  |  | 1
Software Lead Engi-1 | Software Lead Engineer | Labor |  |  | 1
Software Project E-2 | Software Project Engineer Senior | Labor |  |  | 1
Software Senior En-1 | Software Senior Engineer | Labor |  |  | 1
Software Experienc-1 | Software Experienced Engineer | Labor |  |  | 1
Software Project E-3 | Software Project Engineer | Labor |  |  | 1
Software Graduate -1 | Software Graduate Engineer | Labor |  |  | 1
Software Trainee E-1 | Software Trainee Engineer | Labor |  |  | 1
Software Principal-2 | Software Principal Designer | Labor |  |  | 1
Software Lead Desi-1 | Software Lead Design Drafter | Labor |  |  | 1
Software Senior De-1 | Software Senior Design Drafter | Labor |  |  | 1
Software Design Dr-1 | Software Design Drafter | Labor |  |  | 1
Software Graduate -2 | Software Graduate Drafter | Labor |  |  | 1
Software Trainee D-1 | Software Trainee Drafter | Labor |  |  | 1
FW-PM | Project Manager | Labor |  |  | 1
FW-EN | Engineer | Labor |  |  | 1
R-45 | (New Resource) | Labor |  |  | 1
FW-PL | Plumber | Labor |  |  | 1
FW-OWEN | Owner Engineer | Labor |  |  | 1
FW-PU | Purchaser | Labor |  |  | 1
FW-CF | Ceiling Framer | Labor |  |  | 1
FW-CFX | Ceiling Fixer | Labor |  |  | 1
FW-TI | Tiler | Labor |  |  | 1
FW-PA | Painter | Labor |  |  | 1
FW-HVAC | HVAC Technician | Labor |  |  | 1
FW-CA | Carpenter | Labor |  |  | 1
FW-CAR | Carpet Installer | Labor |  |  | 1
FW-PLA | Plasterer | Labor |  |  | 1
FW-GAR | Gardener | Labor |  |  | 1
FW-MAS | Mason | Labor |  |  | 1
FW-FE | Fencing Contractor | Labor |  |  | 1
FW-LAB | Labourer | Labor |  |  | 1
CIV-SRG | Mech (SRG) | Labor |  |  | 1
THER | Thermal Systems | Labor |  |  | 1
99712_CTG_B2 | 99712_CTG_B2 | Labor |  |  | 1
B2_FS_LABOUR | 99712_Labour | Labor |  |  | 1
B2_ENG | 99712_Engineering Support Labour | Labor |  |  | 1
B2_CAR | 99712_Carnac (Process/Mechanical) | Labor |  |  | 1
B2_ESP | 99712_Worley (Electrical/Instrumentation) | Labor |  |  | 1
B2_COSTS | 99712_Costs | Nonlabor |  |  | 1
B2_LAB_C | 99712_Labour Costs | Nonlabor |  |  | 1
B2_PROC_C | 99712_Procurement Costs | Nonlabor |  |  | 1
B2_OWN | Boiler - S32 Owners Team Labour | Labor |  |  | 1
CASS Project | CASS Project | Labor |  |  | 1
CASS_ESP | ESP Engineering | Labor |  |  | 1
CASS_S32 | S32 Owner's Team | Labor |  |  | 1
12624084 | GEMCO Excess Water Disposal Resources | Labor |  |  | 1
GEMCO-B | GEMCO Budget | Nonlabor |  |  | 1
CASS E&A | Environmental & Approval Consultant | Labor |  |  | 1
CASS Early Eng | Early Engineering | Labor |  |  | 1
BOD ESP | ESP Direct hours | Labor |  |  | 1
Q_CADMIN | Contract Admin | Labor |  |  | 1
Q_ENGST | Engineer Structural | Labor |  |  | 1
Q_ENGME | Engineer Mechanical | Labor |  |  | 1
Q_DESST | Designer Structural | Labor |  |  | 1
Q_DESME | Designer Mechanical | Labor |  |  | 1
Q_DESEL | Designer Electrical | Labor |  |  | 1
Studies Specialist | Studies Specialist | Labor |  |  | 1
Manager Planning | Manager Planning | Labor |  |  | 1
Environmental Specia | Environmental Specialist | Labor |  |  | 1
Marketing S | Marketing S | Labor |  |  | 1
Marketing Specialist | Marketing Specialist | Labor |  |  | 1
Port Logistic Specia | Port Logistic Specialist | Labor |  |  | 1
Land Tenure Speciali | Land Tenure Specialist | Labor |  |  | 1
Supply Specialist | Supply Specialist | Labor |  |  | 1
Laboratory Specialis | Laboratory Specialist | Labor |  |  | 1
Senior Geologist | Senior Geologist | Labor |  |  | 1
Transhipping Contrac | Transhipping Contractor | Labor |  |  | 1
Contractor Managemen | Contractor Management Specialist | Labor |  |  | 1
Port Administrator | Port Administrator | Labor |  |  | 1
Pilot | Pilot | Labor |  |  | 1
Master Data Speciali | Master Data Specialist | Labor |  |  | 1
Port Projects Team | Port Projects Team | Labor |  |  | 1
Electrical Contracto | Electrical Contractor | Labor |  |  | 1
Earthworks Contracto | Earthworks Contractor | Labor |  |  | 1
Pipeline Contractor | Pipeline Contractor | Labor |  |  | 1
Cane Toad Fence Cont | Cane Toad Fence Contractor | Labor |  |  | 1
Port Projects Engine | Port Projects Engineer | Labor |  |  | 1
Civil Enginer | Civil Enginer | Labor |  |  | 1
Construction Contrac | Construction Contractor | Labor |  |  | 1
S32-BRDA5 | S32 BRDA5 Manhours | Labor |  |  | 1
AMPGARD | AMPGARD | Labor |  |  | 1
AMP_ABB | AMPGARD ABB | Labor |  |  | 1
AMP_SET | AMPGARD Supersett | Labor |  |  | 4
AMP_JWC | AMPGARD JW Cross | Labor |  |  | 4
AMP_GRE | AMPGARD GRE On-Site Normal | Labor |  |  | 4
AMP_LGM | AMPGARD LGM | Labor |  |  | 1
AMP_ENG1 | AMPGARD Electrical Engineer 1 - Rudi | Labor |  |  | 1
AMP_GRE_SHUT_DAY | AMPGARD GRE Shutdown Day | Labor |  |  | 4
AMP_GRE_SHUT_NIGHT | AMPGARD GRE Shutdown Night | Labor |  |  | 4
99628-Reclaimers 1&2 | Reclaimers 1 & 2 | Labor |  |  | 1
99628-FS-204 | OEM Contractor | Labor |  |  | 1
E&C Resources | E&C Resources | Labor |  |  | 1
SEE-1 | Flinders Trunk Road | Labor |  |  | 1
FRP | Concrete Contractors | Labor |  |  | 1
FRPculvert | FRP Culvert Crew | Labor |  |  | 5
EoL | ESP EoL | Labor |  |  | 1
South32- FS2 | FS2 Resources | Labor |  |  | 1
FS2-Qa | Quality Lead | Labor |  |  | 1
FS2-PAT Lead | PAT Lead | Labor |  |  | 1
FS2-EM | Engineering Manager | Labor |  |  | 1
FS2-PI Eng | PIping Eng | Labor |  |  | 1
FS2-PROC Lead | Procurement lead | Labor |  |  | 1
FS2-HSE | Heath & Safety Lead | Labor |  |  | 1
FS2-Mech Lead | Mechanical Lead | Labor |  |  | 1
FS2-PC Lead | Project Controls Lead | Labor |  |  | 1
FS2-PE | Project Engineer | Labor |  |  | 1
FS2-STR Lead | Structural Lead | Labor |  |  | 1
FS2-Pi Lead | Piping Lead | Labor |  |  | 1
FS2-Cont Adm | Contract Admin | Labor |  |  | 1
FS2-FE | Field Engineer | Labor |  |  | 1
FS2-PR DSGR | Process Dsgr | Labor |  |  | 1
FS2-CM | Construction Manager | Labor |  |  | 1
FS2-DC | Document Controller | Labor |  |  | 1
FS2-EL Lead | Elect Lead | Labor |  |  | 1
FS2-Exp Lead | Expediting Lead | Labor |  |  | 1
FS2-Mat Coor | Materials Coordinator | Labor |  |  | 1
FS2-Op Coor | Operational Coordinator | Labor |  |  | 1
FS2-Mech Eng | Mech Eng | Labor |  |  | 1
FS2-STR Eng | Structural Eng | Labor |  |  | 1
FS2-EL Dsgr | Elect Dsgr | Labor |  |  | 1
FS2-Civ Eng | Civil Eng | Labor |  |  | 1
FS2-Hydro Lead | Hydrotechnical Lead | Labor |  |  | 1
FS2-Hydro Eng | Hydrotechnical Eng | Labor |  |  | 1
FS2-Comm Lead | Commissioning & OR Lead | Labor |  |  | 1
FS2-Est Lead | Estimation Lead | Labor |  |  | 1
FS2-IC Lead | I&C Lead | Labor |  |  | 1
FS2-VQS | Vendor Quality Surveillance | Labor |  |  | 1
FS2-PC | Project Controls | Labor |  |  | 1
FS2-Est | Estimator | Labor |  |  | 1
FS2-PI Dsgr | PIping Dsgr | Labor |  |  | 1
FS2-STR Dsgr | Structural Dsgr | Labor |  |  | 1
FS2-IC Eng | I&C Eng | Labor |  |  | 1
FS2-Civ Dsgr | Civil Dsgr | Labor |  |  | 1
FS2-PAT | PAT Support | Labor |  |  | 1
FS2-PM | Project Manager | Labor |  |  | 1
FS2-Risk | Risk Specialist | Labor |  |  | 1
FS2-PR Lead | Process Lead | Labor |  |  | 1
FS2-CIV Lead | Civil Lead | Labor |  |  | 1
FS2-Cont Lead | Contract Lead | Labor |  |  | 1
FS2-Planner | Project Planner | Labor |  |  | 1
FS2-PR ENG | Process Eng | Labor |  |  | 1
FS2-Mech Dsgr | Mech Dsgr | Labor |  |  | 1
FS2-EL ENG | Elect Eng | Labor |  |  | 1
FS2-IC Dsgr | I&C Dsgr | Labor |  |  | 1
FS2-Geo Lead | Geotech Lead | Labor |  |  | 1
FS2-Geo Eng | Geotech Eng | Labor |  |  | 1
FS2-Exp | Expediting | Labor |  |  | 1
Jason F | Jason F | Labor |  |  | 1
Matt L | Matt L | Labor |  |  | 1
Aurecon | Aurecon | Labor |  |  | 1
Mike C | Mike C | Labor |  |  | 1
Ben M | Ben M | Labor |  |  | 1
S32 Finance | S32 Finance | Labor |  |  | 1
St john | St john | Labor |  |  | 1
S McSwiney | S McSwiney | Labor |  |  | 1
David S | David S | Labor |  |  | 1
VPP | VPP | Labor |  |  | 1
PO | PO | Labor |  |  | 1
VPO | VPO | Labor |  |  | 1
Assurance | Assurance | Labor |  |  | 1
COO | COO | Labor |  |  | 1
COSec | COSec | Labor |  |  | 1
Arup | Arup | Labor |  |  | 1
R-8-1 | Truck Tip Structural | Material | Tonnes |  | 12
Corporate | Corporate Resources | Labor |  |  | 1
Trades | Trades | Labor |  |  | 1
Management | Management | Labor |  |  | 1
Operations | Process Operations | Labor |  |  | 1
SEEGROUP | SEE GROUP TRADES | Labor |  |  | 1
SteelF | Steel Fixer | Labor |  |  | 1
CR250 | 250T Crawler Crane | Nonlabor |  |  | 1
GHD-Mhrs | GHD HON Manhours | Labor |  |  | 1
WOR | Worsley Contractors | Labor |  |  | 1
WOR_SUR | Worsley-Survey (Thompsons) | Labor |  |  | 1
WOR_JMD | Worsley-Scanning (JMD) | Labor |  |  | 1
WOR_CAB | Worsley-Scanning (Cable Locates) | Labor |  |  | 1
WOR_CIV | Worsley-Civil (JW Cross) | Labor |  |  | 1
WOR_MEC | Worsley-Mechanical (MEA) | Labor |  |  | 1
WOR_EIC | Worsley-Electrical (GRE) | Labor |  |  | 1
WOR-DEM | Worsley-Demolition (Focus) | Labor |  |  | 1
WOR_SRG | Worsley-Scaffold (SRG) | Labor |  |  | 1
WOR_COR | Worsley-Scaffold (CORE) | Labor |  |  | 1
6154-SFB | 6154-Santafe Jack Up Barge(JUB) | Nonlabor |  |  | 1
6154-FCB | 6154-Floating Crane Barge (FCB) | Nonlabor |  |  | 1
6154 | 6154-Groote Eylandt Project | Labor |  |  | 1
6154-P | 6154-Plant and Equipment (Groote Eylandt) | Nonlabor |  |  | 1
6154-JUB | 6154-Santafe Jack Up Barge(JUB) | Nonlabor |  |  | 1
6154-FCB-1 | 6154-Floating Crane Barge (FCB #1) | Nonlabor |  |  | 1
6154-FCB-2 | 6154-Floating Crane Barge (FCB #2) | Nonlabor |  |  | 1
S32-C&E | S32 Civils and Earthworks | Labor |  |  | 2
S32-SMP | S32 Structural Mechanical and Piping | Labor |  |  | 1
S32-CON | S32 Concrete | Labor |  |  | 1
S32-EI&C | S32 EI&C | Labor |  |  | 1
Lab | Labourer | Labor |  |  | 1
S32-HON EXE | S32 HON Execution Manhours | Labor |  |  | 1
R-47 | Grading Crew A (2) | Labor |  |  | 1
R-49 | Topsoil Crew B (5) | Labor |  |  | 1
R-56 | Clearing Crew A (5) | Labor |  |  | 1
R-60 | Clearing Crew B (5) | Labor |  |  | 1
R-61 | Topsoil Crew A (5) | Labor |  |  | 1
R-62 | Grading Crew B (2) | Labor |  |  | 1
R-69 | S32 Owners Team | Labor |  |  | 1
R-70 | Contractor Indirects (Earthworks & Civils) | Labor |  |  | 1
R-71 | Visitors/Specialsit/Contingency | Labor |  |  | 1
R-72 | Piling Crew (Bridge) (12) | Labor |  |  | 1
R-80 | Structural Crews (Bridge) (35persons) | Labor |  |  | 1
R-81 | Contractor Indirects (Bridge) | Labor |  |  | 1
R-82 | Girder Assembly And Install Crews (10persons) | Labor |  |  | 1
FIP-DPS CTR1 | FIP DPS Labor Resourses Reforecast | Labor |  |  | 1
P013¦8.5 | Supporting Project Controller | Labor |  |  | 1
FS2-PKG | PKG ENG | Labor |  |  | 1
FS2 Resources Hatch | PM Support | Labor |  |  | 1
FS2-DM | Document Management | Labor |  |  | 1
R-83 | NPI - Fuel Facility Crew | Labor |  |  | 1
R-84 | NPI - Northern StandPipe Facility Crews | Labor |  |  | 1
R-85 | NPI - Office Area Crews | Labor |  |  | 1
R-86 | Fibre Crew | Labor |  |  | 1
R-87 | LTE Tower Crew | Labor |  |  | 1
R-88 | Nullaga - EarthWorks & Civil Crews | Labor |  |  | 1
R-98 | Nullaga TREE HARVESTING | Labor |  |  | 1
R-100 | Water (Litres) | Nonlabor |  |  | 1
240610 S32 Nullaga | 240610 S32 Nullaga | Labor |  |  | 1
NUL-C&G | Clearing & Grubbing | Material | Square Metres |  | 11
NUL-TS | Topsoil Strip | Material | Cubic Metres |  | 11
NUL-SUB C&S | Crushing & Screening Subcontractor | Labor |  |  | 1
NUL-QBOP | QB Operator | Labor |  |  | 1
NUL-SUB BRDG | Bridge Subcontractor | Labor |  |  | 1
NUL-SUB CSP | CSP Subcontractor | Labor |  |  | 1
NUL-CSP | CSP Culvert | Material | Lineal Metres |  | 11
NUL-RCBC | RCBC Culvert Underpass | Material | Lineal Metres |  | 11
NUL-RP | Rock Protection | Material | Cubic Metres |  | 11
NUL-GF | General Fill | Material | Cubic Metres |  | 11
NUL-BC | Base Course | Material | Cubic Metres |  | 11
NUL-WC | Wearing Course | Material | Cubic Metres |  | 11
NUL-GST | Ground Surface Treatment | Material | Square Metres |  | 11
NUL-SG TRIM | Subgrade Trim | Material | Square Metres |  | 11
NUL-BROCK | Blast Rock | Material | Cubic Metres |  | 11
NUL-WC TRIM | Wearing Course Trim | Material | Square Metres |  | 11
NUL-SUB D&B | Drill & Blast Subcontractor | Labor |  |  | 1
NUL-D&B | Drill & Blast | Material | Cubic Metres |  | 11
NUL-SUB RCBC | RCBC Subcontractor | Labor |  |  | 1
AMP_ABB_SHUT_DAY | AMPGARD ABB Shutdown Day | Labor |  |  | 1
AMP_ABB_SHUT_NIGHT | AMPGARD ABB Shutdown Night | Labor |  |  | 1
CR100T | 100T Crane | Nonlabor |  |  | 1
CR280T | 280T Crane | Nonlabor |  |  | 1
CR250T | 250T Crane | Nonlabor |  |  | 1
REMMhrs | Remaining PFS Mhrs | Labor |  |  | 1
NRRes | Northern Region Project Resources | Labor |  |  | 1
6154 -01- Sta Fe JUB | 01-1 - SantaFe - JUB | Nonlabor |  |  | 1
6154 -03 - JUB/Sealift#2 | 03-1 - JUB/ Sealift EWP | Nonlabor |  |  | 1
6154 -06 - HLV#1 | 06 - HLV | Nonlabor |  |  | 1
6154 -04 - JUB 2 | 04 - JUB 2 | Nonlabor |  |  | 1
6154 -07 - MEP | 07 - MEP | Nonlabor |  |  | 1
6154 -08 - COM | 09 - Commissioning | Nonlabor |  |  | 1
MCD | McCONNEL DOWELL | Nonlabor |  |  | 1
AUSMCD | AUSTRALIA | Labor |  |  | 1
6154 - Groote Eylandt | Groote Eylandt Wharf Remediation Project (LIVE) | Nonlabor |  |  | 1
NUL-STUDY | Study Resource | Labor |  |  | 1
R-102 | Study - S32 | Labor |  |  | 1
R-109 | Study - ESP | Labor |  |  | 1
WOR_FF | Worsley-Specialist (FUELFIX) | Labor |  |  | 1
WOR_CLN | Worsley-Cleanup (Cleanaway) | Labor |  |  | 1
WOR_3DS | Worsley-Scanning (3-D) | Labor |  |  | 1
BOD D | FAC110 Diesel Modification | Labor |  |  | 1
TEAM_A | Team A Resources | Labor |  |  | 1
TEAM_B | Team B Resources | Labor |  |  | 1
FLOAT-1 | Float Resources | Labor |  |  | 1
CW-A1 | Coded Welder 1 | Labor |  |  | 1
CW-B1 | Coded Welder 1 | Labor |  |  | 1
CW-B2 | Coded Welder 2 | Labor |  |  | 1
BMW-A1 | BMW 1 | Labor |  |  | 1
BMW-A2 | BMW 2 | Labor |  |  | 1
BMW-B1 | BMW 1 | Labor |  |  | 1
TA-A1 | Trade Assistant 1 | Labor |  |  | 1
TA-B1 | Trade Assistant 1 | Labor |  |  | 1
BLAST | Blaster / Painter | Labor |  |  | 1
RIG-1 | Rigger 1 | Labor |  |  | 1
RIG-2 | Rigger 2 | Labor |  |  | 1
CRANE-3 | Crane Operator | Labor |  |  | 1
SCAF | Core Scaffolding | Nonlabor |  |  | 1
CORE DRILL | Third Party | Nonlabor |  |  | 1
CASS_S32 Eng | S32 Owner Engineering | Labor |  |  | 1
R-110 | Mike | Labor |  |  | 1
R-123 | Venkatesh | Labor |  |  | 1
R-124 | Nick | Labor |  |  | 1
R-125 | Tejas | Labor |  |  | 1
MACMAHON | Macmahon Resources | Labor |  |  | 1
Overheads | Overhead Resourcing | Labor |  |  | 1
DT_777 | Dump Truck -777 | Nonlabor |  |  | 3
EX_30t | Excavator-30t | Nonlabor |  |  | 1
DZ_D10 | Dozer-D10 | Nonlabor |  |  | 1
LD_980 | Loader-980 | Nonlabor |  |  | 1
RL_SD18t | Roller-SD18t | Nonlabor |  |  | 1
WC_Body | Water Cart-Body | Nonlabor |  |  | 1
GR_16M | Grader-16M | Nonlabor |  |  | 1
GR_14M | Grader-14M | Nonlabor |  |  | 1
WC_740 | Water Cart-740 | Nonlabor |  |  | 1
Fill Materials | Embankment Fill Materials | Material |  |  | 2500
EX_120t | Excavator-120t | Nonlabor |  |  | 1
Plant Resource | Plant Resources | Nonlabor |  |  | 1
CM_825 | Compactor 825 | Nonlabor |  |  | 1
CM_815 | Compactor 815 | Nonlabor |  |  | 1
Survey | Survey | Labor |  |  | 1
HSE | HSE | Labor |  |  | 1
PCO | Project Controls | Labor |  |  | 1
SP | Supervision | Labor |  |  | 1
Con | Construction Managemenr | Labor |  |  | 1
Corp | Corporate Senior Management | Labor |  |  | 1
GF | General Fill | Material | Cubic Metres |  | 2500
x_Lab | x_Lab | Labor |  |  | 10
x_ProjectMaintenance | x_ProjectMaintenance | Labor |  |  | 1
WC | Wearing Course | Material | Cubic Metres |  | 1800
RL_SD | RL_SD | Nonlabor |  |  | 1
SCR_631 | SCR_631 | Nonlabor |  |  | 4
SPE | Senior Project Engineer | Labor |  |  | 1
CM | Construction Manager | Labor |  |  | 1
SE | Site Engineer | Labor |  |  | 1
SI | Superintendent | Labor |  |  | 1
QA | QA Engineer | Labor |  |  | 1
OPM | Operations Manager | Labor |  |  | 1
EA | Enviromental Advisor | Labor |  |  | 1
PCM | Project Controls Manager | Labor |  |  | 1
SFA | Safety Advisor | Labor |  |  | 1
HSEQ | HSEQ Manager | Labor |  |  | 1
SV | Surveyor | Labor |  |  | 1
CNM | Contract Administrator | Labor |  |  | 1
SF | Supervisor / Foreman | Labor |  |  | 1
BC | Basecourse | Material | Cubic Metres |  | 2500
RK | Rock | Material | Cubic Metres |  | 2500
TS | Topsoil | Material | Cubic Metres |  | 2500
CG | Clear and Grub | Material | Cubic Metres |  | 2500
PR_001 | Piling Rig | Nonlabor |  |  | 1
CR_750 | 750T Crane | Nonlabor |  |  | 1
SC | Subcontractor | Nonlabor |  |  | 5
GR | Gravel | Material | Cubic Metres |  | 2500
CR_150 | 150T Crane | Nonlabor |  |  | 1
6154-Crew1 | SantaFe Crew | Labor |  |  | 1
6154-Crew2 | Pauline Crew | Labor |  |  | 1
6154-Crew 3 | Welding Crew | Labor |  |  | 1
6154-Crew 4 | Painting Crew | Labor |  |  | 1
6154-Crew 5 | Plank Crew | Labor |  |  | 1
6154-Crew 6 | Electrical Crew | Labor |  |  | 1
6154-Crew 7 | Mechanical Crew | Labor |  |  | 1
6154-Crew 8 | Dive Crew | Labor |  |  | 1
6154-Crew 9 | Scaffold Crew | Labor |  |  | 1
6154-Crew 10 | Yard Crew | Labor |  |  | 1
6154-Crew 11 | Mildred Tug Crew | Labor |  |  | 1
6154-Crew 12 | Laurie M Crew | Labor |  |  | 1
6154-Crew 14 | 250T Crane Barge Crew | Labor |  |  | 1
6154-Crew 15 | GEMCO Projects TA | Labor |  |  | 1
6154-Crew16 | Demolition S/c Liberty Crew | Labor |  |  | 1
6154-Crew1.1 | GEMCO Projects - Boiler Maker | Labor |  |  | 8
6154-Crew 4.1 | GEMCO Projects - Painting - Painter #1 | Labor |  |  | 1
6154-Crew 5.1 | GEMCO Projects - Rigger #1 | Labor |  |  | 1
6154-Crew 8.1-1 | GEMCO Projects Scaffold crew | Labor |  |  | 1
83 M | Mechanical Engineer | Labor |  |  | 1
84 S | Structural Engineer | Labor |  |  | 1
85 D | Draughtsman - SMP | Labor |  |  | 1
86 C | Civil Engineer | Labor |  |  | 1
87 P | Project Manager | Labor |  |  | 1
88 P | Project Engineer | Labor |  |  | 1
89 D | Document Controller | Labor |  |  | 1
90 C | Client | Labor |  |  | 1
91 S | Simulation Consultant | Labor |  |  | 1
92 D | Draughtsman - Civil | Labor |  |  | 1
93 F | Fire Consultant | Labor |  |  | 1
94 P | Process Engineer | Labor |  |  | 1
95 P | Planner | Labor |  |  | 1
96 C | Client Project Team | Labor |  |  | 1
97 P | Project Engineer - LSL | Labor |  |  | 1
98 M | Mechanical Engineer - LSL | Labor |  |  | 1
99 D | Draughtsman - SMPP - LSL | Labor |  |  | 1
100 D | Document Controller -LSL | Labor |  |  | 1
101 E | EC&I Engineer - LSL | Labor |  |  | 1
102 S | Structural Engineer - LSL | Labor |  |  | 1
103 C | Civil Engineer - LSL | Labor |  |  | 1
104 Q | QS - LSL | Labor |  |  | 1
105 D | Draughtsman - Civil - LSL | Labor |  |  | 1
106 D | Draughtsman - EC&I - LSL | Labor |  |  | 1
107 S | Simulation Consultant - LSL | Labor |  |  | 1
108 P | Planner - LSL | Labor |  |  | 1
109 D | Drawing Office Manager - LSL | Labor |  |  | 1
110 L | Luke | Labor |  |  | 1
111 A | Alfred | Labor |  |  | 1
112 L | Llewellyn | Labor |  |  | 1
113 L | Lynette | Labor |  |  | 1
114 N | N/A | Labor |  |  | 1
115 L | Lynette + Luke | Labor |  |  | 1
116 M | Mel | Labor |  |  | 1
117 B | Barry | Labor |  |  | 1
118 T | Tebogo | Labor |  |  | 1
119 S | Sphamandla | Labor |  |  | 1
120 H | HMM BI & AI | Labor |  |  | 1
121 T | Tania | Labor |  |  | 1
122 W | Wonder | Labor |  |  | 1
123 S | Smith | Labor |  |  | 1
124 L | Llewellyn Jenner | Labor |  |  | 1
125 D | Dave Spurges | Labor |  |  | 1
126 S | Sphamandla Nkomo | Labor |  |  | 1
127 E | Erin Gilfillan | Labor |  |  | 1
128 B | BB | Labor |  |  | 1
129 Q | Quentin Berrange | Labor |  |  | 1
130 T | Tebogo Motlhamme | Labor |  |  | 1
131 Q | QD | Labor |  |  | 1
132 T | TB | Labor |  |  | 1
Structural Engineer | Structural Engineer | Labor |  |  | 1
Draughtsman - SMP | Draughtsman - SMP | Labor |  |  | 1
Client | Client | Labor |  |  | 1
Simulation Consultan | Simulation Consultant | Labor |  |  | 1
Draughtsman - Civil | Draughtsman - Civil | Labor |  |  | 1
Fire Consultant | Fire Consultant | Labor |  |  | 1
Planner | Planner | Labor |  |  | 1
Client Project Team | Client Project Team | Labor |  |  | 1
Project Engineer - L | Project Engineer - LSL | Labor |  |  | 1
Draughtsman - SMPP - | Draughtsman - SMPP - LSL | Labor |  |  | 1
EC&I Engineer - LSL | EC&I Engineer - LSL | Labor |  |  | 1
Civil Engineer - LSL | Civil Engineer - LSL | Labor |  |  | 1
QS - LSL | QS - LSL | Labor |  |  | 1
Draughtsman - EC&I - | Draughtsman - EC&I - LSL | Labor |  |  | 1
Planner - LSL | Planner - LSL | Labor |  |  | 1
Drawing Office Manag | Drawing Office Manager - LSL | Labor |  |  | 1
Luke | Luke | Labor |  |  | 1
Alfred | Alfred | Labor |  |  | 1
Llewellyn | Llewellyn | Labor |  |  | 1
Lynette | Lynette | Labor |  |  | 1
N/A | N/A | Labor |  |  | 1
Lynette + Luke | Lynette + Luke | Labor |  |  | 1
Mel | Mel | Labor |  |  | 1
Barry | Barry | Labor |  |  | 1
Tebogo | Tebogo | Labor |  |  | 1
Sphamandla | Sphamandla | Labor |  |  | 1
HMM BI & AI | HMM BI & AI | Labor |  |  | 1
Tania | Tania | Labor |  |  | 1
Wonder | Wonder | Labor |  |  | 1
Smith | Smith | Labor |  |  | 1
Llewellyn Jenner | Llewellyn Jenner | Labor |  |  | 1
Dave Spurges | Dave Spurges | Labor |  |  | 1
Sphamandla Nkomo | Sphamandla Nkomo | Labor |  |  | 1
Erin Gilfillan | Erin Gilfillan | Labor |  |  | 1
BB | BB | Labor |  |  | 1
Quentin Berrange | Quentin Berrange | Labor |  |  | 1
Tebogo Motlhamme | Tebogo Motlhamme | Labor |  |  | 1
QD | QD | Labor |  |  | 1
TB | TB | Labor |  |  | 1
6154-Demo-Steel | Wharf - Demolition - Steel Tons | Material |  |  | 8
R-126 | Wharf - Demolition Steel tons | Material |  |  | 8
R-127 | Wharf Installation Steel tons | Material |  |  | 8
R-128 | Wharf - Piles | Material |  |  | 8
HMM Concentrate | Ukwazi Resource | Labor |  |  | 1
ESP-Ukwazi | Ukwazi Resource | Labor |  |  | 1
S32-HMM | S32 Owners Team | Labor |  |  | 1
6154-Demo1 | Demolition - Steel | Material | Tonnes of Steel |  | 8
6154-Demo2 | Demolition - Concrete | Material | Tonne |  | 20
6154-Pile | Pile Driving | Material | Each Unit |  | 8
Liebenberg; Tania | Liebenberg; Tania | Labor |  |  | 1
Sigwebela; Wonder | Sigwebela; Wonder | Labor |  |  | 1
April; Alfred | April; Alfred | Labor |  |  | 1
Jenner; Llewellyn (S | Jenner; Llewellyn (Synntech) | Labor |  |  | 1
Ndebele; Vanessa | Ndebele; Vanessa | Labor |  |  | 1
Ngoepe; Thapelo | Ngoepe; Thapelo | Labor |  |  | 1
Smith; Vanessa | Smith; Vanessa | Labor |  |  | 1
Booysen; Jolene | Booysen; Jolene | Labor |  |  | 1
Mooketsi; Keobakile | Mooketsi; Keobakile | Labor |  |  | 1
SLR - Karin | SLR - Karin | Labor |  |  | 1
SLR - Tash | SLR - Tash | Labor |  |  | 1
SLR Edwynn | SLR Edwynn | Labor |  |  | 1
GHT | GHT | Labor |  |  | 1
DWS | DWS | Labor |  |  | 1
SLR - Piet | SLR - Piet | Labor |  |  | 1
Landman; Fanie | Landman; Fanie | Labor |  |  | 1
Sisa | Sisa | Labor |  |  | 1
AMP_HV_DAY | AMPGARD HV Switching Team Day | Labor |  |  | 2
AMP_HV_NIGHT | AMPGARD HV Switching Team Night | Labor |  |  | 2
LVL Direct | Level - Direct Manhours | Labor |  |  | 1
LVL Indirect | Level - Indirect Manhours | Labor |  |  | 1
LVL Direct Reduced | Level - Direct Manhours Reduced | Labor |  |  | 1
LVL Indirect Reduced | Level - Indirect Manhours Reduced | Labor |  |  | 1
Top Cut Project (TC) | TC Project | Labor |  |  | 1
TC S32 Owner | TC S32 Owners | Labor |  |  | 1
R-44 | (New Resource) | Labor |  |  | 1
99628-FS-205 | Engineering Support | Labor |  |  | 1
99628-FS-206 | OEM Design Audit | Labor |  |  | 1
PFS-ESP-2 | Tie-in Engineering - ESP Manhours | Labor |  |  | 1
Ukwazi Resource | Ukwazi Resource | Labor |  |  | 1
Ukwazi Resource-1 | Ukwazi Resource | Labor |  |  | 1
S32 Owners Team | S32 Owners Team | Labor |  |  | 1
Ukwazi Resource-2 | Ukwazi Resource | Labor |  |  | 1
Supplier | Supplier | Labor |  |  | 1
R-46 | (New Resource) | Labor |  |  | 1
R-129 | WHARF Top Structure welding and install Hours | Labor |  |  | 1
R-130 | WHARF M&E Commissioning Hours | Labor |  |  | 1
R-131 | WHARF HOURS | Labor |  |  | 1
WOR_FRC | Worsley - Fatal Risk Controls | Nonlabor |  |  | 0
FRC001 | ARC Flash | Nonlabor |  |  | 0
FRC002 | Confined Space | Nonlabor |  |  | 0
FRC003 | Dropped Objects | Nonlabor |  |  | 0
FRC004 | Electrocution | Nonlabor |  |  | 0
FRC005 | Entanglement | Nonlabor |  |  | 0
FRC006 | Movement of Ground | Nonlabor |  |  | 0
FRC007 | Hazardous Energy | Nonlabor |  |  | 0
FRC009 | Vehicle Interactions | Nonlabor |  |  | 0
FRC010 | Lifting Operations | Nonlabor |  |  | 0
FRC011 | Fall From Height | Nonlabor |  |  | 0
PEGGY | Store/Peggy | Labor |  |  | 1
R-132 | Piling Hours | Labor |  |  | 1
R-133 | Welding Hours | Labor |  |  | 1
R-134 | M&E Install and Commissioning Hours | Labor |  |  | 1
BOD ECI | BOD ECI | Labor |  |  | 1
MELCHOR | MELCHOR RESOURCE POOL | Labor |  |  | 1
T5 | TEAM 5 | Labor |  |  | 1
T3 | TEAM 3 | Labor |  |  | 1
T4 | TEAM 4 | Labor |  |  | 1
2. CON-TEN-OPEN | Tender Project Resources | Nonlabor |  |  | 1
CODE01 | CODED WELDER | Labor |  |  | 1
BMW01 | BMW | Labor |  |  | 1
MECH01 | MECHANICAL FITTER | Labor |  |  | 1
RIG01 | ADVANCED RIGGER | Labor |  |  | 1
TA01 | TRADE ASSISTANT | Labor |  |  | 1
SCAF01 | ADVANCED SCAFFOLDER | Labor |  |  | 1
CODE02 | CODED WELDER | Labor |  |  | 1
BMW02 | BMW | Labor |  |  | 1
MECH02 | MECHANICAL FITTER | Labor |  |  | 1
TA02 | TRADE ASSISTANT | Labor |  |  | 1
SCAF02 | ADVANCED SCAFFOLDER | Labor |  |  | 1
CODE03-1 | CODED WELDER | Labor |  |  | 1
RIG03-1 | ADVANCED RIGGER | Labor |  |  | 1
BMW03-1 | BMW | Labor |  |  | 1
MECH03-1 | MECHANICAL FITTER | Labor |  |  | 1
TA03-1 | TRADE ASSISTANT | Labor |  |  | 1
SCAF03 | ADVANCED SCAFFOLDER | Labor |  |  | 1
CODE04 | CODED WELDER | Labor |  |  | 1
RIG04 | ADVANCED RIGGER | Labor |  |  | 1
BMW04 | BMW | Labor |  |  | 1
MECH04 | MECHANICAL FITTER | Labor |  |  | 1
TA04 | TRADE ASSISTANT | Labor |  |  | 1
BMW05 | BMW | Labor |  |  | 1
RIG05 | ADVANCED RIGGER | Labor |  |  | 1
SCAF05 | ADVANCED SCAFFOLDER | Labor |  |  | 1
CRANE1 | CRANE OPERATOR | Labor |  |  | 1
CODE05 | CODED WELDER | Labor |  |  | 1
TA05 | TRADE ASSISTANT | Labor |  |  | 1
MECH05 | MECHANICAL FITTER | Labor |  |  | 1
GR1-1 | Electrician 1 | Labor |  |  | 1
GR1-2 | Electrician 2 | Labor |  |  | 1
GR1-3 | Electrician 3 | Labor |  |  | 1
GR1-4 | Electrician 4 | Labor |  |  | 1
GR1-5 | Electrician 5 | Labor |  |  | 1
GR1-6 | Electrician 6 | Labor |  |  | 1
GR1-7 | Electrician 7 | Labor |  |  | 1
GR1-8 | Electrician 8 | Labor |  |  | 1
GR1-9 | Electrician 9 | Labor |  |  | 1
GR1-10 | Electrician 10 | Labor |  |  | 1
GR1-11 | Electrician 11 | Labor |  |  | 1
GR1-12 | Electrician 12 | Labor |  |  | 1
GR1-13 | Electrician 13 | Labor |  |  | 1
GR1-14 | Electrician 14 | Labor |  |  | 1
GR1-15 | Electrician 15 | Labor |  |  | 1
GR1-16 | Electrician 16 | Labor |  |  | 1
GR1-17 | Electrician 17 | Labor |  |  | 1
GR1-18 | Electrician 18 | Labor |  |  | 1
GR1-19 | Electrician 19 | Labor |  |  | 1
GR1-20 | Electrician 20 | Labor |  |  | 1
GR1-21 | Electrician 21 | Labor |  |  | 1
GR1-22 | Electrician 22 | Labor |  |  | 1
GR1-23 | Electrician 23 | Labor |  |  | 1
GR1-24 | Electrician 24 | Labor |  |  | 1
GR1-25 | Electrician 25 | Labor |  |  | 1
GR1-26 | Electrician 26 | Labor |  |  | 1
GR1-27 | Electrician 27 | Labor |  |  | 1
GR1-28 | Electrician 28 | Labor |  |  | 1
SOU201 | SOU201 | Labor |  |  | 1
CODE-1 | CODED WELDER 1 | Labor |  |  | 1
CODE-2 | CODED WELDER 2 | Labor |  |  | 1
CODE-3 | CODED WELDER 3 | Labor |  |  | 1
CODE-4 | CODED WELDER 4 | Labor |  |  | 1
BMW-ONE | BMW 1 | Labor |  |  | 1
MECH -1 | MECHANICAL FITTER 1 | Labor |  |  | 1
MECH -2 | MECHANICAL FITTER 2 | Labor |  |  | 1
RIG -1 | ADVANCED RIGGER 1 | Labor |  |  | 1
TA - 1 | TRADE ASSISTANT 1 | Labor |  |  | 1
TA -2 | TRADE ASSISTANT 2 | Labor |  |  | 1
TA -3 | TRADE ASSISTANT 3 | Labor |  |  | 1
TA - 4 | TRADE ASSISTANT 4 | Labor |  |  | 1
SCAF -1 | ADVANCED SCAFFOLDER 1 | Labor |  |  | 1
SCAF -2 | ADVANCED SCAFFOLDER 2 | Labor |  |  | 1
CODE-5 | CODED WELDER 1 | Labor |  |  | 1
CODE-6 | CODED WELDER 2 | Labor |  |  | 1
CODE-7 | CODED WELDER 3 | Labor |  |  | 1
CODE-8 | CODED WELDER 4 | Labor |  |  | 1
BMW -2 | BMW 1 | Labor |  |  | 1
MECH -3 | MECHANICAL FITTER 1 | Labor |  |  | 1
MECH -4 | MECHANICAL FITTER 2 | Labor |  |  | 1
TA - 1-1 | TRADE ASSISTANT 1 | Labor |  |  | 1
TA -1 | TRADE ASSISTANT 2 | Labor |  |  | 1
TA -4 | TRADE ASSISTANT 3 | Labor |  |  | 1
TA - 4-1 | TRADE ASSISTANT 4 | Labor |  |  | 1
SCAF -3 | ADVANCED SCAFFOLDER 1 | Labor |  |  | 1
SCAF -4 | ADVANCED SCAFFOLDER 2 | Labor |  |  | 1
CODE-9 | CODED WELDER 1 | Labor |  |  | 1
CODE-10 | CODED WELDER 2 | Labor |  |  | 1
CODE-11 | CODED WELDER 3 | Labor |  |  | 1
CODE-12 | CODED WELDER 4 | Labor |  |  | 1
RIG -2 | ADVANCED RIGGER 1 | Labor |  |  | 1
BMW -3 | BMW 1 | Labor |  |  | 1
MECH -5 | MECHANICAL FITTER 1 | Labor |  |  | 1
MECH -6 | MECHANICAL FITTER 2 | Labor |  |  | 1
TA - 1-2 | TRADE ASSISTANT 1 | Labor |  |  | 1
TA -5 | TRADE ASSISTANT 2 | Labor |  |  | 1
TA -6 | TRADE ASSISTANT 3 | Labor |  |  | 1
TA - 4-2 | TRADE ASSISTANT 4 | Labor |  |  | 1
SCAF -5 | ADVANCED SCAFFOLDER 1 | Labor |  |  | 1
SCAF -6 | ADVANCED SCAFFOLDER 2 | Labor |  |  | 1
CODE-13 | CODED WELDER 1 | Labor |  |  | 1
CODE-14 | CODED WELDER 2 | Labor |  |  | 1
CODE-15 | CODED WELDER 3 | Labor |  |  | 1
CODE-16 | CODED WELDER 4 | Labor |  |  | 1
RIG -4 | ADVANCED RIGGER 1 | Labor |  |  | 1
BMW -1 | BMW 1 | Labor |  |  | 1
MECH -7 | MECHANICAL FITTER 1 | Labor |  |  | 1
MECH -8 | MECHANICAL FITTER 2 | Labor |  |  | 1
TA -8 | TRADE ASSISTANT 3 | Labor |  |  | 1
TA - 4-3 | TRADE ASSISTANT 4 | Labor |  |  | 1
BMW -4 | BMW 1 | Labor |  |  | 1
BMW -5 | BMW 2 | Labor |  |  | 1
RIG -5 | ADVANCED RIGGER 1 | Labor |  |  | 1
RIG -6 | ADVANCED RIGGER 2 | Labor |  |  | 1
RIG -7 | ADVANCED RIGGER 3 | Labor |  |  | 1
RIG -8 | ADVANCED RIGGER 4 | Labor |  |  | 1
SCAF -9 | ADVANCED SCAFFOLDER 1 | Labor |  |  | 1
SCAF -10 | ADVANCED SCAFFOLDER 2 | Labor |  |  | 1
CRANE -1 | CRANE OPERATOR | Labor |  |  | 1
RIG -9 | ADVANCED RIGGER 5 | Labor |  |  | 1
CODE-17 | CODED WELDER 1 | Labor |  |  | 1
CODE-18 | CODED WELDER 2 | Labor |  |  | 1
CODE-19 | CODED WELDER 3 | Labor |  |  | 1
CODE-20 | CODED WELDER 4 | Labor |  |  | 1
RIG -10 | ADVANCED RIGGER 6 SPOOLING | Labor |  |  | 1
TA - 1-4 | TRADE ASSISTANT 1 | Labor |  |  | 1
TA -9 | TRADE ASSISTANT 2 | Labor |  |  | 1
BMW -6 | BMW 3 | Labor |  |  | 1
BMW -7 | BMW 4 | Labor |  |  | 1
TA -10 | TRADE ASSISTANT 3 MF | Labor |  |  | 1
MECH -9 | MECHANICAL FITTER 1 | Labor |  |  | 1
RIG -11 | ADVANCED RIGGER 2 | Labor |  |  | 1
RIG -12 | ADVANCED RIGGER 3 | Labor |  |  | 1
RIG -15 | ADVANCED RIGGER 2 | Labor |  |  | 1
RIG -16 | ADVANCED RIGGER 3 | Labor |  |  | 1
RIG -17 | ADVANCED RIGGER 2 | Labor |  |  | 1
RIG -18 | ADVANCED RIGGER 3 | Labor |  |  | 1
BMW -8 | BMW 2 | Labor |  |  | 1
RIG -19 | ADVANCED RIGGER 4 SPOOLING | Labor |  |  | 1
SOU201.EW | Earthworker | Labor |  |  | 1
SOU201.PO | Plant Operator | Labor |  |  | 1
SOU201.FM | Formworker | Labor |  |  | 1
SOU201.ST | Steel Fixer | Labor |  |  | 1
SOU201.CN | Concreter | Labor |  |  | 1
SOU201.SC | Subcontractor | Labor |  |  | 1
OB-6 | Water (kl) | Material | kl |  | 0
OB | Overburden | Material | Cubic Metres |  | 0
OB-1 | Vermeer (m3) | Material | Cubic Metres |  | 0
OB-2 | Vermeer (m2) | Material | Square Metres |  | 0
OB-3 | Drill & Blast | Material | Cubic Metres |  | 0
OB-4 | Rock Haul (m3) | Material | Cubic Metres |  | 0
OB-5 | Crush Rock (t) | Material | Tonnes |  | 0
CG-3 | Saftey Berm | Material | Square Metres |  | 0
OB-7 | Subgrade Trim (m2) | Material | Square Metres |  | 0
OB-8 | Wearing Course Trim (m2) | Material | Square Metres |  | 0
x_Lab-1 | x_Lab-O | Labor |  |  | 1
NUL-UNS | Unsuitable Removal | Material | Cubic Metres |  | 11
NUL-WATER | Construction Water | Material | Litres |  | 50
NUL-SG PREP | Subgrade Preparation | Material | Square Metres |  | 11
NUL-POLYMER | Polymer Surface Treatments | Material | Square Metres |  | 11
NUL-OB | Overburden | Material | Cubic Metres |  | 11
NUL-DR | Drain Construction | Material | Cubic Metres |  | 11
NUL-SED | Sediment Basin | Material | Cubic Metres |  | 11
NUL-GP | Guide Posts & Signs | Material | Each |  | 11
NUL-SB | Safety Berms | Material | Cubic Metres |  | 11
S1-1 | S1 | Labor |  |  | 1
S2-1 | S2 | Labor |  |  | 1
P | PC | Labor |  |  | 1
C | C1 | Labor |  |  | 1
C-1 | CP | Labor |  |  | 1
S | SPC | Labor |  |  | 1
S-1 | EW | Labor |  |  | 1
S-2 | SF1 | Labor |  |  | 1
6154-Crew 6.1-3 | GEMCO Projects Electrical -RSGx Crew | Labor |  |  | 1
J950 - Direct | Direct Labour | Labor |  |  | 1
GEMCO Elec | GEMCO Elec | Labor |  |  | 1
SCAFFOLDER | SCAFFOLDER | Labor |  |  | 1
BELT TECH | BELT TECH | Labor |  |  | 1
GEMCO QA | GEMCO QA | Labor |  |  | 1
GEMCO FT | GEMCO FT | Labor |  |  | 1
SCRAPER TECH | SCRAPER TECH | Labor |  |  | 1
FRANNA OP | FRANNA OP | Labor |  |  | 1
250T CRANE | 250T CRANE | Labor |  |  | 1
250T OP | 250T OP | Labor |  |  | 1
GEMCO SV | GEMCO SV | Labor |  |  | 1
GEMCO A&I | GEMCO A&I | Labor |  |  | 1
GEMCO BM | GEMCO BM | Labor |  |  | 1
GEMCO SN | GEMCO SN | Labor |  |  | 1
GEMCO ENG | GEMCO ENG | Labor |  |  | 1
60FT EWP | 60FT EWP | Labor |  |  | 1
BELT FT | BELT FT | Labor |  |  | 1
GEMCO LUBE | GEMCO LUBE | Labor |  |  | 1
Blast/Paint | Blast/Paint | Labor |  |  | 1
Rollers | Rollers | Labor |  |  | 1
GEMCO PT OPS | GEMCO PT OPS | Labor |  |  | 1
PROJECTS | PROJECTS | Labor |  |  | 1
BLACK CAT | BLACK CAT | Labor |  |  | 1
GEMCO Ops | GEMCO Ops | Labor |  |  | 1
FLUID SV | FLUID SV | Labor |  |  | 1
FLUID FT | FLUID FT | Labor |  |  | 1
Control Room | Control Room | Labor |  |  | 1
OHTC OP | OHTC OP | Labor |  |  | 1
Processing 11 | Processing 11 | Labor |  |  | 1
Isolation Officer 7 | Isolation Officer 7 | Labor |  |  | 1
Isolation Officer 8 | Isolation Officer 8 | Labor |  |  | 1
Isolation Officer 1 | Isolation Officer 1 | Labor |  |  | 1
Isolation Officer 2 | Isolation Officer 2 | Labor |  |  | 1
Isolation Officer 3 | Isolation Officer 3 | Labor |  |  | 1
Isolation Officer 4 | Isolation Officer 4 | Labor |  |  | 1
Isolation Officer 5 | Isolation Officer 5 | Labor |  |  | 1
Processing 4 | Processing 4 | Labor |  |  | 1
Processing 5 | Processing 5 | Labor |  |  | 1
Isolation Officer 6 | Isolation Officer 6 | Labor |  |  | 1
Processing 6 | Processing 6 | Labor |  |  | 1
Processing 1 | Processing 1 | Labor |  |  | 1
Processing 2 | Processing 2 | Labor |  |  | 1
Processing 8 | Processing 8 | Labor |  |  | 1
NORTECH BLAST | NORTECH BLAST | Labor |  |  | 1
TECHNIBELT | TECHNIBELT | Labor |  |  | 1
RUBBERLINER | RUBBERLINER | Labor |  |  | 1
MAXI TA | MAXI TA | Labor |  |  | 1
GEMCO HV Elec | GEMCO HV Elec | Labor |  |  | 1
ACI - ELEC | ACI - ELEC | Labor |  |  | 1
ELASTOMERS | ELASTOMERS | Labor |  |  | 1
80FT EWP | 80FT EWP | Labor |  |  | 1
34FT EWP | 34FT EWP | Labor |  |  | 1
SCHENCK | SCHENCK | Labor |  |  | 1
SIP | SIP | Labor |  |  | 1
WEIR | WEIR | Labor |  |  | 1
CRAWLER | CRAWLER | Labor |  |  | 1
FLUID BM | FLUID BM | Labor |  |  | 1
FLUID SN | FLUID SN | Labor |  |  | 1
FLS Tech | FLS Tech | Labor |  |  | 1
RIG | Req - LAB-RIG | Labor |  |  | 1
34' EWP | 34' EWP | Labor |  |  | 1
CAP PROJECTS | CAP PROJECTS | Labor |  |  | 1
Tradesman | Tradesman | Labor |  |  | 1
Operator | Operator | Labor |  |  | 1
Forklift | Forklift | Labor |  |  | 1
Mobile Scaffold | Mobile Scaffold | Labor |  |  | 1
LAB-BLM | LAB-BLM | Labor |  |  | 1
LAB-CONC | LAB-CONC | Labor |  |  | 1
LAB-SB/P | LAB-SB/P | Labor |  |  | 1
EWP | EWP | Labor |  |  | 1
80' EWP | 80' EWP | Labor |  |  | 1
BREAKDOWN | BREAKDOWN | Labor |  |  | 1
JUB/EWP | JUB/EWP | Labor |  |  | 1
JUB/CRANE | JUB/CRANE | Labor |  |  | 1
MP | MP | Labor |  |  | 1
MP STRUCT | MP STRUCT | Labor |  |  | 1
ELEC BM | ELEC BM | Labor |  |  | 1
ZDP | ZDP | Labor |  |  | 1
WOR_FRC-1 | BOD EW TPs | Nonlabor |  |  | 0
TP001 | TP001 | Nonlabor |  |  | 0
TP002 | TP002 | Nonlabor |  |  | 0
TP003 | TP003 | Nonlabor |  |  | 0
TP004 | TP004 | Nonlabor |  |  | 0
TP007 | TP007 | Nonlabor |  |  | 0
TP008 | TP008 | Nonlabor |  |  | 0
TP009 | TP009 | Nonlabor |  |  | 0
TP010 | TP010 | Nonlabor |  |  | 0
TP011 | TP011 | Nonlabor |  |  | 0
TP012 | TP012 | Nonlabor |  |  | 0
TP013 | TP013 | Nonlabor |  |  | 0
TP014 | TP014 | Nonlabor |  |  | 1
TP017 | TP017 | Nonlabor |  |  | 1
TP018 | TP018 | Nonlabor |  |  | 1
TP025 | TP025 | Nonlabor |  |  | 1
TP026 | TP026 | Nonlabor |  |  | 1
TP028 | TP028 | Nonlabor |  |  | 1
TP029 | TP029 | Nonlabor |  |  | 1
TP030 | TP030 | Nonlabor |  |  | 1
TP031 | TP031 | Nonlabor |  |  | 1
TP033 | TP033 | Nonlabor |  |  | 1
TP034 | TP034 | Nonlabor |  |  | 1
TP035 | TP035 | Nonlabor |  |  | 1
TP046 | TP046 | Nonlabor |  |  | 1
TP047 | TP047 | Nonlabor |  |  | 1
TP068 | TP068 | Nonlabor |  |  | 1
6154-Crew 6.3-1 | GEMCO EWP and Spotter | Labor |  |  | 1
Exact | Exact Resources | Material |  |  | 12
RL_825 | RL_825 | Nonlabor |  |  | 1
WC_Body_10kL | WC_Body_10kL | Labor |  |  | 1
Skid_Steer | Skid_Steer | Labor |  |  | 1
x_FRP | x_FRP | Labor |  |  | 5
z_Piling | z_Piling | Labor |  |  | 1
DT_40T | DT_40T | Nonlabor |  |  | 2
x_Drainage | x_Drainage | Labor |  |  | 1
RL_18T | RL_18T | Nonlabor |  |  | 1
x_Dogman | x_Dogman | Labor |  |  | 1
EX_12T | EX_12T | Nonlabor |  |  | 1
x_Surveyor | x_Surveyor | Labor |  |  | 1
Conc_Pump_36 | Conc_Pump_36 | Nonlabor |  |  | 1
CR_20T | CR_20T | Nonlabor |  |  | 1
CR_350T | CR_350T | Nonlabor |  |  | 1
Gen_Lab | Gen_Lab | Labor |  |  | 1
EX_35T | EX_35T | Nonlabor |  |  | 1
DT_Body | DT_Body | Nonlabor |  |  | 1
Crusher_Screen | Crusher_Screen | Nonlabor |  |  | 1
z_Piling_Lab | z_Piling_Lab | Labor |  |  | 1
x_Lab_Steel | x_Lab_Steel | Labor |  |  | 23
QTY RESOURCE | Quantity Resource | Nonlabor |  |  | 1
Civil Lead-1 | Civil Lead | Labor |  |  | 1
Senior Project Manager-1 | Senior Project Manager | Labor |  |  | 1
Structural Lead-1 | Structural Lead | Labor |  |  | 1
Mechanical Lead-1 | Mechanical Lead | Labor |  |  | 1
99555 STEAM | STEAM ELECTRIFICATION | Labor |  |  | 1
S32-STEAM | S32 Steam Manhours | Labor |  |  | 1
ESP-STEAM | ESP Steam Manhours - Direct | Labor |  |  | 1
S-SPP | Sedgman Senior Project Planner | Labor |  |  | 1
S32-CLE | Civil Lead Engineer | Labor |  |  | 1
S32-CSE | Senior Civil Engineer | Labor |  |  | 1
S32-CSD | Senior Civil Designer | Labor |  |  | 1
S32-MSD | Senior Mechanical Designer | Labor |  |  | 1
S32-SLE | Structural Lead Engineer | Labor |  |  | 1
S32-SSE | Senior Structural Engineer | Labor |  |  | 1
S32-SSD | Senior Structural Designer | Labor |  |  | 1
S32-ELE | Electrical Lead Engineer | Labor |  |  | 1
S32-ESE | Senior Electrical Engineer | Labor |  |  | 1
S32-ESD | Senior Electrical Designer | Labor |  |  | 1
S32-PMS | PM / Eng Support | Labor |  |  | 1
S32-DM | Design Manager | Labor |  |  | 1
S32-EM | Engineering Manager | Labor |  |  | 1
S32-LPP | Lead Scheduler | Labor |  |  | 1
S32-LDC | Lead Document Controller | Labor |  |  | 1
S32-JDC | Admin | Labor |  |  | 1
S32-SPE | Senior Project Engineer | Labor |  |  | 1
S32-LCC | Principal/Lead Cost Controller | Labor |  |  | 1
S32-CA | CAD Admin | Labor |  |  | 1
S32-BLE | Process Lead Engineer | Labor |  |  | 1
S32-BSD | Senior Process Designer | Labor |  |  | 1
S32-MLE | Mechanical Lead Engineer | Labor |  |  | 1
S32-MSE | Senior Mechanical Engineer | Labor |  |  | 1
S32-MLD | Mechanical Lead Designer | Labor |  |  | 1
S32-BPE | Process Principle Engineer | Labor |  |  | 1
PP211608 | PP211608 Hours | Labor |  |  | 1
PJ_DS | Design | Labor |  |  | 1
PJ_PM | Project Management | Labor |  |  | 1
PJ_EN | Engineering | Labor |  |  | 1
PJ_PL | Planner | Labor |  |  | 1
PJ_ES | Estimator | Labor |  |  | 1
PJ_CT | Cost | Labor |  |  | 1
Project Engineer --1 | Project Engineer - LSL | Labor |  |  | 1
Mechanical Enginee-1 | Mechanical Engineer - LSL | Labor |  |  | 1
Structural Enginee-1 | Structural Engineer - LSL | Labor |  |  | 1
Document Controlle-5 | Document Controller -LSL | Labor |  |  | 1
CB | CB | Labor |  |  | 1
NM | NM | Labor |  |  | 1
ENG1 | ENG1 | Labor |  |  | 1
ENG2 | ENG2 | Labor |  |  | 1
ENG3 | ENG3 | Labor |  |  | 1
ENG 1 | ENG 1 | Labor |  |  | 1
Subcontractors | Subcontractor | Labor |  |  | 1
Fabrication | Fabrication | Labor
PP | Piping / Valves / SP Items Qty | Nonlabor |  |  | 1
ENG 2 | ENG 2 | Labor |  |  | 1
ENG 3 | ENG 3 | Labor |  |  | 1
ENG 4 | ENG 4 | Labor |  |  | 1
LEAD ENG | LEAD ENG | Labor |  |  | 1
7 | 7 | Labor |  |  | 1
15 | 15 | Labor |  |  | 1
Ben Piromanski | Ben Piromanski | Labor |  |  | 1
Anthony Iddon | Anthony Iddon | Labor |  |  | 1
Justin Woolston | Justin Woolston | Labor |  |  | 1
Others | Others | Labor |  |  | 1
MG | Management | Labor |  |  | 1
PI-1 | Piping | Labor |  |  | 1
EL | Electrical | Labor |  |  | 1
IN | Instrumentation | Labor |  |  | 1
CI | Civil | Labor |  |  | 1
PC | Project Controls | Labor |  |  | 1
DC-1 | Doc Control | Labor |  |  | 1
ES | Estimator | Labor |  |  | 1
PR | Process | Labor |  |  | 1
advanced_rigger_crew | Advanced Rigger Crew | Labor |  |  | 16
advanced_scaffolder_crew | Advanced Scaffolder Crew | Labor |  |  | 8
bmw_crew | BMW Crew | Labor |  |  | 9
coded_welder_crew | Coded Welder Crew | Labor |  |  | 20
concreter_crew | Concreter Crew | Labor |  |  | 16
crane_operator_crew | Crane Operator Crew | Labor |  |  | 4
earthworker_crew | Earthworker Crew | Labor |  |  | 60
electrician_crew | Electrician Crew | Labor |  |  | 28
formworker_crew | Formworker Crew | Labor |  |  | 19
mechanical_fitter_crew | Mechanical Fitter Crew | Labor |  |  | 9
plant_operator_crew | Plant Operator Crew | Labor |  |  | 8
steel_fixer_crew | Steel Fixer Crew | Labor |  |  | 25
subcontractor_crew | Subcontractor Crew | Labor |  |  | 16
trade_assistant_crew | Trade Assistant Crew | Labor |  |  | 18
fabrication_piperack_stair | Fabrication_PipeRack&Stair | Labor |  |  | 1
AMP_SRG | AMPGARD SRG On-Site Normal | Labor |  |  | 4
AMP_LGM-WAREHOUSE | AMPGARD LGM | Labor |  |  | 4
G-8000 | Consulting | Labor |  | A | 1
G-B-2081 | Cost Engineering-GID | Labor |  |  | 1
BOD Execution | BOD Execution | Labor |  |  | 1
BOD Concrete RF | BOD Concrete RF | Labor |  |  | 1
BOD Civil RF | BOD Civil RF | Labor |  |  | 1
BOD Piping RF | BOD Piping RF | Labor |  |  | 1
BOD Electrical RF | BOD Electrical RF | Labor |  |  | 1
BOD Mechanical RF | BOD Mechanical RF | Labor |  |  | 1
BOD Instrument RF | BOD Instrumentation RF | Labor |  |  | 1
BOD Steel RF | BOD Steel RF | Labor |  |  | 1
FS2-PM Supp | PM Support | Labor |  |  | 1
UKW | UKW | Labor |  |  | 1
S32/UKW | S32/UKW | Labor |  |  | 1
Middindi/UKW/S32 | Middindi/UKW/S32 | Labor |  |  | 1
Middindi | Middindi | Labor |  |  | 1
UKW/Prysm | UKW/Prysm | Labor |  |  | 1
Artesium | Artesium | Labor |  |  | 1
UKW/Artesium/S32 | UKW/Artesium/S32 | Labor |  |  | 1
UKW/Artesium | UKW/Artesium | Labor |  |  | 1
HMI1 | HMI1 | Labor |  |  | 1
HMI2 | HMI2 | Labor |  |  | 1
BOD Concrete BF | BOD Concrete BF | Labor |  |  | 1
BOD Steel BF | BOD Steel BF | Labor |  |  | 1
BOD Mech BF | BOD Mechanical BF | Labor |  |  | 1
BOD Electrical BF | BOD Electrical BF | Labor |  |  | 1
BOD Instrument BF | BOD Instrumentation BF | Labor |  |  | 1
BOD Piping BF | BOD Piping BF | Labor |  |  | 1
LABOUR DAY | LABOUR RESOURCES DAY SHIFT | Labor |  |  | 1
BOD-CO | 06 - BOD Commissioning & Ops Readiness | Labor |  |  | 1
A - BOD Earthworks | BOD Earthworks Qty M3 | Nonlabor |  |  | 1
B - BOD Civil | BOD Civil Qty M | Nonlabor |  |  | 1
C - BOD Concrete | BOD Concrete Qty M3 | Nonlabor |  |  | 1
D - BOD Steel | BOD Steel Qty Tonnes | Nonlabor |  |  | 1
M - BOD Mech Bulks | BOD Mech Bulks Qty Tonnes | Nonlabor |  |  | 1
N - BOD Mech Equip | BOD Mech Equip Qty EA | Nonlabor |  |  | 1
P - BOD Piping | BOD Piping Qty LM | Nonlabor |  |  | 1
T - BOD Elec Equip | BOD Electrical Equip Qty EA | Nonlabor |  |  | 1
U - BOD Raceway | BOD Raceway Qty LM | Nonlabor |  |  | 1
W - BOD Wire & Cable | BOD Wire & Cable Qty LM | Nonlabor |  |  | 1
X - BOD Inst & Cont | BOD Inst & Control Qty EA | Nonlabor |  |  | 1
BOD-OR-01 | BOD Asset Management Lead - Reliantix | Labor |  |  | 1
BOD FS2 Owner | BOD FS2 Owners | Labor |  |  | 1
BOD-VAR | Variation | Labor |  |  | 1
NUL-SEDCON | Sediment Controls for Drains | Material | Cubic Metres |  | 11
NUL-SUB FEN | Fencing Subcontractor | Labor |  |  | 1
NUL-FEN | Fencing | Material | Lineal Metres |  | 11
R-135 | (New Resource) | Labor |  |  | 1
R-136 | GEMCO Excess Water - ES to NH2 | Labor |  |  | 1
R-137 | Piping and Civil Installation Crews | Labor |  |  | 1
R-138 | Mechanical Crew | Labor |  |  | 1
R-139 | Electrical Crew | Labor |  |  | 1
HMI3 | HMI3 | Labor |  |  | 1
HMI4 | HMI4 | Labor |  |  | 1
HMI5 | HMI5 | Labor |  |  | 1
HMI6 | HMI6 | Labor |  |  | 1
HMI7 | HMI7 | Labor |  |  | 1
HMI8 | HMI8 | Labor |  |  | 1
HMI9 | HMI9 | Labor |  |  | 1
HMI10 | HMI10 | Labor |  |  | 1
DCSE1 | DCSE1 | Labor |  |  | 1
DCSL | DCSL | Labor |  |  | 1
OL | OL | Labor |  |  | 1
HM3 | HM3 | Labor |  |  | 1
DCS2 | DCS2 | Labor |  |  | 1
SS-L | SS-L | Labor |  |  | 1
SSE1 | SSE1 | Labor |  |  | 1
SSE2 | SSE2 | Labor |  |  | 1
HMIL | HMIL | Labor |  |  | 1
SSE3 | SSE3 | Labor |  |  | 1
DCSE3 | DCSE3 | Labor |  |  | 1
LOG_TM | LOG_TM | Labor |  |  | 1
HMI11 | HMI11 | Labor |  |  | 1
OTSL | OTSL | Labor |  |  | 1
OTS1 | OTS1 | Labor |  |  | 1
SSL | SSL | Labor |  |  | 1
SE1 | SE1 | Labor |  |  | 1
SE2 | SE2 | Labor |  |  | 1
NW1 | NW1 | Labor |  |  | 1
NW2 | NW2 | Labor |  |  | 1
DCE3 | DCE3 | Labor |  |  | 1
229 | 229 | Labor |  |  | 1
DDCDCSE3DCSE3 | DDCDCSE3DCSE3 | Labor |  |  | 1
DCS2-1 | DCS2 | Labor |  |  | 1
DCS3 | DCS3 | Labor |  |  | 1
PHD1 | PHD1 | Labor |  |  | 1
SS2 | SS2 | Labor |  |  | 1
SSE4 | SSE4 | Labor |  |  | 1
SSS | SSS | Labor |  |  | 1
DCE2 | DCE2 | Labor |  |  | 1
SSSSSE2E | SSSSSE2E | Labor |  |  | 1
OTS2 | OTS2 | Labor |  |  | 1
HMI12 | HMI12 | Labor |  |  | 1
NW3 | NW3 | Labor |  |  | 1
DCSE4 | DCSE4 | Labor |  |  | 1
DCSE2 | DCSE2 | Labor |  |  | 1
DCSE5 | DCSE5 | Labor |  |  | 1
DCSE6 | DCSE6 | Labor |  |  | 1
DCSL1 | DCSL1 | Labor |  |  | 1
NW4 | NW4 | Labor |  |  | 1
SSE5 | SSE5 | Labor |  |  | 1
SSE6 | SSE6 | Labor |  |  | 1
SS-L1 | SS-L1 | Labor |  |  | 1
Monadelphous | Monadelphous | Labor |  |  | 1
100T | 100T | Labor |  |  | 1
CRN | CRN | Labor |  |  | 1
COX | COX | Labor |  |  | 1
FITT | FITT | Labor |  |  | 1
SL6 | SL6 | Labor |  |  | 1
TUG | TUG | Labor |  |  | 1
PGX | Primero Group | Labor |  |  | 1
D1 | Engineering and Design | Labor |  |  | 1
Engineering | Engineering | Labor |  |  | 1
Design | Drafting | Labor |  |  | 1
Electrician 1 | Electrician 1 | Labor |  |  | 1
Major Projects | Major Projects | Labor |  |  | 1
Damage Since ATO | Damage Since ATO | Labor |  |  | 1
Electrician 2 | Electrician 2 | Labor |  |  | 1
Electrician 3 | Electrician 3 | Labor |  |  | 1
Boilermaker 1 | Boilermaker 1 | Labor |  |  | 1
Boilermaker 2 | Boilermaker 2 | Labor |  |  | 1
Trelleborg | Trelleborg | Labor |  |  | 1
Trelleborg 2 | Trelleborg 2 | Labor |  |  | 1
Trelleborg 1 | Trelleborg 1 | Labor |  |  | 1
Wessels North | Resources | Labor |  |  | 1
B-1 | Team A-B | Labor |  |  | 24
B-2 | Team B-B | Labor |  |  | 24
B-3 | Team C-B | Labor |  |  | 24
B-4 | Team D-B | Labor |  |  | 24
E-1 | Team A-E | Labor |  |  | 24
E-2 | Team B-E | Labor |  |  | 24
E-3 | Team C-E | Labor |  |  | 24
E-4 | Team D-E | Labor |  |  | 24
Cab-1 | Cable Pull MS23 | Labor |  |  | 84
Cab-2 | Cable Pull MS24 | Labor |  |  | 84
LH | LH | Labor |  |  | 1
ELEC | ELEC | Labor |  |  | 1
Diver | Diver | Labor |  |  | 1
60'EWP | 60'EWP | Labor |  |  | 1
COP/160T | COP/160T | Labor |  |  | 1
HPWB | HPWB | Labor |  |  | 1
PROCURE | PROCURE | Labor |  |  | 1
PLAN | PLAN | Labor |  |  | 1
COOR | COOR | Labor |  |  | 1
CONSTRUCT | CONSTRUCT | Labor |  |  | 1
CIVIL | CIVIL | Labor |  |  | 1
GEBIE | GEBIE | Labor |  |  | 1
SCurve | SCurve | Labor |  |  | 1
SCAFF(600%) | SCAFF(600%) | Labor |  |  | 1
Da Vinci | Da Vinci | Labor |  |  | 1
DIV | DIV | Labor |  |  | 1
DIV SUP | DIV SUP | Labor |  |  | 1
POLY WELD | POLY WELD | Labor |  |  | 1
CONSTRUCTOR | CONSTRUCTOR | Labor |  |  | 1
PUNT | LAB-PUNT | Labor |  |  | 1
VIBE_CONTRACTOR | VIBE_CONTRACTOR | Labor |  |  | 1
SIDE TIPPER | SIDE TIPPER | Labor |  |  | 1
LAURIEM | LAURIEM | Labor |  |  | 1
HUSSEY | HUSSEY | Labor |  |  | 1
BLM | Required BLM | Labor |  |  | 1
SB/P | Required SB/P | Labor |  |  | 1
NDT | NDT | Labor |  |  | 1
CONC | CONC | Labor |  |  | 1
MMC_BLM | MMC_BLM | Labor |  |  | 1
MMC_RIG | MMC_RIG | Labor |  |  | 1
AR-S32-2 | Nigel Scott | Labor |  |  | 1
AR-S32-3 | Nick Kitis | Labor |  |  | 1
AR-S32-4 | Brandon Rademeyer | Labor |  |  | 1
AR-S32-5 | Project Administrator | Labor |  |  | 1
AR-S32-6 | Engineer - Management and Reporting | Labor |  |  | 1
AR-S32-7 | Aaron Fretwell | Labor |  |  | 1
AR-S32-8 | Senior Drafter/Modeller | Labor |  |  | 1
AR-S32-9 | Experienced Engineer | Labor |  |  | 1
AR-S32-10 | Cameron Maher | Labor |  |  | 1
AR-S32-11 | Senior Engineer-Bridge Design | Labor |  |  | 1
AR-S32-12 | Kugan Naidoo | Labor |  |  | 1
AR-S32-13 | Technical Director-Electrical | Labor |  |  | 1
AR-S32-14 | Engineer-Electrical | Labor |  |  | 1
AR-S32-15 | Tung Nguyen | Labor |  |  | 1
AR-S32-16 | Senior Engineer-Water | Labor |  |  | 1
AR-S32-17 | Engineer-Water | Labor |  |  | 1
AR-S32-18 | Steven Voss | Labor |  |  | 1
AR-S32-19 | Technical Director | Labor |  |  | 1
AR-S32-20 | Experienced Engineer | Labor |  |  | 1
AR-S32-21 | Duncan Crook | Labor |  |  | 1
AR-S32-22 | Associate-NPI | Labor |  |  | 1
AR-S32-23 | Technical Director-NPI | Labor |  |  | 1
AR-S32-24 | Senior Engineer-NPI | Labor |  |  | 1
AR-S32-25 | Experienced Engineer-NPI | Labor |  |  | 1
AR-S32-26 | Engineer-NPI | Labor |  |  | 1
AR-S32-27 | Riaan Van Wyk | Labor |  |  | 1
AR-S32-28 | Senior Engineer1-Geo | Labor |  |  | 1
AR-S32-29 | Senior Engineer2-Geo | Labor |  |  | 1
AR-S32-30 | Experienced Engineer-Geo | Labor |  |  | 1
AR-S32-31 | Ben Smith | Labor |  |  | 1
AR-S32-32 | Technical Director-Geo | Labor |  |  | 1
AR-S32-33 | Experienced Engineer-Geo | Labor |  |  | 1
AR-S32-34 | Frankie Kong | Labor |  |  | 1
AR-S32-35 | Experienced Drafter/Modeller-Digital | Labor |  |  | 1
AR-S32-39 | BEST - FOC | Labor |  |  | 1
AR-S32-40 | MGA - Cost | Labor |  |  | 1
AR-S32-41 | Kim Stimson-WGA Management | Labor |  |  | 1
AR-S32-42 | Project Director-WGA Management | Labor |  |  | 1
AR-S32-43 | Project Administrator-WGA Management | Labor |  |  | 1
AR-S32-48 | Samuel Hammond | Labor |  |  | 1
AR-S32-49 | Engineer-Structural | Labor |  |  | 1
AR-S32-51 | Keith Lundy | Labor |  |  | 1
AR-S32-52 | Experienced Engineer | Labor |  |  | 1
AR-S32-53 | Experienced Drafter/Modeller | Labor |  |  | 1
AR-S32-59 | Associate-Hydro | Labor |  |  | 1
AR-S32-60 | Senior Engineer-Hydro | Labor |  |  | 1
AR-S32-61 | Associate-Geo | Labor |  |  | 1
AR-S32-62 | Experinced Engineer-Geo | Labor |  |  | 1
MMC_SB/P | MMC_SB/P | Labor |  |  | 1
GOLD_BLM | GOLD_BLM | Labor |  |  | 1
GOLD_FITT | GOLD_FITT | Labor |  |  | 1
MMC_TA | MMC_TA | Labor |  |  | 1
WATER_TRUCK | WATER_TRUCK | Labor |  |  | 1
MANITOU | MANITOU | Labor |  |  | 1
INSPECTOR | INSPECTOR | Labor |  |  | 1
NPI_PLUMBER | NPI_PLUMBER | Labor |  |  | 1
TANKER | TANKER | Labor |  |  | 1
Environmental spec-1 | Environmental specialist - Lead | Labor |  |  | 1
Environmental spec-2 | Environmental specialist - Senior | Labor |  |  | 1
Risk Consultant | Risk Consultant | Labor |  |  | 1
Financial Consultant | Financial Consultant | Labor |  |  | 1
Techno Economic Spec | Techno Economic Specialist - Senior | Labor |  |  | 1
Discipline engineer | Discipline engineer - Lead | Labor |  |  | 1
Discipine engineer - | Discipine engineer - Senior | Labor |  |  | 1
Design coordinator | Design coordinator | Labor |  |  | 1
Engineering draughts | Engineering draughtsman | Labor |  |  | 1
Engineering Manager | Engineering Manager | Labor |  |  | 1
Project Controls Man | Project Controls Manager | Labor |  |  | 1
Environmental spec-3 | Environmental specialist - Lead | Labor |  |  | 1
Environmental spec-4 | Environmental specialist - Senior | Labor |  |  | 1
Techno Economic Sp-1 | Techno Economic Specialist - Senior | Labor |  |  | 1
Discipline enginee-1 | Discipline engineer - Lead | Labor |  |  | 1
Discipine engineer-1 | Discipine engineer - Senior | Labor |  |  | 1
Engineering draugh-1 | Engineering draughtsman | Labor |  |  | 1
Project Controls M-1 | Project Controls Manager | Labor |  |  | 1
NPI_ELECT | NPI_ELECT | Labor |  |  | 1
Environmental spec-5 | Environmental specialist - Lead | Labor |  |  | 1
Environmental spec-6 | Environmental specialist - Senior | Labor |  |  | 1
Ukwazi | Ukwazi Resource | Labor |  |  | 1
S32 Owner | S32 Owners | Labor |  |  | 1
99628-FS-201 | Owners Team | Labor |  |  | 1
12609653 | CASS Resources | Labor |  |  | 1
12609653-GHD | CASS FS ENG | Labor |  |  | 1
12609653-CASS | CASS Execution | Labor |  |  | 1
Techno Economic Sp-2 | Techno Economic Specialist - Senior | Labor |  |  | 1
Discipline enginee-2 | Discipline engineer - Lead | Labor |  |  | 1
Discipine engineer-2 | Discipine engineer - Senior | Labor |  |  | 1
Engineering draugh-2 | Engineering draughtsman | Labor |  |  | 1
Project Controls M-2 | Project Controls Manager | Labor |  |  | 1
CAR | CAR | Labor |  |  | 1
S.FIX | S.FIX | Labor |  |  | 1
DAVINCI | DAVINCI | Labor |  |  | 1
Freo - 220T | Freo - 220T | Labor |  |  | 1
NDT(E) | NDT (E) | Labor |  |  | 1
BOD_BRN | BOD Brownfields | Labor |  |  | 1
SCAFF01 | Scaff Team 01 | Labor |  |  | 1
SMP | SMP Team | Labor |  |  | 1
WHARFPIPE | GEMCO Pipewelder | Labor |  |  | 1
R-140 | Western Power Crew | Labor |  |  | 1
Res | RESOURCING | Labor |  |  | 1
AR-S32-64 | Lead Alignment Designer | Labor |  |  | 1
REE3 | Electrical Drafter | Labor |  |  | 1
REE4 | Electrical Engineer | Labor |  |  | 1
RME2 | Mechanical Drafter | Labor |  |  | 1
RME0 | Mechanical Engineer | Labor |  |  | 1
RSE2 | Structural Drafter | Labor |  |  | 1
RSE3 | Structural Engineer | Labor |  |  | 1
RSE9 | Civil Drafter | Labor |  |  | 1
RSE8 | Civil Engineer | Labor |  |  | 1
RSE10 | Process Engineer | Labor |  |  | 1
RSE11 | Process Drafter | Labor |  |  | 1
RSE7 | Geotech Engineer | Labor |  |  | 1
RSE6 | Hydrogeologist | Labor |  |  | 1
RSE12 | Project manager | Labor |  |  | 1
S32-HON PFSEXT | S32 HON PFS Extension Manhours | Labor |  |  | 0
AR-S32-36 | Cameron Maher - Bridge Lead | Labor |  |  | 1
AR-S32-37 | Xuan Lam - Senior Engineer | Labor |  |  | 1
AR-S32-38 | Kurtis Pepler - Senior Modeller | Labor |  |  | 1
RSE13 | Administration | Labor |  |  | 1
AR-S32-66 | Arnold Antonyo | Labor |  |  | 1
Wharf | WP17 Cashflow | Nonlabor |  |  | 1
J956 - Direct | J956 - Direct Labour | Labor |  |  | 1
Daniel Moland - Crew | Daniel Moland - Crew Leader | Labor |  |  | 1
James McGowan - Exca | James McGowan - Excavator Operator | Labor |  |  | 1
Josh Prowse - Plumbe | Josh Prowse - Plumber | Labor |  |  | 1
Anthony Vella - Plum | Anthony Vella - Plumber | Labor |  |  | 1
Daniel Prowse - Plum | Daniel Prowse - Plumber | Labor |  |  | 1
Oliver Taylor - Supe | Oliver Taylor - Supervisor | Labor |  |  | 1
Daniel Howarth - Sup | Daniel Howarth - Supervisor | Labor |  |  | 1
Blair Robertson - Op | Blair Robertson - Operator | Labor |  |  | 1
Callam Webster - Ser | Callam Webster - Service Layer | Labor |  |  | 1
Cheyenne Speight - O | Cheyenne Speight - Offsider | Labor |  |  | 1
Mark Bowering - Offs | Mark Bowering - Offsider | Labor |  |  | 1
Darren Rodney - Exca | Darren Rodney - Excavator Operator | Labor |  |  | 1
Dino Bacich - Truck | Dino Bacich - Truck and Posi | Labor |  |  | 1
Richard Morris - Pip | Richard Morris - Pipelayer | Labor |  |  | 1
Shea Sheppard - Pipe | Shea Sheppard - Pipelayer | Labor |  |  | 1
Richard Broadhurst - | Richard Broadhurst - Pipelayer | Labor |  |  | 1
Dylan Leeuwenburg - | Dylan Leeuwenburg - Project Manager | Labor |  |  | 1
Matt Dixon - Senior | Matt Dixon - Senior Engineer | Labor |  |  | 1
Joe Hickey - Senior | Joe Hickey - Senior Engineer | Labor |  |  | 1
Micheal Roche - Site | Micheal Roche - Site Engineer | Labor |  |  | 1
Josh Mountford - Cre | Josh Mountford - Crew Leader | Labor |  |  | 1
Kai Landgren - Excav | Kai Landgren - Excavator Operator | Labor |  |  | 1
Tug2 | Tug2 | Labor |  |  | 1
PMG124 | PMG124 | Labor |  |  | 1
PMG151 | PMG151 | Labor |  |  | 1
Tug1 | Tug1 | Labor |  |  | 1
PMG182 | PMG182 | Labor |  |  | 1
PMG181 | PMG181 | Labor |  |  | 1
PMG121 | PMG121 | Labor |  |  | 1
Drill | Drill | Labor |  |  | 1
X002 | SMPP | Labor |  |  | 1
E001 | Power Factor Correction (PFC) | Labor |  |  | 1
E002 | MV Switchgear | Labor |  |  | 1
E003 | Distribution Transformers | Labor |  |  | 1
E004 | Diesel Generator | Labor |  |  | 1
E005 | MCC's | Labor |  |  | 1
E006 | LV Distribution Boards | Labor |  |  | 1
E007 | Earthing & Lightning Protection design | Labor |  |  | 1
E008 | Miniature Substations | Labor |  |  | 1
E009 | High mast Poles | Labor |  |  | 1
E010 | Polemount Transformers | Labor |  |  | 1
E011 | 50kW Solar Panel with Lithium BatteriesDistribution Transformers | Labor |  |  | 1
E012 | Protection Grading Study | Labor |  |  | 1
E013 | Step-up Transformer - 5MVA | Labor |  |  | 1
E014 | Electrical Building Services | Labor |  |  | 1
E017 | Grid Power (Mahenge to Site Power Line) | Labor |  |  | 1
G001 | Logistics | Labor |  |  | 1
G002 | General Services | Labor |  |  | 1
G004 | Preliminaries & General | Labor |  |  | 1
G007 | Project Insurance | Labor |  |  | 1
G008 | Owner's Team Costs | Labor |  |  | 1
I001 | Control System | Labor |  |  | 1
I007 | Field Instrumentation - Miscellaneous | Labor |  |  | 1
I009 | Level Instrumentation | Labor |  |  | 1
I010 | Pressure Instrumentation | Labor |  |  | 1
I011 | Conveyor Instrumentation | Labor |  |  | 1
I012 | Flow Meters | Labor |  |  | 1
I013 | Nuclear Instrumentation | Labor |  |  | 1
I017 | Control Valves - Modulating And On Off | Labor |  |  | 1
I021 | ICT Communications Systems & Access Control | Labor |  |  | 1
M003 | Compressors | Labor |  |  | 1
M006 | Crushers | Labor |  |  | 1
M012 | Floatation Cells and Blowers | Labor |  |  | 1
M022 | Mobile Equipment (Vehicles, forklifts, telehandlers ect.) | Labor |  |  | 1
M026 | Thickeners | Labor |  |  | 1
M014 | Reagent Plants | Labor |  |  | 1
M029 | Bagging Plant | Labor |  |  | 1
M035 | Diesel Storage and Supply | Labor |  |  | 1
M040 | Site Fuel Supply and Distribution | Labor |  |  | 1
S004 | Buildings | Labor |  |  | 1
M041 | Mining Early Works | Labor |  |  | 1
M033 | Water Treatment Plant | Labor |  |  | 1
M034 | Potable and Fire water | Labor |  |  | 1
M032 | Sewage Treatment Plant | Labor |  |  | 1
S005 | Medical Facilities / Clinic | Labor |  |  | 1
X001 | Process Plant Earthworks & CivilsBuildings | Labor |  |  | 1
X003 | EC&I | Labor |  |  | 1
X005 | Operations Camp Accommodation | Labor |  |  | 1
X006 | Construction Camp Accommodation | Labor |  |  | 1
X007 | Site Access Roads | Labor |  |  | 1
X008 | Haul and Other Roads | Labor |  |  | 1
X013 | Bulk Earthwork Sitewide | Labor |  |  | 1
X014 | Earthworks and Civils TSF | Labor |  |  | 1
X015 | Boreholes | Labor |  |  | 1
X016 | Camp Management | Labor |  |  | 1
X017 | EPCM Cost | Labor |  |  | 1
X018 | Resettlement Action Plan (RAP) | Labor |  |  | 1
G005 | Board Contingency | Labor |  |  | 1
G009 | RAP Contingency | Labor |  |  | 1
AMP_ENG2 | AMPGARD Electrical Engineer 2 - Rajan | Labor |  |  | 1
AMP_COORD1 | AMPGARD Coordinator 1 - Dave | Labor |  |  | 1
AMP_COORD2 | AMPGARD HV Coordinator 2 - John | Labor |  |  | 1
R-141 | (New Resource) | Labor |  |  | 1
R-142 | EASTERN LEASE NORTH - FS STUDY | Labor |  |  | 1
KUCC-ES | Engineering & Projects | Labor |  |  | 1
Costs | Costs | Nonlabor |  |  | 1
NRS | Underground Development (Trent Thayn) | Labor |  |  | 1
RTKC | RTKC | Labor |  |  | 1
DGO | Drainage Gallery Ore Project | Labor |  |  | 1
JB-4 | Jan Boully | Labor |  |  | 0
UDC | Underground Development Crew | Labor |  |  | 12
Construction | Construction Work Crew | Labor |  |  | 1
UDDC | Underground Dewatering Drilling Crew | Labor |  |  | 2
Dewatering Drill | Dewatering Drilling Footage | Nonlabor |  |  | 28
URDC | Underground Resource Drilling Crew | Labor |  |  | 2
Mine Crew-6 | 6 Man Crew | Labor |  |  | 6
Con-1 | Contractor | Labor |  |  | 3
Mine Crew-1 | 2 Man Elec. Crew | Labor |  |  | 3
Skyline | Skyline Electric Company | Labor |  |  | 1
Dev Footage | Development Footage | Nonlabor |  |  | 1
RTKC Ph1/Ph2 | Budgeted Cost | Labor |  |  | 1
Drill Footage NL | Drill Footage | Nonlabor |  |  | 28
Mine Crew-3 | 3 Man Crew (Miners) | Labor |  |  | 2
DGO 03 | Engineering | Labor |  |  | 0
CC | Construction Crew | Labor |  |  | 2
CE | Construction Electrician Crew | Labor |  |  | 1
AR-S32-63 | CDI - Conveyors | Labor |  |  | 1
AR-S32-65 | Expenses | Nonlabor |  |  | 1
Fab | Offsite Fabrication | Material | Lump Sum |  | 10
BMW D | Boilermaker Resources | Labor |  |  | 1
MF D | Mechanical Fitter Resources | Labor |  |  | 1
TA D | Trade Assistant Resources | Labor |  |  | 1
RIG D | Rigger Resources | Labor |  |  | 1
CW D | Coded Welder Resources | Labor |  |  | 1
RTW D | Painter (RTW) | Labor |  |  | 1
MW-M | Indirects | Nonlabor |  |  | 1
MW-R | Resources | Nonlabor |  |  | 1
P&E | Plant & Equipment | Nonlabor |  |  | 0
BMW D 1 | Boilermaker | Labor |  |  | 1
BMW D 2 | Boilermaker | Labor |  |  | 1
BMW D 3 | Boilermaker | Labor |  |  | 1
BMW D 4 | Boilermaker | Labor |  |  | 1
BMW D 5 | Boilermaker | Labor |  |  | 1
BMW D 6 | Boilermaker | Labor |  |  | 1
BMW D 7 | Boilermaker | Labor |  |  | 1
BMW D 8 | Boilermaker | Labor |  |  | 1
BMW D 9 | Boilermaker | Labor |  |  | 1
BMW D 11 | Boilermaker | Labor |  |  | 1
BMW D 12 | Boilermaker | Labor |  |  | 1
CW D 1 | Coded Welder | Labor |  |  | 1
CW D 2 | Coded Welder | Labor |  |  | 1
CW D 3 | Coded Welder | Labor |  |  | 1
CW D 4 | Coded Welder | Labor |  |  | 1
CW D 5 | Coded Welder | Labor |  |  | 1
CW D 6 | Coded Welder | Labor |  |  | 1
MF D 1 | Mechanical Fitter | Labor |  |  | 1
MF D 2 | Mechanical Fitter | Labor |  |  | 1
MF D 3 | Mechanical Fitter | Labor |  |  | 1
MF D 4 | Mechanical Fitter | Labor |  |  | 1
MF D 5 | Mechanical Fitter | Labor |  |  | 1
MF D 6 | Mechanical Fitter | Labor |  |  | 1
RIG D 1 | Rigger | Labor |  |  | 1
RIG D 2 | Rigger | Labor |  |  | 1
RIG D 3 | Rigger | Labor |  |  | 1
RIG D 5 | Rigger | Labor |  |  | 1
RIG D 4 | Rigger | Labor |  |  | 1
RIG D 6 | Rigger | Labor |  |  | 1
RIG D 7 | Rigger | Labor |  |  | 1
RIG D 8 | Rigger | Labor |  |  | 1
TA D 1 | Trade Assistant | Labor |  |  | 1
TA D 2 | Trade Assistant | Labor |  |  | 1
TA D 3 | Trade Assistant | Labor |  |  | 1
TA D 5 | Trade Assistant | Labor |  |  | 1
TA D 4 | Trade Assistant | Labor |  |  | 1
TA D 6 | Trade Assistant | Labor |  |  | 1
TA D 7 | Trade Assistant | Labor |  |  | 1
TA D 8 | Trade Assistant | Labor |  |  | 1
TA D 10 | Trade Assistant | Labor |  |  | 1
TA D 11 | Trade Assistant | Labor |  |  | 1
FREO CO D-1 | Crane Operator | Labor |  |  | 1
BMW D 10 | Boilermaker | Labor |  |  | 1
CW D 8 | Coded Welder | Labor |  |  | 1
CW D 9 | Coded Welder | Labor |  |  | 1
CW D 11 | Coded Welder | Labor |  |  | 1
MW-BMW | Boilermaker | Labor |  |  | 1
MW-CW | Coded Welder | Labor |  |  | 1
MW-RIG | Rigger | Labor |  |  | 1
MW-MF | Mech Fitter | Labor |  |  | 1
MW-TA | Trade Assistant | Labor |  |  | 1
MW-LAB | Labourer/Peggy/Sentry | Labor |  |  | 1
MW-CN<80T | Franna Operator | Labor |  |  | 1
MW-CAR | Carpenter | Labor |  |  | 1
MW-B&P | Blast & Painter | Labor |  |  | 1
Core-SV | Supervisor - Scaffolder (Core) | Nonlabor |  |  | 1
Truck | Scaffold Truck | Nonlabor |  |  | 0
4x4 | 4x4 Ute | Nonlabor |  |  | 0
TC | Tooling Container | Nonlabor |  |  | 0
20T-F | 20t Franna | Nonlabor |  |  | 0
12s B | 12 Seater Bus | Nonlabor |  |  | 0
40T-C | 40T Crane | Nonlabor |  |  | 0
FREO CO D | Crane Operator | Labor |  |  | 1
Core-Scaff | Scaffolder (Core) | Labor |  |  | 1
Sch | Planner/Scheduler | Nonlabor |  |  | 1
MW-LG | Sheet Metal/Lagging | Labor |  |  | 1
B1-COMM-1 | Ops Readiness (Relaintix) | Labor |  |  | 1
Tug3 | Tug3 | Labor |  |  | 1
Project Engineer --2 | Project Engineer - LSL | Labor |  |  | 1
Mechanical Enginee-2 | Mechanical Engineer - LSL | Labor |  |  | 1
Structural Enginee-2 | Structural Engineer - LSL | Labor |  |  | 1
Document Controlle-6 | Document Controller -LSL | Labor |  |  | 1
HS | H-374558 - Hillside PTA Resources | Labor |  |  | 1
HSP | HS Procurement | Labor |  |  | 1
PTM | Excisting Plant - PTM's | Labor |  |  | 1
CL | Construction Laydown Areas | Labor |  |  | 1
WS | New Workshop Area | Labor |  |  | 1
ALT | Alterations (Civil, Mech , Elec.) | Labor |  |  | 1
HSC | HS Commissioning | Labor |  |  | 1
AR-S32-67 | Kai Males | Labor |  |  | 1
AR-S32-68 | Mags Williams | Labor |  |  | 1
RSE14 | Nick Serpentzis | Labor |  |  | 1
RSE15 | Matt Hoffmann | Labor |  |  | 1
RSE16 | Andrew Wharton | Labor |  |  | 1
RSE17 | Fiona Edgerton | Labor |  |  | 1
RSE18 | Jim Bilessuris | Labor |  |  | 1
RSE19 | Sam Hammond | Labor |  |  | 1
RSE20 | Anna Yang | Labor |  |  | 1
RSE21 | Jim Curtis | Labor |  |  | 1
AR-S32-69 | Ancillary Activities | Labor |  |  | 1
BOD-BM | 01 - BOD Management | Labor |  |  | 1
BOD-BS | 02 - BOD Support Services | Labor |  |  | 1
BOD-BE | 03 - BOD Engineering | Labor |  |  | 1
BOD-BC | 04 - BOD Construction | Labor |  |  | 1
BOD-BM-01 | BOD EXE Program Manager - Jason Cross | Labor |  |  | 1
BOD-BM-02 | BOD Project Manager - Paul Cusack | Labor |  |  | 1
BOD-BM-03 | BOD Brownfields Package Owner - TBC | Labor |  |  | 1
BOD-BS-01 | BOD Cost Controller - Fenny Lo | Labor |  |  | 1
BOD-BS-02 | BOD Planner - Pam Matheson | Labor |  |  | 1
BOD-BS-03 | BOD Contracts Administrator - David Le Roux | Labor |  |  | 1
BOD-BS-04 | BOD Quantity Surveyor - Petro Van Der Merwe | Labor |  |  | 1
BOD-BS-05 | BOD Snr Document Controller - Janice Paton | Labor |  |  | 1
BOD-BS-06 | BOD Document Controller - TBC | Labor |  |  | 1
BOD-BS-07 | BOD Administrator - Karen Miller | Labor |  |  | 1
BOD-EX | 05 - BOD Construction External Support | Labor |  |  | 1
BOD-BE-01 | BOD Engineering Lead - TBC | Labor |  |  | 1
BOD-BE-02 | BOD SMP Field Engineer 01 - TBC | Labor |  |  | 1
BOD-BE-03 | BOD SMP Field Engineer 02 - TBC | Labor |  |  | 1
BOD-BE-04 | BOD Civil Field Engineer - TBC | Labor |  |  | 1
BOD-BE-05 | BOD E&I Field Engineer 01 - Declan Quille | Labor |  |  | 1
BOD-BE-06 | BOD E&I Field Engineer 02 - TBC | Labor |  |  | 1
BOD-BE-07 | BOD Control Field Engineer - TBC | Labor |  |  | 1
BOD-BC-01 | BOD Construction Lead - Mick Hasard | Labor |  |  | 1
BOD-BC-02 | BOD Mobilisation/Training Coordinator - Rob Blyth | Labor |  |  | 1
BOD-BC-03 | BOD HSEC Advisor - TBC | Labor |  |  | 1
BOD-BC-04 | BOD SMP Coordinator 01 (Brownfields) - TBC | Labor |  |  | 1
BOD-BC-05 | BOD SMP Coordinator 02 (Brownfields) - TBC | Labor |  |  | 1
BOD-BC-07 | BOD SMP Coordinator (BOD Facility) - Travis MacIntyre | Labor |  |  | 1
BOD-BC-06 | BOD E&I Coordinator (Brownfields) - TBC | Labor |  |  | 1
BOD-BC-08 | BOD E&I Coordinator (BOD Facility) - TBC | Labor |  |  | 1
BOD-BC-09 | BOD Civil Coordinator (BOD Facility) - TBC | Labor |  |  | 1
BOD-BC-10 | BOD Materials Mngt - SMP Coordinator (BOD Facility) - TBC | Labor |  |  | 1
BOD-EX-01 | BOD Design Engineering - HATCH | Labor |  |  | 1
BOD-EX-02 | BOD Control Engineering - TBC | Labor |  |  | 1
BOD-EX-03 | BOD ED Network Engineering - SEL | Labor |  |  | 1
BOD-CO-01 | BOD Commissioning & OR Lead - Steve Morrow | Labor |  |  | 1
BOD-OR-02 | BOD Master Data Tech 01 - Reliantix | Labor |  |  | 1
BOD-OR-03 | BOD Master Data Tech 02 - Reliantix | Labor |  |  | 1
BOD-OR-04 | BOD In8 Build Tech - Reliantix | Labor |  |  | 1
BOD-OR-05 | BOD Training Specialist - TBC | Labor |  |  | 1
BOD-OR-06 | BOD Technical Writer - TBC | Labor |  |  | 1
BOD-OR-07 | BOD Completions Administrator In8 - TBC | Labor |  |  | 1
BOD-OR-08 | BOD Alcoa SME - TBC | Labor |  |  | 1
BOD-OR-09 | BOD Process Control Engineer - Pablo | Labor |  |  | 1
BOD-OR-10 | BOD Honeywell - External Support | Labor |  |  | 1
BOD-CO-02 | BOD Ops Comm Coordinator - Sarah Martin | Labor |  |  | 1
BOD-CO-03 | BOD Operator 01 | Labor |  |  | 0
BOD-CO-04 | BOD Operator 02 | Labor |  |  | 0
BOD-CO-05 | BOD Operator 03 | Labor |  |  | 0
BOD-CO-06 | BOD Operator 04 | Labor |  |  | 0
BOD-CO-07 | BOD Area Coach - TBC | Labor |  |  | 0
BOD-CO-08 | BOD Comm Process Engineer - Mel Allgeuer | Labor |  |  | 1
BOD-CO-09 | BOD Refinery Engineer - TBC | Labor |  |  | 0
BOD-CO-10 | BOD Mech Comm Engineer - TBC | Labor |  |  | 1
BOD-CO-11 | BOD Mech MAI Specialist - TBC | Labor |  |  | 1
BOD-CO-12 | BOD EI & C Engineer - TBC | Labor |  |  | 1
BOD-CO-13 | BOD Elec MAI Specialist - TBC | Labor |  |  | 1
BOD-CO-14 | BOD Comm Process Control - Karan | Labor |  |  | 1
BOD-CO-15 | BOD Process Control - Sam Boyd | Labor |  |  | 0
BOD-RF | 07 - BOD Ring fenced Contractor | Labor |  |  | 1
BOD-BF | 08 - BOD Brownfields Contractor | Labor |  |  | 1
BOD-NL | BOD - Commodities - Non Labour | Nonlabor |  |  | 1
Hatch Engineering | Use for ALL Studies & Proposals | Labor |  |  | 1
FS2-Del Spons | Delivery Sponsor | Labor |  |  | 1
FS2-Des Coor | Design Coordinator | Labor |  |  | 1
100-PRM | 100 - Project Management | Labor |  |  | 1
19595-TSF22 | TSF22 Sands Tailings Storage Facility | Labor |  |  | 1
S32-TSF22 | S32 TSF22 Manhours | Labor |  |  | 1
ESP-TSF22 | ESP TSF22 Manhours | Labor |  |  | 1
AR-S32-44 | George Tregear | Labor |  |  | 1
AR-S32-45 | Robert Lee | Labor |  |  | 1
AR-S32-46 | Charlotte Watson | Labor |  |  | 1
CLIENTS | CLIENTS | Labor |  |  | 1
PPS-PL2-DIR | S32 PL2 PPS Direct Labour | Labor |  |  | 1
PPS-PL2-DIR-CIV | Civi Direct Labour | Labor |  |  | 12
PPS-PL2-DIR-SMP | SMP Direct Labour | Labor |  |  | 12
PPS-PL2-DIR-PIP | Polywelder Direct Labour | Labor |  |  | 12
PPS-PL2-IND-WID | Working Indirect Labour | Labor |  |  | 12
PPS-PL2-DIE-SUB | Subcontractor Direct Labour | Labor |  |  | 12
Project Engineer - LSL | Project Engineer - LSL | Labor |  |  | 1
Mechanical Engineer - LSL | Mechanical Engineer - LSL | Labor |  |  | 1
Structural Engineer - LSL | Structural Engineer - LSL | Labor |  |  | 1
Document Controller -LSL | Document Controller -LSL | Labor |  |  | 1
Project controls manager | Project controls manager | Labor |  |  | 1
Principal mining engineer | Principal mining engineer | Labor |  |  | 1
Lead mining engineer | Lead mining engineer | Labor |  |  | 1
Senior mine planner | Senior mine planner | Labor |  |  | 1
Junior mine planner | Junior mine planner | Labor |  |  | 1
Principal discipline engineer | Principal discipline engineer | Labor |  |  | 1
Lead discipline engineer | Lead discipline engineer | Labor |  |  | 1
Senior discipline engineer | Senior discipline engineer | Labor |  |  | 1
Engineering draughtsperson | Engineering draughtsperson | Labor |  |  | 1
Ventilation specialist | Ventilation specialist | Labor |  |  | 1
Lead environmental specialist | Lead environmental specialist | Labor |  |  | 1
Senior environmental specialist | Senior environmental specialist | Labor |  |  | 1
Senior techno-economic specialist | Senior techno-economic specialist | Labor |  |  | 1
Lead Hydrogeologist | Lead Hydrogeologist | Labor |  |  | 1
Senior hydrogeologist | Senior hydrogeologist | Labor |  |  | 1
Geotechnical consultant | Geotechnical consultant | Labor |  |  | 1
Other Po | Other Po | Labor |  |  | 1
Principal geotechnical consultant | Principal geotechnical consultant | Labor |  |  | 1
PC % | PC % | Labor |  |  | 1
CIV-DIRECT | Civil Construction - Direct Manhours | Labor |  |  | 1
CIV-INDIRECT | Civil Construction - Indirect Manhours | Labor |  |  | 1
AR-S32-70 | Managing Drafter (Adam) | Labor |  |  | 1

## TASKPRED
pred_task_id | task_id | pred_type | PREDTASK__status_code | TASK__status_code | pred_proj_id | proj_id | predtask__projwbs__wbs_full_name | task__projwbs__wbs_full_name | predtask__task_name | task__task_name | lag_hr_cnt | predtask__rsrc_id | task__rsrc_id | delete_record_flag
Predecessor | Successor | Relationship Type | (*)Predecessor Activity Status | (*)Successor Activity Status | (*)Predecessor Project | (*)Successor Project | (*)Predecessor WBS | (*)Successor WBS | (*)Predecessor Activity Name | (*)Successor Activity Name | Lag | (*)Predecessor Primary Resource | (*)Successor Primary Resource | Delete This Row

## TASKRSRC
rsrc_id | task_id | TASK__status_code | role_id | acct_id | rsrc_type | start_date | end_date | delete_record_flag
Resource ID | Activity ID | (*)Activity Status | Role ID | Cost Account ID | (*)Resource Type | (*)Start | (*)Finish | Delete This Row

## PROJCOST
task_id | cost_name | TASK__status_code | target_cost | act_cost | remain_cost | total_cost | delete_record_flag
Activity ID | Expense Item | (*)Activity Status | Budgeted Cost | Actual Cost | Remaining Cost | At Completion Cost | Delete This Row

## USERDATA
user_data
UserSettings Do Not Edit
DurationQtyType=QT_Day ShowAsPercentage=0 SmallScaleQtyType=QT_Day DateFormat=d/mm/yyyy CurrencyFormat=Australian Dollar